Request For Proposal (RFP)

2026-11001

EXHIBIT A: STATEMENT OF WORK

FOR

STATE TAX ADMINISTRATION RECORD SYSTEM (STARS) SOLUTION

ISSUE DATE

Issued by:

STATE OF CALIFORNIA

State Board of Equalization

Part 1 of the solicitation contains the Bidder and bidding instructions, proposal form instructions, solution requirements and instructions, and all other instructional/compliance information that the Bidder must meet in order to be considered responsive to the solicitation.

Part 2 of the solicitation contains all forms a Bidder must complete and return with its proposal, including the Statement of Work (SOW), administrative forms, qualification forms, requirement responses, and all exhibits/attachments discussed in Part 1.

Disclaimer: The original version and any subsequent solicitation addenda released by the Procurement Officer of this solicitation remain the official version. In the event of any inconsistency between the Bidder’s versions, articles, attachments, specifications, or provisions, the official State version of the solicitation in its entirety shall take precedence.

# Table of Contents

Table of Contents	1

List of Figures	4

List of Tables	5

1	INTRODUCTION	6

2	BACKGROUND AND PURPOSE	6

3	DESCRIPTION OF PROPOSED NEW SYSTEM	6

3.1	STARS SOLUTION FUNCTIONAL BLOCKS	7

3.2	DESCRIPTION OF PROJECT TIMELINE	9

4	TERM OF THE CONTRACT	10

5	AMENDMENT	11

6	LOCATION AND AVAILABILITY	11

7	CONTRACT REPRESENTATIVES	12

8	SOLUTION REQUIREMENTS	13

9	STATE DATA CENTER OR CONTRACTOR HOSTED FACILITY ENVIRONMENT	13

10	STATE’S ROLES AND RESPONSIBILITIES	13

10.1	BOE STARS Project Sponsor	14

10.2	BOE Administration	14

11	CONTRACTOR ROLES AND RESPONSIBILITIES	15

11.1	Contractor Adherence to IT Standards, Guidelines and Policies	15

11.2	KEY STAFF QUALIFICATIONS AND SKILLS	17

11.3	PROJECT MANAGER	17

11.4	TECHNICAL LEAD	18

12	KEY STAFF CHANGES	21

13	ESCALATION PROCESS	22

14	CORRECTIVE ACTION	22

14.1	Notification of Acceptance Problems	22

14.2	Contractor Response to Notice of Acceptance Problem	23

14.3	State Response to Corrective Action Plan	23

14.4	Contractor Revised Corrective Action Plan	23

15	CURE NOTICE	23

15.1	Triggers for a Cure Notice	23

16	CHANGE CONTROL MANAGEMENT PLAN	24

16.1	In-Scope for Change Control	24

16.2	Change Control Activities	24

16.3	Change Request Board	25

17	PROJECT DELIVERABLE OVERVIEW	27

18	CONTRACTOR DELIVERABLES	29

18.1	Project Status Reporting	29

18.2	Maintain and Update STARS Project Management Plans (PMP)	31

18.3	Attend Project Meetings	31

18.4	Perform Ongoing Issues Management and Risks Tracking	31

18.5	Participating in Change Control Process	32

18.6	Participating in the Communications Process	32

18.7	Participating in Organizational Change Management Process	32

18.8	Final Report for Each Stage or Phase	32

18.9	STAGE 1 - INITIATION DELIVERABLES	32

18.10	STAGE II: SYSTEM DESIGN, DEVELOPMENT, IMPLEMENTATION, AND TESTING	45

18.11	STAGE III: PROJECT CLOSE OUT AND WARRANTY PERIOD COMMENCEMENT	72

19	DELIVERABLES EXPECTATION DOCUMENT	76

19.1	TRANSMITTAL OF DELIVERABLES	77

19.2	DELIVERABLE ACCEPTANCE DOCUMENT	77

19.3	DELIVERABLE REJECTION & ACCEPTANCE	80

19.4	GENERAL DELIVERY AND REVIEW PROCESS	80

20	DATA HANDLING AND OWNERSHIP	84

20.1	DATA SOURCES, DATA ENTRY, AND HANDLING	86

20.2	DATA ADMINISTRATION AND MANAGEMENT	87

20.3	DATA SHARING, ACCESSIBILITY, AND ACCESSIBILITY PERFORMANCE	88

20.4	RELATIONAL DATABASE OR SQL QUERIES	88

20.5	RANDOM UNSTRUCTURED DATA SEARCH	88

21	SYSTEM REPORTING	88

22	SECURITY	89

22.1	SECURITY AND DATA PROTECTION	89

22.2	PROTECTION OF CONFIDENTIALITY	90

22.3	ADMINISTRATIVE SAFEGUARDS	91

22.4	MANAGEMENT SAFEGUARDS	92

22.5	USAGE, DUPLICATION, AND REDISCLOSURE SAFEGUARDS	93

22.6	PHYSICAL SAFEGUARDS	93

23	DISASTER RECOVERY	94

24	DELIVERY (HARDWARE AND SOFTWARE)	95

24.1	HARDWARE AND SOFTWARE NEEDS	95

24.2	ESCROW SOURCE CODE	97

24.3	COMPATIBILITY AND INTERFACE	98

24.4	SYSTEM INSTALLATION	100

24.5	TECHNOLOGY REFRESH	102

25	SYSTEM TESTING AND ACCEPTANCE PROCEDURES	102

25.1	ACCEPTANCE TEST DEFECT EXIT	105

26	FINAL STATE ACCEPTANCE	106

27	TRANSITION OF OPERATION TO STATE	107

28	KNOWLEDGE TRANSFER AND/OR TRAINING	107

28.1	Technical STARS Solution Training, Instruction, and Guidance	107

28.2	Train-the-Trainer	108

29	MAINTENANCE AND OPERATIONS (M&O)	108

30	HELP DESK	109

31	INSURANCE REQUIREMENTS	109

32	WARRANTY	112

33	SERVICE LEVEL AGREEMENTS (SLAs)	114

34	LIQUIDATED DAMAGES	138

34.1	LIQUIDATED DAMAGES CAP	138

34.2	PAYMENT OF LIQUIDATED DAMAGES	139

34.3	CALCULATION OF LIQUIDATED DAMAGES	139

35	UNANTICIPATED TASKS	139

36	INFORMATION TECHNOLOGY GENERAL PROVISIONS – CLOUD  COMPUTING SERVICES DGS PD 402-ITGP CLOUD (02/20/2025)	141

37	MISCELLANEOUS	141

37.1	SUBCONTRACTORS	142

38	GLOSSARY OF TERMS	142

39	HYPERCARE ACTION LIST	143

# List of Figures

Figure 1: BOE STARS Solution Conceptual Solution	7

Figure 2: State Change Control Process Flow Diagram	25

Figure 3: Conceptual STARS Solution Implementation and Integration Plan	39

Figure 4: Tax and Valuation Realtime Computation Interaction Visualization	57

Figure 5: Solution Centralized Storage Diagram With Data Migration	58

Figure 6: Data Handling Process Per Data Governance	84

Figure 7: Data Quantities and Migration Flow	84

Figure 8: State Data Management Plan and Flow	87

Figure 9 State System for Pilot	101

# List of Tables

Table 1 Conceptual STARS Solution Functional Block Intent Description	7

Table 2 Project Timeline	9

Table 3 Project Meeting Venues	26

Table 4 Project Deliverable Overview	28

Table 5 External Data Sources	36

Table 6 State Storage Matrix with Storage Growth Estimates	85

Table 7 Acceptance Test Defect Exit Criteria	105

Table 8 Service Level Agreements and Liquidated Damages	114

Table 9 Service Level Agreements (SLA) and Liquidated Damages for Defect	137

Table 10 Hyper Care Service Level Agreement (SLA)	145

# INTRODUCTION

This Statement of Work (SOW) describes the services to be provided by the Successful Proposer, hereinafter referred to as the “Contractor”. The Contractor agrees to provide the State Board of Equalization (BOE) with a cloud-based, fully integrated tax administration system as described in this Agreement. Pursuant to the Government (Gov.) Code section 15570.28, the California Department of Tax and Fee Administration shall provide BOE with administrative services relevant to this Contract. The California Department of Tax and Fee Administration (CDTFA) and BOE collectively shall be referred to as the “State”. The BOE and Contractor shall be referred to as the “Parties”. All services rendered by the Contractor pursuant to this Agreement are based on fixed Deliverables. The Contractor is responsible for completing all tasks, work products, and all services as detailed herein at the costs provided in EXHIBIT E: COST WORKBOOK.

"Contractor" refers to the firm or company that shall provide the staffing to perform the services.  "Staff" refers to the Contractor's staff who will perform the services. The terms "Contract" and/or “Agreement” will be used interchangeably.

# BACKGROUND AND PURPOSE

The Contractor shall design, develop, implement, and transition to the BOE the State Tax Administration Record System Solution (STARS Solution). The STARS Solution shall be a cloud-based, fully integrated tax administration system to ensure the accurate and efficient computation of $167.2 billion in property value annually, which results in $2.8 billion in property tax revenues collected by 58 California counties.

The Contractor is responsible for developing, testing, and deploying the STARS Solution in a staged approach. The STARS Solution shall meet the State’s current business needs with flexibility to accommodate future changes efficiently.

The Contractor agrees to perform the services described herein and as set forth in the Contractor’s Proposal, State’s Request for Proposal RFP No. 2026-11001, and subsequent addenda. These documents are hereby incorporated by reference and are part of this Agreement.

This Agreement defines the tasks needed to design, develop, implement, and maintain the STARS Solution. The SOW also establishes the State’s and the Contractor’s responsibilities for completing these tasks during the term of the Contract.

# DESCRIPTION OF PROPOSED NEW SYSTEM

The Contractor shall implement the STARS Solution, an enterprise cloud hybrid solution comprising Modified Off-the-Shelf (MOTS), Commercial Off-the-Shelf (COTS), and custom software, to create a fully integrated tax administration system. The Contractor shall, under their Proposal accepted by the State, include a combination of COTS, MOTS, and/or custom software coding to implement the STARS Solution. Custom software coding will be needed where MOTS or COTS software cannot satisfy the project requirements to deliver the State solution in full, as illustrated:

Figure 1: BOE STARS Solution Conceptual Solution

## STARS SOLUTION FUNCTIONAL BLOCKS

The STARS Solution shall include the following functional blocks to perform key functions for the State’s tax administration purposes:

Table 1 Conceptual STARS Solution Functional Block Intent Description

| Functional Block | Intended High-Level Purpose |
| --- | --- |
| Assessee/Customer e-File Web Portal | - Assessee/Customer service web account to do State business - Provide an easy means to file tax schedules and forms via uploads or manual entry filing |
| Board Roll and PRC valuation and tax computation per Industry Type by business rules | - Perform tax and valuation computations as the assessee files their tax schedules and forms |
| Case Management | - Provide better service for the assessee account - Research the assessee account as needed for business purposes - Send communications to the assessee |
| Going Paperless, Mass Paper Mailing, and e-Mailing | - Reduce paper in the tax filing process - Reduce USPS paper letter mailing - Save postage, paper, and printing expenses |
| Data Governance Implementation | - Facilitate Data Migration - Guide Data Validation & Cleansing Process - Metadata Strategy Implementation - Institute Data Catalog Process - Implement BOE Data Policy |
| Ad hoc Report Generation and Dashboarding (tasks and workflows) | - Generate the tax “Board Roll” - Create reports - Create letters - Track tasks and workflow progress - Dashboard BOE KPI’s (Key Performance Indicators) |
| Architected Centralized Storage | - Provide a centralized data and file storage of all of the State tax administration needs - Be able to search for any account data needed - Have scalable storage |
| Broadband Connectivity for Real Property Field Work | - Provide a convenient means for BOE field auditors and appraisers to upload land pictures and notes via their cellular phones to the STARS solution for the account |
| Appraisals/Audits Efficiencies | - Speed up audit and appraisal work - Manage audit and appraisal assignments and respective property parcels - Create a new Parcel/Map "Indexing/grouping" System into Work Assignments |

## DESCRIPTION OF PROJECT TIMELINE

This section describes the high-level project timelines that will coordinate and align the Contractor's tasks, activities, and deliverables. The project implementation timeline is eighteen (18) months.

The actual project implementation timeline will be defined by the vendor’s project manager with State approvals, but the State's projected timeline is as follows:

Table 2 Project Timeline

| No. | Project Task | Estimated Task Duration (Months) |
| --- | --- | --- |
| 1 | - Vendor Team Onboarding and Training - Project pre-planning documents | 1.5 months |
| 2 | Solution Design and Development | 3 months |
| 3 | Cloud Solution Implementation | 5 months |
| 4 | Test: - System - Functional, Integration, and Connectivity - Performance and Loading - Security and Access | 2.5 months |
| 5 | Training: - System Operation, Administration, and Maintenance - User | 0.5 months |
| 6 | State User Acceptance Testing (UAT) and Assessee Pilot Testing (APT) | 2 months |
| 7 | Solution Modifications and Optimizations From UAT Feedback | 1.5 months |
| 8 | Regression Testing | 1.5 months |
| 9 | Solution Acceptance and Handoff to State | 0.5 months |
| Total |  | 18 months |

The following three (3) Stages parse out the organization of the SOW over the course of this Project:

Stage 1 – Initiation

Stage 2 – System Design, Development, Implementation, and Testing

Stage 3 – Project Closeout and Warranty Period Commencement

Each of these Stages will require the development of specific Deliverables along with ongoing activities and services that the Contractor must conduct and perform. Each Deliverable requires the State to review and accept as identified in SECTION 19: DELIVERABLE ACCEPTANCE PROCESS.

# TERM OF THE CONTRACT

Effective upon approval of CDT, Office of Statewide Technology Procurement (OSTP), the base term of the Contract is two (2) years.

The State, at its sole discretion, may exercise its option to execute one (1), one (1) year extension for a maximum Contract term of three (3) years (includes Base Contract term plus optional extension). Should the State choose to exercise the optional extension, the Contractor will be notified in writing by the State at least 120 days in advance of the commencement of the option period. The extension will be effective upon execution by the Parties and approval by the CDT-OSTP.

The Contractor shall not be authorized to deliver goods and/or commence performance of services described in this Agreement prior to the effective date of the contract. Any delivery of goods and/or performance of services by the Contractor that is commenced prior to the effective date shall be at no cost to the State.

The State is not obligated to use any or all of these options. The Agreement is of no effect unless approved by CDT-OSTP and no work shall begin before full execution of the Agreement.

# AMENDMENT

Consistent with the terms and conditions of this Agreement, and by mutual consent of both Parties, this Agreement may be amended. Any Amendment is subject to approval by the CDT-OSTP pursuant to Public Contract Code (PCC) section 12100. No amendment or variation of the terms of this Agreement shall be valid unless made in writing, signed by the Parties, and approved by CDT-OSTP if required. No oral understanding not incorporated in the Agreement is binding on either of the Parties.

# LOCATION AND AVAILABILITY

All Contractor work shall be performed at the address below:

State Board of Equalization

160 Promenade Circle, Suite 200

Sacramento, CA 95834

The State will allow the Contractor to propose remote Staff, based in the continental United States. The State will provide a set of collaboration tools to facilitate remote development. No offshore remote work shall be allowed under this Agreement.

The Contractor shall work onsite and/or telework during the work schedule as approved by the BOE STARS Project Sponsor. All the State software and equipment usage is restricted to activities specifically related to the performance of this Agreement. The State does not permit non-State computers and devices access to the State local area network. The State does not permit work from, nor for, equipment to be taken offshore for this Agreement.

Normal hours of access are Monday through Friday, 7:00 a.m. to 5:00 p.m., excluding State holidays. The Contractor is required to perform work duties within the normal hours of work. The Contractor must make prior arrangements and receive approval from the State for access to the project office outside these normal working hours. State holidays are listed on the California Department of Human Resources (Cal HR) website at the link below, and are subject to change: http://www.calhr.ca.gov/employees/Pages/state-holidays.aspx

# CONTRACT REPRESENTATIVES

All notices required by, or relating to, this Agreement shall be in writing and shall be sent to the Parties of the Contract at the addresses set below.

Should Contract Representative information change, written notice with the updated information shall be sent by the changing Parties in writing as soon as the changing Party is aware of the staffing changes. The written notice shall be via mail or email and will contain the new Contract Manager’s name, mailing address, email address, and telephone number and shall be sent by the changing Parties no later than ten (10) business days after the change.

The State Board of Equalization Contract Representatives during the term of this Agreement will be:

| PROJECT/PROGRAM CONTRACT REPRESENTATIVES |  |  |  |
| --- | --- | --- | --- |
| State Board of Equalization |  | Contractor: TBD |  |
| Name: | TBD | Name: | TBD |
| Title: | TBD | Title: | TBD |
| Telephone Number: | TBD | Telephone Number: | TBD |
| E-mail Address: | TBD | E-mail Address: | TBD |

Direct all Contract inquiries to:

| CONTRACT REPRESENTATIVES FOR INQUIRIES |  |  |  |
| --- | --- | --- | --- |
| California Department of Tax and Fee Administration |  | Contractor: TBD |  |
| Name: | TBD | Name: | TBD |
| Title: | TBD | Title: | TBD |
| Telephone Number: | TBD | Telephone Number: | TBD |
| E-mail Address: | TBD | E-mail Address: | TBD |

All inquiries during the term of this Agreement will be directed to the Contract contacts listed above. Either Contract Representative may be changed by written notice without a formal amendment to this Agreement.

# SOLUTION REQUIREMENTS

The Contractor shall adhere to all Solution requirements identified in EXHIBIT C: FUNCTIONAL AND NON-FUNCTIONAL REQUIREMENTS.

# STATE DATA CENTER OR CONTRACTOR HOSTED FACILITY ENVIRONMENT

The State must receive an end-to-end solution from the Contractor. The STARS Solution must be hosted in a cloud environment as directed by the State CDT's Cloud First Policy, Technology Letter (TL) TL 14-04 (revision 08/2014, or latest version) and TL 23-03 (revision 10/2023, or latest version). All required hosting environments must be in the Continental United States. The Contractor must develop the STARS Solution in compliance with the provisions listed on the TECH 213 Standard Agreement, the State Administrative Manual (SAM) 4983 (revision 08/2017, or latest version) and SAM 4983.1 as part of the Cloud Computing policy (revision 08/2020, or latest version).

# STATE’S ROLES AND RESPONSIBILITIES

The State is responsible for the following roles and responsibilities.

## BOE STARS Project Sponsor

The State shall provide a BOE STARS Project Sponsor to oversee and manage this Agreement. The BOE STARS Project Sponsor shall:

### Work with the Contractor to facilitate the successful completion of the Contractor’s obligations.

### Review and have authority to provide Acceptance of Deliverables in accordance with SECTION 25: SYSTEM TESTING AND ACCEPTANCE PROCEDURES.

### Review and have authority to accept staffing changes in accordance with SECTION 12 KEY STAFF CHANGES.

### Be responsible for the overall management of the Governance Structure that includes the Program Management Office (PMO) and serves as the primary contact.

## BOE Administration

### The State shall provide subject matter experts knowledgeable of relevant State law, processes, policies, and regulations.

### The State shall maintain a PMO to manage program operations, including staffing changes, budget/fiscal controls, contract management, State reporting, and recruitment.

### The State shall administer and maintain the STARS Solution Document Library for deposit of Deliverables and other Project artifacts. The STARS Solution Document Library will be comprised of electronic documents.

### The State shall provide one (1) laptop per person with relevant software and network access for Contractor staff to work onsite and/or telework during the work schedule approved by the BOE STARS Project Sponsor.  The networked computer(s) will have Microsoft Windows Explorer, Microsoft Office, Google Chrome, and other supporting software installed. Use and possession of the laptop(s) shall be subject to the State and State usage policies.

### The State shall provide workspace, printers, and copiers.

### The State shall continue to support its existing legacy systems until no longer needed.

### For work performed remote of the State premises, the State shall provide virtual desktop and/or Virtual Private Network (VPN) access to the Contractor staff for remote access when needed.

### The BOE STARS Project Sponsor (or designee) will manage the performance and availability of the State personnel under this Agreement and is the sole individual to whom all official communication relating to this Agreement will be addressed by the Contractor.

### The State shall lead and manage the overall Organization Change Management; Organization Change Management activities, business process re-engineering and business process training.

### The State shall designate an Organization Change Management Lead to manage, coordinate and execute Organization Change Management activities.

### The State shall lead coordination with external stakeholders with inputs from the Contractor.

### The State shall provide up to three (3) licenses for GitHub to the Contractor.

### The State shall provide one (1) license for a code scanning tool.

### The State shall assist Contractor in its ongoing data cleansing and validation.

### The State shall, upon Contract start, provide information and background knowledge regarding the State data cleansing efforts and current data quality rules.

# CONTRACTOR ROLES AND RESPONSIBILITIES

The Contractor is responsible for the following roles and responsibilities.

## Contractor Adherence to IT Standards, Guidelines, and Policies

The Contractor shall adhere to the State’s minimum required IT standards, guidelines, and policies. The State Contract Manager will provide the Contractor with copies of all relevant State policies, which shall be signed by the Contractor and all lead and/or primary resources providing services under this Agreement and returned to the State Contract Manager within five (5) business days of the Contract start date. In addition, the Contractor shall abide by the same standards and policies as State staff, including but not limited to the following regulations, standards, guidelines, and policies, which serve as the referenced minimum criteria:

### State Policies: Political Activities in the Workplace, Email, Internet/Intranet Access and Usage, Drug-Free Workplace, Anti-Discrimination Harassment Retaliation Policy, and Internal Privacy Policy.

### State Security Policies.

### Additional policies as adopted by the State during the duration of the Agreement.

### Background investigations, fingerprinting, the State security training, and signing the State Conflict of Interest (COI) form.

### Administrative and related service-provided policies and procedures.

### The Centers for Disease Control and Prevention (CDC) guidelines for infection control.

### Personal safety relating to fire, electrical hazards, disaster preparedness, hazardous materials, equipment safety, and management.

### The Contractor certifies that it has appropriate systems and controls in place to ensure that State funds will not be used in the performance of this Agreement for the acquisition, operation, or maintenance of computer software in violation of copyright laws.

### The Contractor shall cooperate with any third party contracted by the State, as identified by the State.

### The Contractor shall store, package (draft and final copies) and deliver electronic copies of all documentation, Deliverables, project artifacts and other materials for deposit into the STARS Solution GitHub library or other State designated STARS Solution Document Library.

### The Contractor shall provide access to the State and designees, including but not limited to CDT personnel, all Deliverables in development for review within ten (10) business days of request.

### The Services provided by the Contractor to accomplish the SOW shall be under the control, management, and supervision of the Contractor, including Services provided by any Subcontractors and off-site Contractor staff (if applicable).

### For all Project-related activities, the Contractor and all Contractor staff must have the ability to interact with State team members via virtual tools, including Zoom, Webex, and/or Microsoft Teams, at the State's discretion, during State Business Days throughout the term of the base Agreement and M&O contract, including Amendments, if any. At the State's discretion and only for specified meetings, telephone interactions may be acceptable in lieu of virtual meetings. State Business Days are defined as Monday – Friday (7:00 AM – 5:00 PM Pacific Time [PT]), excluding State Holidays as defined by the California Department of Human Resources at: http://www.calhr.ca.gov/employees/Pages/state-holidays.aspx

### The Contractor is responsible for updating and maintaining all the Deliverable artifacts.

## KEY STAFF QUALIFICATIONS AND SKILLS

The Contractor shall provide the necessary Staff to successfully perform all services and meet the requirements set forth in the SOW. There are two (2) Key Staff identified as part of this Agreement. For purposes of this Agreement, the term “Key Staff” refers to Contractor personnel deemed by the State to be essential to the Contractor’s satisfactory performance of the requirements contained in this Agreement. The Contractor shall comply with all staffing requirements identified within this Agreement. The Contractor shall ensure that the number of appropriately qualified and trained personnel, as approved by the State, is always available to provide timely services required under the Contract.

## PROJECT MANAGER

The duties and responsibilities of the Contractor's Project Manager include, but are not limited to, the following:

### Execution and overall management of the Contract.

### Manage all Contractor resources and activities outlined in the Contract.

### Manage, resolve, and document risks and issues.

### Manage Contract scope, schedule, timeline, budget, and deliverables.

### Engage with the STARS Solution stakeholders and executives on a day-to-day basis to ensure the project receives stakeholder commitment and support.

### Provide direction to all Contractor resources to ensure that all Contractor staffing and project resources are met, as required, and maintain accountability for Contractor Staff and resource performance.

### Report to the BOE STARS Project Sponsor.

### Prepare and assist the BOE STARS Project Sponsor in developing and presenting reports for meetings and discussions.

### Identify and bring forward options that will provide the highest value to the State.

Refer to RFP ATTACHMENT 15.1 Project Manager Qualifications form, for experience requirements.

## TECHNICAL LEAD

The duties and responsibilities of the Technical Lead include, but are not limited to, the following:

### Manage all design, development, integration and implementation tasks, activities and resources.

### Lead and manage all development activities and ensure that the application meets the STARS Solution Requirements.

### Manage all Program Increment tasks and activities.

### Lead and manage development efforts to deliver Solution technical requirements, design, configuration, customization, features testing, and implementation.

### Coordinate release content and effort based on the backlog, application programming interface, third party applications and updates.

### Manage risks and resolve issues that affect system performance, release scope, schedule, and quality.

### Coordinate ADA compliance, data migration, data integration, security, testing and all other areas with the respective Leads for these areas.

### Plan and manage all development and release activities.

### Manage configuration management methodologies, technologies, and needs.

### Oversee and conduct release readiness reviews.

### Oversee and ensure that the documentation of key information, such as build and release procedures, dependencies, and defect fixes, is reflected and documented accurately in the appropriate Deliverables documentation.

### Lead the day-to-day activities of the Contractor technical staff who are engaged in the technical development and management of the STARS Solution.

### Manage technical resources to ensure that all technical issues are resolved.

### Assess proposed design alternatives based on all identified constraints, such as cost, schedule, usability, and reliability.

### Develop solution components that protect the STARS Solution and data by establishing policies, practices, and tools that prevent unauthorized access, unauthorized use, disclosure, modification, or disruption.

### Develop and deliver the STARS Solution security design and oversee the Contractor’s implementation of security roles, separation-of-duties analysis rules, security role provisioning solutions, and application security scanning.

### Ensure security-related STARS Solution functions comply with the Contract requirements.

### Manage the creation and maintenance of user accounts, roles, as well as managing role hierarchy, function security policies, data security policies, and provisioning.

### Manage security features, such as encryption and masking sensitive data, such as credit card information, PII, and bank account numbers.

### Identify and resolve all weaknesses and vulnerabilities in the STARS Solution.

### Perform security and penetration testing of all infrastructure and application components.

### Create a security test plan for infrastructure and all application components. Map security test plan items to NIST controls.

### Coordinate Contractor’s response to information security vulnerabilities, incidents, breaches, audit requests and reporting.

### Provide security implementation plan and architecture topology in advance of code deployment.

### Work with the other resources, including the Database resource and Solution/Cloud Architect, to ensure that all security configurations and policies are in place.

### Work with the Contractor’s Test resource to ensure that all security testing, including penetration testing of all infrastructure and application components, complies with NIST requirements.

### Plan and lead implementation of accessibility standards, ensuring compliance with Web Content Accessibility Guideline (WCAG) 2.2, meeting A/AA standards, Section 508 of the United States Rehabilitation Act, and ADA guidelines.

### Participate in design sessions with various Project team members to ensure that accessibility requirements and considerations are considered early in the design process.

### Collaborate with Contractor developers on accessibility principles, solution development, code review, issue remediation, and best practices, including but not limited to, providing resources and leadership on accessible design, color contrast, error handling, usage of Accessible Rich Internet Applications (ARIA) attributes, document accessibility, and testing.

### Actively participate in all aspects of the software development lifecycle (SDLC), and resolve accessibility issues from design, development, testing, through deployment.

### Lead accessibility audit of the design and the solution, identifying accessibility issues, areas for improvement, and recommending appropriate fixes.

### Lead automated and manual accessibility testing, collaborating with Test resources, using tools utilized by people with disabilities, including but not limited to keyboard navigation, screen reader testing, semantics testing, color contrast, focus, reading order, alternative text, language and reading level testing, and document testing.

### Develop reports and log defects with detailed findings, including the type of violation, reference to WCAG guidelines and other applicable laws, screenshots, severity level, and recommendations for remediation.

### Perform regression testing to ensure accessibility bug fixes and document the results.

### Co-ordinate all activities with designers, developers, business users, project managers, and stakeholders, and provide guidance on accessibility best practices and techniques, including applicable laws and regulations, to ensure that accessibility is considered and implemented throughout the Project lifecycle.

Refer to RFP ATTACHMENT 15.2 Technical Lead Qualifications form for experience requirements.

# KEY STAFF CHANGES

The Contractor shall commit to the continuing availability and participation of the Contractor's staff filling two (2) Key Staff Roles, to the extent of the Contractor's control, for the duration of the Contract or for their proposed period of involvement (as defined in the State approved Project Management Plan).

The State recognizes that changes to Key Staff may be necessary and in the best interest of the State; however, advance notice of the proposed change and the reasons for such change must be made to the State within ten (10) State business days prior to the existing Key Staff’s departure. If this should occur, the BOE STARS Project Sponsor or designee must approve any changes to the Key Staff prior to the termination of the existing Key Staff and retention of the new Key Staff. This also includes any changes made between submittal of the proposal and the actual start of the Contract.

All approved replacement staff must be available to begin working on the Contract no later than five (5) State business days following the State’s approval.

The Contractor may request changes to staff designated to fill any one of the two (2) Key Staff roles by submitting a written request to the BOE STARS Project Sponsor using RFP ATTACHMENT 18: KEY STAFF REPLACEMENT FORM. The request must include a staff qualifications form, customer references, and a current resume for each replacement staff member. The State may, at its sole discretion, request additional information to substantiate whether the replacement staff complies with the RFP requirements and may request an interview. The State shall have the right to contact references, evaluate information provided, and determine if the Key Staff candidate is acceptable.

Within seven (7) State business days after receipt of the request or additional information, the BOE STARS Project Sponsor will respond, in writing, to indicate approval or rejection of the proposed replacement staff.

If any of the proposed replacement staff designated to fill any one of the two (2) Key Staff roles is rejected, the Contractor shall work diligently to promptly provide a qualified replacement to the State for approval within twenty (20) State business days of the rejection.

The State will notify the Contractor concerning any issues and/or concerns the State has regarding performance that may include, but are not limited to, poor performance, lack of experience, unprofessional behavior and/or harassment in the workplace (subject to compliance with applicable law and State policies), and violating any State policies and procedures agreed to by the Contractor at the start of the Project. The Contractor will have ten (10) State business days in which to remedy the State issues and/or concerns. If Contractor has not remedied the State issues and/or concerns regarding the Contractor staff within this period, the State reserves the right in its sole discretion to require the Contractor to replace such staff at any time thereafter. Key Staff shall be replaced according to the procedure set forth above. The State will notify the Contractor in writing when exercising that right. The Contractor shall provide a replacement candidate no later than twenty (20) State business days of such notification.

# ESCALATION PROCESS

The Parties acknowledge and agree that Project-related problems or issues may arise, and that such matters shall be brought to the State’s attention. Problems or issues shall be reported in regular status reports or in-person meetings. However, there may be instances where the severity of the problem justifies escalated reporting. To this extent, the BOE STARS Project Sponsor and CDT-OSTP shall determine the level of severity and notify the appropriate State staff, as set forth below. The State staff shall be notified, and the time taken to report the problem or issue shall be at a level commensurate with the severity of the problem or issue. The State personnel include, but are not limited to, the following:

- First level, BOE Contract Manager

- Second level, BOE Program Director

- Third level, CDTFA Chief Information Officer

The Contractor will advise the State Contract Manager of any intended escalation. If the Contractor is not entirely satisfied that the State is making its best efforts to resolve any problem or issue in an appropriate period, then the Contractor must escalate the problem or issue to the next appropriate level.

# CORRECTIVE ACTION

The State will be the sole judge of the acceptability of all work performed and all work products produced by the Contractor as a result of this Agreement. Should the work performed, or products produced by the Contractor, fail to meet the State ’s minimum conditions, requirements, specifications, and/or guidelines, the following process will be employed, except as superseded by other binding processes:

## Notification of Acceptance Problems

The State will notify the Contractor in writing within ten (10) business days after discovery of any acceptance problems by identifying the specific inadequacies and/or failures in the services performed and/or the products produced by the Contractor unless otherwise agreed upon by the State in the approved schedule.

## Contractor Response to Notice of Acceptance Problem

The Contractor will, within five (5) business days after initial problem notification, respond to the State by submitting a detailed explanation describing precisely how the identified services and/or products adhere to and satisfy all applicable requirements, and/or a proposed corrective action plan to address the specific inadequacies and/or failures in the identified services and/or products.

## State Response to Corrective Action Plan

The State will, within five (5) business days after receipt of the Contractor’s detailed explanation and/or proposed corrective action plan, notify the Contractor in writing whether it accepts or rejects the explanation and/or plan. If the State rejects the explanation and/or plan, the Contractor will submit a revised corrective action plan within three (3) business days of notification of rejection.

## Contractor Revised Corrective Action Plan

The State will, within three (3) business days of receipt of the revised corrective action plan, notify the Contractor in writing whether it accepts or rejects the revised corrective action plan proposed by the Contractor.

If a Contractor’s project component or deliverable is rejected three (3) times by the State, the Cure Notice process will follow.

# CURE NOTICE

The State will issue a Notice to Cure to inform the Contractor in the event the Contractor fails to meet and/or complete a Project work product, component, requirement, and/or Deliverable. Upon issuance, the cure notice will specify the timeline in which the Contractor must remedy the condition. If the condition is not corrected within the period specified, the cure note states that the Contractor may face termination of its Agreement by default as stated in INFORMATION TECHNOLOGY GENERAL PROVISIONS – CLOUD COMPUTING SERVICES DGS PD 402-ITGP CLOUD (REVISED 2/20/2025), SECTION 16.3, TERMINATION FOR DEFAULT(SEE LINK IN SECTION 36).

## Triggers for a Cure Notice

Cure notice may be triggered by any of the following conditions, or other conditions that arise in performance of the Agreement, including but not limited to:

- The Contractor continues to miss agreed-upon deadlines.

- Quantifiable evidence is lacking to show that work is being accomplished.

- The quality of tasks does not meet the STARS Solution’s standards

- The Contractor’s project component of deliverables is rejected three (3) times.

- The Contractor is non-responsive to the STARS Solution requests, and/or

- The Contractor does not replace key personnel, as outlined in SECTION 12. KEY STAFF CHANGES.

# CHANGE CONTROL MANAGEMENT PLAN

The scope of the BOE Change Control Management Plan is limited to requests impacting the STARS Solution Project. The Change Control Management Plan has the complete change control process. The overall changes to the STARS Solution project are governed by the decision levels and escalation hierarchy delineated in the STARS Project Management Plan.

## In-Scope for Change Control

The following is subject to Change Control:

- Feature enhancement requests

- Training sessions

- User Access / Permissions

- Machine Learning

The Change Control Process (CCP) for the STARS Solution describes the actions required to change the Solution’s approved and baseline documents, schedule, scope, costs, resources, and contracts. A formal CCP aids management by defining the process of requesting, analyzing, approving, monitoring, and controlling change. Adhering to the CCP prevents unauthorized changes and ensures proper analysis and input. The STARS Project Manager will work with the change request (CR) originator to move the CR through the CCP.

## Change Control Activities

The high-level CCP includes but is not limited to the following activities:

### Submit – How STARS Project team members submit CRs into the STARS project TEAMS site.

### Analyze – How the STARS CR originator coordinates and documents the impacts of CRs on the Project's baseline.

### Approve – How the CR was reviewed and approved by those with the STARS Change Control authority.

### Implement – How the STARS Project team members will execute CR closeout activities.

### Close – How the STARS Project Manager will execute and drive the CR closeout activities (updating project baselines, generating action items as necessary, verifying the implementation, and closing the CR Form).

### Monitor and Control – How the STARS Project Manager will execute tracking, monitoring, reporting, and communicating CRs.

The CCP will describe how the STARS Project will monitor and control the Project’s CRs by defining a formal and repeatable process for effective and efficient organizational change management. The objective of the CCP is to ensure that changes introduced to the Project have been appropriately evaluated for impact and risks to ensure Project quality.

Figure 2: State Change Control Process Flow Diagram

The Contractor may be invited to participate in the Project Change Control meetings as needed.

## Change Request Board

The Change Request Board (CRB) comprises Voting and Non-Voting members. Voting members participate in all CRB meetings and decide the ultimate disposition of CRs. Non-voting members attend meetings upon request and provide an impact assessment to assist voting members in making decisions on Requests. The CRB Voting and Non-voting composition will have representative(s) from the State, CDTFA, and CDT-Project Approvals & Oversight (PAO).

The BOE STARS Project Sponsor has final authority on all requests and must approve the Change Control Report as the last step in the approval process.

Any member or attendee may send a representative to vote on their behalf or serve as a Subject Matter Expert (SME). This practice is encouraged if attendees cannot attend since a quorum (three (3) of five (5) voting members) must be present to hold the meetings.

The Project Change Control Board consists of the following:

- BOE STARS Project Sponsor(s) 	Voting Members

- BOE Business Manager(s)		Voting Members

- BOE Data Owner			Voting Member

- CDTFA Technical Manager		Voting Member

- CDFTA Project Manager		Non-Voting Member

- CDTFA SME 				Non-Voting Member

- BOE SME 				Non-Voting Member

- CDT-PAO Representative		Non-Voting Member

The Project will use a spreadsheet as a Change Request tracking mechanism to track the status and implementation of Change Requests (CR), and the spreadsheet will be maintained on a TEAMS site.

Change Requests reporting will be communicated and updated via the weekly Project meetings.

Table 3 Project Meeting Venues

| Title | Frequency | Content | Usage |
| --- | --- | --- | --- |
| Opened, Pending, and Approved CRs | Regularly Scheduled Team Meetings (Weekly) | Summary of the CRs that have been opened are still pending and have been approved since the last reporting. Root Cause Analysis (RCA) will be done as needed. | Keeps the Project team and Stakeholders informed about the changes being made |
| CR Implementation Status | As Completed | Lists all CRs approved for implementation, activities to implement, estimated completion date, and current status. | Used by management, the CRC, and CR Owners to track CR implementation |
| Metrics Report | Monthly | Identifies the total number of CRs opened, approved, and pending. Include aging statistics that show how long it takes to approve a CR, the duration at each stage of the process, the number of CRs referred to the CCB and the Executive Steering Committee (ESC), and the number of rejected CRs. | Include as part of quality reporting |

# PROJECT DELIVERABLE OVERVIEW

This section provides an overview of the deliverables associated with the STARS Solution. The table below categorizes the major project deliverables. The table column headings are as follows:

- Stages: A stage number with associated Deliverables. This Project expects to have Stages 1, 2, and 3. If the Contractor has a different approach to the Stages, they may propose an alternative approach after contract award, subject to review and approval by the State. The Contractor must ensure all required Deliverables are mapped to their approach.

  - Stage 1 – Initiation: This Stage consists of all Project management plans, as shown in the table below, within one and a half (1.5) months from the Project kickoff.

  - Stage 2 – System Design, Development, Testing, and Implementation: This Stage milestone will complete the STARS Solution build-out, functional testing, requirements and features testing, integration testing, security testing, system load testing, and user acceptance testing per the test plan deliverable.

  - Stage 3 – Project Closeout and Warranty Period Commencement

- Activities: Assigns activity names to each of the respective stages and deliverables.

- Deliverables:  An end result thing, tangible or intangible, that is provided as a result of work. The Deliverables that must be completed within the Stage.

Table 4 Project Deliverable Overview

| Stage | Stage Activities and Deliverable Overview (See Section 18 : CONTRACTOR DELIVERABLES for Details) | Schedule Completion (Calendar Days) |
| --- | --- | --- |
| Stage 1 INITIATION | Vendor Team Onboarding and Security Training Project Pre-Planning (Deliverables: DEL1.0 – DEL1.13) | 45 Days |
| Stage 2 SYSTEM DESIGN, DEVELOPMENT, TESTING, AND IMPLEMENTATION | Solution Design and Development (Deliverables: DEL2.0 – DEL2.1.3) | 90 Days |
|  | Cloud Solution Implementation (Deliverables: DEL2.2 - DEL2.11) | 150 Days |
|  | Test: - System, Functional, Integration, and Connectivity (Deliverable DEL2.13) - Performance and Loading Deliverable (Deliverable DEL2.14) - Security and Access (Deliverable: Section 32) | 75 Days |
|  | Training (Deliverable: DEL2.12 and Section 28: Knowledge Transfer and/or Training): System Operation, Administration, Maintenance and the Users. | 15 Days |
|  | State User Acceptance Testing (UAT) (Deliverable DEL2.15) Assessee Pilot Testing (APT) (SECTION 24.4 SYSTEM INSTALLATION) | 60 Days |
|  | Solution Modifications and Optimizations From UAT Feedback (Deliverable DEL2.15.6) | 45 Days |
|  | System Regression Testing (Deliverable DEL2.15.7) | 45 Days |
| Stage 3 PROJECT CLOSEOUT AND WARRANTY PERIOD COMMENCEMENT | Solution Acceptance and Handoff to State (Deliverable: Section: 25 SYSTEM TESTING AND ACCEPTANCE PROCEDURES) (Deliverable: Section: 27 TRANSITION OF OPERATION TO STATE, Transition Out Plan, and Transition Out Services, Deliverable 3.4) | 15 Days |
| Total |  | 540 Days |

# CONTRACTOR DELIVERABLES

The Contractor must complete the Deliverables listed in this section. Descriptions of each Deliverable are in this section. The numbering of the Deliverables does not indicate the order in which the Deliverables must be completed unless otherwise stated. The performance of tasks is set forth in the RFP and Contractor’s proposal as accepted by the State.

Completion of the identified Deliverables must be under the direction of the Contractor Project Manager in collaboration with the State Contract Manager, in accordance with the State policies and procedures.  For documents to assist the Contractor in completing Deliverables, upon contract award, the Contractor will be provided with access to the State Dictionary and Glossary of Terms.

The Contractor shall perform ongoing processes, tasks, and activities as identified in this section for each Deliverable.

## Project Status Reporting

The Contractor’s Project Manager shall conduct monthly reviews (on a timeframe mutually agreed-upon by the Parties) to present the current and cumulative Project status information related to assigned open and ongoing Project issues and risks in accordance with DEL1.2– Project Management Plan (PMP). These reviews shall be held with the BOE STARS Project Sponsor or designee, IT Manager, and CDT IPO, and no later than three (3) State business days after the last day of the previous month.
The Contractor’s Project Manager or designee shall present monthly project updates to the STARS Executive Steering Committee (ESC) members. The Contractor’s Project Manager shall provide updates for the reporting period, which include but are not limited to:

- A summary of Contractor activities.

- Accomplishments to date.

- Significant decisions.

- DevSecOps (Development, Security, Operations) Security Implementations.

- Project Tasks to be completed for the next period.

- Explanation for any tasks that are delayed and how the schedule delays will be recouped.

- Recommendations for issue resolution for all issues.

- Recommendations for mitigation of high-severity risks.

Additional meetings that the Contractor shall attend at the BOE’s request include, but are not limited to, the following:

- Daily informal meetings between the BOE, the BOE’s Project Manager, Contractor Project Manager, and/or their designees.

- Weekly management meetings between the BOE and Contractor Project Managers.

- Ad Hoc meetings on Contractor adherence to STARS project management processes and practices.

The Contractor’s Project Manager shall provide a written bi-weekly summary of activities for the reporting period (preceding two (2) calendar weeks), including but not limited to:

- Significant activities initiated.

- Significant activities completed.

- Activities planned but not completed.

- Activities and assigned resources planned for the next reporting period.

- Schedule status (including planned versus actual and reasons for variances).

- Project resource utilization and assignments review.

- DevSecOps (Development, Security, Operations) Security Implementation.

- Significant action items.

- Identified or assigned project risks and project issues (with a description of the action item, risk or issue, due date of resolution, and planned activities to address.

- Significant decisions made.

The Contractor’s Project Manager shall attend weekly Project status meetings to discuss the Project status. A report shall be presented to the BOE STARS Project Sponsor or designee at least one (1) full State business day prior to the weekly status meeting. To the degree the report is incomplete or inaccurate, the Contractor's Project Manager shall revise the report and present it as a final Deliverable for Acceptance.

## Maintain and Update STARS Project Management Plans (PMP)

The Contractor shall maintain and update all PMP that are defined as Deliverables for Stage I – Initiation, as well as the Contractor’s Project Schedule (SECTION 18: Deliverable DEL1.3), as required by events or at prescribed intervals during the life of the STARS Solution Project. The Contractor’s Project Schedule shall be updated bi-weekly at a minimum and shall be submitted to the State no later than two (2) State business days after the end of the immediately preceding two (2) calendar week period. Additionally, the Project Schedule shall adhere to all standards defined in the State Schedule Management Plan and the Contractor’s PMP. All Project Management Plans must be updated at the end of each stage or phase.

## Attend Project Meetings

At the State's request, the Contractor and any required Contractor Staff must be available for meetings with State team members during State Business Hours and Days.

The Contractor shall attend Project meetings with business users, IT subject matter experts, the State management, and other Stakeholders as required. The Contractor’s Project Manager or designated Contractor Staff shall be available as required by the BOE STARS Project Sponsor or designee to attend meetings related to the Project.

The Contractor’s Staff shall attend checkpoint and code review meetings as defined in the State approved Contractor’s Schedule, with the State TSD staff to review custom code, receive feedback, and discuss technical issues, concerns, and other IT related topics.

## Perform Ongoing Issues Management and Risks Tracking

The Contractor shall identify and formally submit its issues and risks in accordance with the State Issue Management and Risk Management processes. The Contractor shall report on assigned Project issues and risks to the BOE STARS Project Sponsor, or designee. The Contractor shall present this report at each status meeting using a format that includes the following:

- Identification of Project issues and potential risks.

- Management of technical issues or risks.

- Analysis and mitigation strategies for issues and risks including root cause analysis.

- Status of the issues and risks (i.e., open, pending, under investigation, or resolved).

- Appropriate tracking dates.

- Person and organization responsible for resolution.

- Contractor’s recommendations for resolving issues or risks.

- Maintain in Project SharePoint.

## Participating in Change Control Process

The Contractor shall participate in the Change Control Process as outlined in SECTION 16 CHANGE CONTROL PROCESS.

## Participating in the Communications Process

The Contractor shall contribute content to all written and verbal communications as needed throughout the STARS Solution Project per the STARS Communication and Stakeholder Engagement Plan, unless otherwise specified by the State.

## Participating in Organizational Change Management Process

The Contractor shall support the BOE STARS Project Sponsor or designed in executing Organizational Change Management (OCM) activities per the STARS OCM Plan. The State anticipates providing an approved OCM Plan by the start of this Agreement. The State will lead the OCM effort. The Contractor shall work with the State and provide input on how the new system affects Organizational Change, the State's business processes, and related OCM activities throughout the project.

## Final Report for Each Stage

At the end of each Stage or phase and at the final project completion, the Contractor shall submit a report indicating that all Stage or phase activities are complete, for review and Acceptance by the State. The Report shall include the status of Deliverables and outstanding issues, along with mitigation strategies for issues.

## STAGE 1 - INITIATION DELIVERABLES

The Contractor shall prepare the following Deliverables during Stage 1 and shall use them to guide its management of Project work. Each plan shall conform to relevant industry standards and other criteria as defined below for the corresponding Deliverable plan. Refer to EXHIBIT D: DELIVERABLES AND MILESTONES TABLE.

##### DEL1.1 – KICK OFF MEETING

The Contractor shall provide a draft agenda and materials to the BOE STARS Project Sponsor and participate in one or more kick-off meetings that review the goals and scope of the Project, introduce Key Staff members, present a summary of the key phases and activities (including key milestones in the Contractor’s Project Schedule), discuss major activities or efforts that will be required of meeting participants. This meeting(s) shall be held with different stakeholders which could include the State management and staff, contractors, and/or STARS stakeholders.

##### DEL1.2 – PROJECT MANAGEMENT PLAN (PMP) INCLUDING PRODUCT SOLUTION IMPLEMENTATION ROADMAP

The Contractor shall develop its STARS PMP detailing how it will execute this engagement, including its Product Implementation Roadmap for the successful design, development, testing, implementation, and maintenance of the STARS Solution, complying with all requirements of this Agreement. The Contractor shall submit the updated STARS PMP within forty-five (45) calendar days of the Contract Start Date for review and acceptance by the State. Content shall include, at a minimum, the following components:

- Project overview.

- Project work breakdown structure.

- Management objectives and priorities.

- Organization chart.

- Roles and responsibilities of the Contractor resources and all stakeholders.

- RACI Matrix (Responsible, Accountable, Consulted, Informed).

- Project assumptions, dependencies, risks and constraints.

- Contractor’s approach to the Implementation Roadmap for the STARS solution.

- Project tasks, Deliverables, and milestones.

- Microsoft Project schedule file (filename.mpp)

- Approach for integrating the Contractor's risk and issue management procedures with the State STARS Project processes.

- Project Schedule Management Plan for the Contractor’s Project Schedule, including resource updates, tracking of resource activities, tracking of milestone progress and reporting, critical path monitoring, resolution of schedule variances, status reporting based on work breakdown structure, and contingency activities.

- Contractor approach to supporting the following project management areas:

  - Scope and Requirements Management

  - Change Control

  - Deliverables Management

The delivered STARS PMP shall conform to the most current version of the Project Management Institute (PMI ®), A Guide to the Project Management Body of Knowledge (PMBOK ® Guide).

This PMP shall be implemented upon completion and updated, as needed, at the end of each step, as required during the life of the STARS Solution Project.

##### DEL1.3 – PROJECT SCHEDULE, INCLUDING PRODUCT SOLUTION IMPLEMENTATION ROADMAP AND SCHEDULE

In collaboration with the BOE STARS Project Sponsor or designee, the Contractor shall, within fourteen (14) calendar days of the Contract Start Date, update the Project Schedule that the Contractor submitted in its proposal, identifying all activities the Contractor shall undertake to complete its Deliverables per the Project schedule. The schedule should be updated weekly thereafter per the State Project Schedule Management Plan (SMP).

The Contractor shall specify all predecessor-successor relationships among activities and Deliverables in DEL1.2 – Project Management Plan (PMP), including Product Solution Implementation Roadmap. The Contractor’s Project Schedule, for which the State provides Acceptance, shall also determine the exact date these Deliverables shall be due.

The updated and submitted Contractor’s Project Schedule shall also include identifying all activities that other STARS Solution Project team members (including Contractor staff and State team members) must perform to complete the Project. The Contractor’s Project Schedule shall include the Implementation Roadmap for developing the STARS Solution. In addition, the Contractor’s Project Schedule shall clearly identify all phases, tasks, Deliverables, assigned resources, and interim milestones. The Contractor’s Project Schedule shall include a work decomposition that includes resource loading of the STARS Solution Project team members (including but not limited to the Contractor, other state departments, and quality assurance), as well as the State staff, and shall have start and finish predecessors and successor dependencies identified for each task. In addition, the Contractor’s Project Schedule must accommodate time for the State Project team to inspect any of the Contractor’s work in progress and periodically review Contractor-specific plans and documents that are a work in progress.

The Contractor’s Project Schedule shall be developed and maintained using the latest version of Microsoft Project. Managing and updating the Contractor’s Project Schedule shall conform to the STARS Schedule Management standards, processes, and roles and responsibilities defined and documented in the STARS PMP. The Contractor shall maintain the schedule which captures all its work across the STARS Solution Project. The Contractor shall be responsible for defining and tracking all tasks and dependencies related to completing its contracted Deliverables. The Contractor’s Project Schedule shall be comprehensive and detailed for the current and upcoming Steps, but may be high-level for future Steps. Twenty-one (21) calendar days prior to the start of each stage or phase, Contractor shall present a comprehensive and detailed schedule that includes full details for that stage or phase for Acceptance by the State.

Upon the State's acceptance of the Contractor’s Project Schedule, the Contractor shall participate in the weekly ongoing schedule maintenance and schedule update processes. The Contractor shall follow the defined procedures and standards documented in the  STARS PMP. The Contractor shall:

- Gather and incorporate updates on scheduled work products into Microsoft Project.

- Elaborate and develop detailed work breakdown and duration estimates required for planning, including assigned resources needed.

- Identify the Project’s critical path.

- Conduct and complete schedule analysis and schedule quality assurance activities required to control performance.

The Contractor shall update its Project Schedule at least weekly, and shall submit the Contractor’s updated Project Schedule, incorporating progress as of the end of each week, to the BOE STARS Project Sponsor or designee within two (2) State business days of the end of that one-week period. The Contractor’s Project Schedule update process shall include work with the BOE STARS Project Sponsor or designee to complete schedule quality assurance to verify that dates, resource allocations, percentages, etc., are correct, and thereby ensure that reporting against baseline data can be generated accurately according to the quality-related components outlined in the State Schedule Management Plan available in the Bidder’s Library.

##### DEL1.4 – INTERFACES MANAGEMENT PLAN

The Contractor shall deliver, within forty-five (45) calendar days from Contract Execution Date, an Interfaces Management Plan that sets forth how the Third-Party Interfaces and Application Programming Interfaces with existing State External Data Sources (such as, Payment processors; RealQuest, CHARM, ORER) will be designed, developed, integrated, and tested.

The plan also shall indicate how the third-party interface partners are identified and communicated with on a regular basis. The plan also shall indicate how their testing timeframe needs will be identified and accommodated by the Project.

This Interfaces Management Plan shall be implemented and shall be updated as required during the life of the STARS Solution Project.

The current interfaces and data sharing processes will need to be supported in the proposed solution. The Contractor must provide interface design documentation as detailed in SECTION 18. CONTRACTOR DELIVERABLES. Additionally, the Contractor must provide suggested tasks and timelines for any required data conversions, data cleaning, and data verification, as applicable, within the proposed Project schedule.

The table below lists details of the interfaces for the STARS Solution. The proposed Solution must support APIs and be scalable to include future additional interfaces as needed.

Table 5 External Data Sources

| External Data Source System | Interface Name | Inbound or Outbound | Description |
| --- | --- | --- | --- |
| RealQuest | RQuest | Inbound | - Property Information - Property Values |
| Rail Inc. | RailInc | Inbound | - Rail Car Information - Rail Car Operation Condition |
| CHARM (Car Hire Accounting Rate Master (CHARM)) | CHARM | Inbound | - Rail Car Information - Helps users manage and understand the costs of railcar use and repair. - CHARM is the official source of time and mileage rates on freight cars. |
| ORER (Official Railway Equipment Register) | ORER | Inbound | - Rail Car Information - Rail Car Operation Condition - A Comprehensive Register: Published for decades, the ORER documented virtually every freight car in North American interchange service, including cars from the U.S., Canada, and Mexico. - Key Data: It provided essential details like reporting rail car marks, car numbers, dimensions, carrying capacity, and car type (e.g., gondola, boxcar, flatcar). |

##### DEL1.5 – DATA MANAGEMENT PLAN WITH DATA CONVERSION AND MIGRATION

The Contractor shall deliver, within forty-five (45) calendar days from Contract Execution Date,  in consultation with the State team, a Data Management Plan with Data Conversion and Migration in accordance with the BOE Data Governance Plan and Policies. This plan shall identify the scope and sequence of steps for data mapping, conversion, and migration, as well as the timing and method by which the STARS Solution data will be integrated and imported into the STARS Solution.

The STARS Solution data management plan document (In Bidder’s Library) outlines the flow of data elements and provides suggestions. However, the Project is open to the Contractor’s suggestions and recommendations to improve or enhance accessibility, manageability, searchability, reliability, security, and storage costs. This data management plan is to be implemented by the Contractor to be operational and complete for the State to maintain in the production Stage.

##### DEL1.6 – SYSTEM CONFIGURATION MANAGEMENT PLAN

The Contractor shall develop, in consultation with the State, a detailed System Configuration Management Plan (SCMP). This plan shall include a build versioning control and how GitHub will be utilized to track build versioning, including methods and tools (if appropriate). The Deliverable shall include, at a minimum:

- The sequence of operations or steps that shall be carried out to deliver code and configuration changes to the STARS Solution within the system environments and functional modules: Development, Testing, Training, Staging, and Production.

- Configuration management methodology and processes to manage Solution development and integration of Solution components.

- Various environments that are part of the security, accessibility, user activity journaling, and processes of deployment between environments and functional modules.

- The anticipated impacts of the staging/production release.

- Release contingency plans and Hypercare Action List (SECTION 39: HYPER CARE ACTION LIST).

- Personnel to contact or escalate any issues during the releases.

- Planned notifications and reports to stakeholders regarding the releases; and

- Go/no-go deployment criteria.

The Contractor shall use and maintain the State’s STARS Solution repository in the latest version of GitHub or the current version the State is utilizing, for all development artifacts, code, and work items. The Contractor shall have all Solution source code and all other artifacts in GitHub, in sync with the deployed release.

Work items include, but are not limited to, the following:

- The STARS Functional and Non-Functional Requirements

- Business Rules

- Use Cases

- User Stories

- Change Requests

- Defect/Bugs

The Contractor shall provide the System Configuration Management Plan within forty-five (45) calendar days of the Contract Start Date for review and Acceptance by the State.

The System Configuration Management Plan shall be implemented and shall be updated within five (5) business days as required during the life of the STARS Solution Project.

##### DEL1.7 – STARS SOLUTION IMPLEMENTATION PLAN

At least twelve (12) months before the go-live date established in the State-approved Project Schedule, the Contractor shall develop an Implementation and Deployment Plan to describe how the Contractor will implement and deploy the STARS Solution. The narrative must be complete and adequately address the implementation of software, hardware, and other components to meet all aspects of the STARS Solution requirements as conceptually illustrated in Figure 3: Conceptual STARS Solution Implementation and Integration Plan.

Figure 3: Conceptual STARS Solution Implementation and Integration Plan

The Implementation Plan must include, at a minimum, the following:

- Implementation approach, including details of the approach to be taken to implement and integrate all solution components.

- Roles and responsibilities for Contractor and State staff and alignment between State and Contractor resources.

- Pre-go-live and post-go-live activities and dependencies.

- Develop and support communication with STARS Stakeholders regarding the STARS Solution implementation, deployment, and go-live.

- Collaborate with the State and STARS Stakeholders to capture go/no-go criteria.

- Go-live and cutover timeline.

- Legacy STARS Solution go-live dependencies.

- How interfaces/APIs and other non-prepackaged features will be implemented, configured, and deployed.

- How the STARS Solution will integrate with any State infrastructure and IT system components.

The Contractor shall successfully configure and deploy the STARS Solution in the Staging and Production environments. The Contractor shall develop, plan, manage, track, and execute detailed go-live procedures, activities, and dependencies. The Contractor shall actively coordinate with the State and all Stakeholders for a successful go-live by March 31, 2028. The Contractor shall work with the State to ensure the updated System Configuration documentation provides the details necessary to successfully configure and deploy the STARS Solution in the Staging and Production environments. The Contractor shall also provide documentation describing disaster recovery procedures for the STARS Solution, including but not limited to, sequence of fail-over procedures, fail-over scenarios, configurations required for each scenario, tasks, roles, and responsibilities.

##### DEL1.8 – QUALITY MANAGEMENT PLAN

The Contractor shall deliver, within forty-five (45) calendar days of the Contract Start Date, a Quality Management Plan for review and Acceptance by the State. The Quality Management Plan shall include a complete description of the Contractor’s quality management process, methodology, and the specific standard(s) on which the details of the plan are based. If multiple standards are used, the plan shall specify which portions of these standards were used in the development of each portion of the plan. The Quality Management Plan shall detail the following at a minimum:

- Contractor’s Quality Management activities throughout the Stages and Phases.

- Definition of quality standards, policies, and procedures.

- Quality control approach for work products.

- Description of how quality will be monitored and measured.

The Quality Management Plan shall be implemented and shall be updated at the end of each phase and as required during the life of the State’s STARS Solution Project.

##### DEL1.9 – TEST PLAN WITH A TEST MANAGEMENT PLAN (TMP)

The Contractor shall deliver, within forty-five (45) calendar days from Contract Execution Date, a detailed Test Plan. This Test Plan shall include test scope and/or criteria, testing tools, testing methodology, including the development of test procedures, test cases, test scripts, test data, defect tracking and resolution, as well as roles and responsibilities for various testing activities. The Test Plan shall include a description of the Contractor’s testing strategy through all the test phases, including support during the State User Acceptance Testing. Subsequently, a Test Management Plan (TMP) is to be developed outlining how the test plan will be managed. The Contractor shall collaborate to gain functional understanding from the State system test scenarios or cases before initiating development of individual features.

The Test Plan shall include details of Contractor coordination with the State during Systems Testing and Final User Acceptance Testing. This plan shall include how GitHub will be utilized for testing activities. The activities addressed in the Test Plan shall also be reflected in the Contractor’s Project Schedule.

The Test Plan shall address Contractor’s testing that includes but is not limited to the following:

- Establishing structured testing processes and procedures.

- Unit Testing.

- Integration Testing.

- Tax and Valuation Computations are “to the penny” rounding, except Private Rail Car (PRC).

- Integration testing with external data sources and service providers (i.e. payment processors).

- Performance Testing.

- Regression Testing.

- Stress and load Testing. (need prospective load)

- Accessibility Testing.

- Data Integrity Testing.

- Security Testing.

- Availability Testing.

- Disaster Recovery and Failover Testing.

- Contractor System Integration Testing.

The Test Plan shall also address the Contractor’s support for the following testing to be performed by the State (or designee):

- User Acceptance Testing.

- California AB 434 and WCAG 2.2 or Better Accessibility Testing.

- CDTFA ISO Security Assessment

The Test Management Plan (TMP) shall include the following, but not limited to:

- Identified the Owner of the Test Plan and Test Management Plan

- Scheduling of all STARS Testing and Deliverables to Be Completed

- Team Review and Update of the Test Plan Frequency

- Team Review of all STARS test results and outcomes with appropriate action plans to align STARS performance to the desired specifications

The State reserves the right to identify any additional type of testing it may perform during the Project. The Contractor shall incorporate into their plan any additional type of testing the State may perform.

##### DEL1.10 –STARS SOLUTION TRAINING PLAN

The Contractor shall deliver, within forty-five (45) calendar days from Contract Execution Date, a STARS Training Plan. This Training Plan shall:

- Address the separate needs of the State program staff, the STARS Solution help desk staff, and the State technical system support staff.

- Describe the Contractor’s philosophy on user training, including the method of training to be provided for each group, such as computer-based training software, classroom or virtual lectures, and a hands-on computer laboratory environment.

- Distinguish training approach and materials between user and stakeholder roles (e.g., line level staff, supervisors, policymakers, the State report/query capability users) as each has a different need for the level of information being provided.

- Describe the maximum trainee group size by functional area and define the differences in training for executives, management, business staff, and information technology staff.

- Address the “Train-the-Trainer” concept, which allows the State to conduct training after Stage II – Design, Development, Implementation and Testing.

The Contractor is responsible for the following components:

- Training scope.

- Training environment set-up and refresh procedures.

- Training data development.

- Training courses and prerequisites.

- Training Materials:

  - Provide printed and bound training documentation

  - Provide PDF electronic copies of training documentation

- Training schedule.

- Provide In-person training.

- Training curriculum which includes the following content:

  - Escalation process: What to do and whom to call if there is a problem with the system.

  - The STARS Solution data standards.

  - Solution Administration, Task Assignment and respective Owners, Due Dates, etc.

  - the STARS Solution business rules related to campaign and lobbying disclosures.

  - Execution of predefined STARS Solution reports.

  - Creation of new STARS Solution reports, dashboards, and queries and saving them for execution by other users.

  - Evaluation methodology of training effectiveness and appropriate modification of training curriculum based on the evaluation.

Maintain current curriculum and materials as the STARS Solution and affected business processes are modified during development and after implementation, including:

- Online training scenarios.

- In-person classroom training scenarios.

- Training the trainers.

- Training procedures.

The plan shall include the refresh process and procedures for the training database. This STARS Solution Training Plan shall be implemented and shall be continuously updated as required during the life of the STARS Solution Project.

##### DEL1.11 – SECURITY PLAN

The Contractor shall deliver, within forty-five (45) calendar days from Contract Execution Date, update, implement, and maintain a System Security Plan (SSP), subject to the State approval, in accordance with security industry standards, including:

- State Federal Information Processing Standards (FIPS) (e.g., National Institute of Standards (NIST) 800-53, Rev. 5

- Security and Privacy Controls for Federal Information Systems and Organizations, NIST 800-18, Rev. 1

- Guide for Developing Security Plans for Federal Information Systems, FIPS 199 and the ISO/IEC 27002 Information security, cybersecurity, and privacy protection.

- Information security controls, applicable statutes and regulations, and the State Information Security and Privacy Provisions aligned to the State of California State Administrative Manual (SAM) and Statewide Information Management Manual (SIMM).

The SSP must detail how the STARS Solution implements the security requirements and shall include the following:

- The roles and responsibilities of security personnel

- Reference to existing policies and procedures; and

- All controls implemented in the STARS Solution and associated procedures.

The Plan must provide the Contractor’s approach for maintaining third-party product upgrades to ensure they continue to work with the STARS Solution and establish security practices to prevent the likelihood of security breaches, including ransomware attacks, in accordance with industry best practices.

##### DEL1.12 – TRANSITION OUT PLAN

The Contractor shall deliver and adhere, within forty-five (45) calendar days from Contract Execution Date, to a Transition Out Plan based on the proposed Transition Out approach. The Transition Out Plan must include, but not be limited to, the requirements listed below:

- The roles and responsibilities of both State and Contractor are specified as such.

- The Contractor’s responsibilities for the Transition Out Plan must include the following:

  - Continued support of operations while transitioning tasks.

  - Return of all the State-owned data. Data must be provided to the State in a non-proprietary, mutually agreed-upon format.

  - Final updates and handovers to the State of the design and configuration deliverables.

  - Entry and Exit criteria for all Transition Out activities.

  - Development of all supporting documentation that accompanies and supports the Transition Out activities.

  - Contract closeout processes and how the Contractor will securely destroy any digital data and/or confidential paper data post-termination of the Contract.

- Within the Transition Out Plan, the Contractor shall develop a transition-out schedule that identifies the transition-out steps the Contractor will take. The transition-out schedule will include the following minimum requirements:

  - Required tasks, associated task owners, task dependencies, schedule, and timing.

  - Tools and processes used to coordinate tasks, track and report issues and communicate status to all stakeholders (e.g., Project team, end users, operational support staff, help desk, etc.) throughout the transition-out period.

- The Contractor shall develop a Transition-Out Risk Assessment documenting any known or potential risks associated with the Contractor’s transition-out approach. The Transition-Out Risk Assessment will include the minimum requirements described below:

  - An impact and probability assessment and defined, recommended risk mitigation steps. Any risks identified must follow the established procedures documented in the Project’s Risk and Issue Management Plan.

##### DEL1.13 – MAINTENANCE AND OPERATIONS PLAN

The Contractor shall deliver, within forty-five (45) calendar days from Contract Execution Date, a Maintenance and Operations (M&O) Plan detailing the Contractor’s approach for maintenance and operation of the STARS Solution. The M&O Plan shall describe the processes, methodologies, roles, responsibilities, tasks the Contractor will employ, the documents the Contractor will deliver to maintain and operate the STARS Solution, including Solution enhancements, and how the Contractor will ensure that Project documentation is kept current throughout the One-Year Maintenance and Operations period.

The M&O Plan shall include a description of the following:

- M&O roles and responsibilities.

- Methods for ensuring the STARS Solution is fully functional and performs in accordance with the terms of this Agreement.

- Methods of communication and coordination with the State staff while executing M&O tasks, including an approach to partnering with the State to develop triage processes, procedures, and steps for troubleshooting issues related to the STARS Solution and assigning Severity Levels defined in Table 10.

  - How deficiencies will be escalated and resolved

  - How troubleshooting will be performed to diagnose and resolve defects and/or performance anomalies

  - Methods for monitoring and tuning of Solution performance.

  - Methods for maintaining any accelerants and/or licensed components used in the Solution if required.

- Management of changes to the STARS Solution to support end users, including:

  - Changes due to deficiencies in the STARS Solution components

  - Configuration changes to STARS Solution components

  - Methods for and frequency of updating STARS Solution documentation as changes are applied, including user manuals and training materials.

- Performance of required security activities such as backups and updates.

- Planned maintenance schedule, including when maintenance will be performed and how long the maintenance tasks will take.

## STAGE II: SYSTEM DESIGN, DEVELOPMENT, IMPLEMENTATION, AND TESTING

##### DEL2.0 - DESIGN, DEVELOPMENT, IMPLEMENTATION, AND TESTING OF A STATE ASSESSED PROPERTIES DIVISION (SAPD) WITH PRIVATE RAIL CAR (PRC) TAX AND VALUATION COMPUTATION AND ANALYTICS PLATFORM WITH A FULLY INTEGRATED E-FILE WEB PORTAL, CASE MANAGEMENT SYSTEM, AND ASSOCIATED MODULES

The Deliverables in Stage II shall detail the Contractor's plan and approach for architecting, designing, developing, testing, and deploying the full STARS Solution and related activities. Each Deliverable shall articulate the Contractor’s vision for the solution and contain the following at a minimum for each Deliverable as appropriate:

DEL2.0.1: The Contractor shall detail the Contractor’s plan and approach for architecting, designing, configuring, developing, testing, and deploying the STARS Solution and related activities.

DEL2.0.2: The Contractor will provide a Vision Road Map that details the Contractor's vision for the solution, reporting monthly, as needed.

DEL2.0.3: The Contractor shall provide a primary and secondary level of detail to develop test cases and training materials.

DEL2.0.4: The Contractor shall provide Various Access and Control interface window or graphical user interface (GUI) to include at a minimum:

  - “Super User” or “Master” control window of the e-file system and entire solution and its respective modules to administer workflow variables, schedules, task assignments, due dates, login users, and their respective access privileges.

  - The State employee access window to work accounts and assessees to complete their work assignments necessary to complete the assessee’s tax and valuation and/or their board roll.

  - Manager or supervisor access window to review and approve/sign work.

The Contractor shall utilize its creative and design capabilities to deliver a modern state-of-the-art solution with working elements and modules that are functional and informative, and could be multi-panel, folder-driven, pull-down menus, or a combination of both.

DEL2.0.5: The Contractor shall conduct incremental Requirements, Design, and Code review meetings as defined in the Contractor’s Project Schedule.

The Contractor shall provide extensive and prolific commenting in the lines of code, especially key variables in the tax and valuation code. These variables requiring extensive commenting will be determined in collaboration with the State subject matter experts and the respective division Chief.

DEL2.0.6: The STARS Solution review team (including but not limited to State personnel from CDT and/or CDTFA) has the option to observe testing performed by the Contractor. The Contractor shall provide necessary training to the State testers on using the application so they can execute testing for any required Deliverables.

##### DEL2.1 - SYSTEM TECHNICAL ARCHITECTURE (STA)

The Contractor shall provide the System Technical Architecture (STA) documentation. The document shall clearly explain the distinction between logical and physical architecture, a detailed explanation of diagrams, and clearly defined technical terms. The STA (System Technical Architecture Document) shall include the following at a minimum:

- Executive summary of the STA.

- Overview of the Architectural Strategies.

- Description of the STARS Solution ecosystem, subsystems, and technical environment.

- System configuration.

- Logical, Data, and Security Architecture.

- A detailed explanation of how the architecture addresses performance, availability, data/application/server security, scalability, maintainability and system management, accessibility, external interfaces, and extensibility.

- Detailed explanation of how the architecture addresses disaster recovery and business continuity.

- List of all cloud environments, services (such as but not limited to identity management and notification, internet, networking, broadband, and storage services), and software products. The list shall include minimum requirements, and a description of how each item will be managed, used, and integrated into the STARS Solution.

- Details of accelerators used or existing off-the-shelf products, and how these integrate with the overall solution.

- List of programming languages and tools selected for the development of the STARS Solution.

- Delineation of the environments to be provisioned (e.g., Development, Test, Training, Staging, Production, etc. Business Continuity/Disaster Recovery, etc. including but not limited to data mart / reporting / data analytics, and data archiving.

- Minimum end-user and administrator workstation and browser requirements.

- A glossary that defines all technical terms used in the document.

- Provide Lessons Learned for each Phase and Deliverable as appropriate for State review and approval.

The Contractor shall also specify within this Deliverable any proposed changes that the Contractor deems necessary to any of the State infrastructure or cloud-based environments. Any changes must be reviewed and approved by the State before this Deliverable is accepted. Refer to SECTION 11: CONTRACTOR ROLE AND RESPONSIBILITIES for software license cost and transfer of ownership.

DEL2.1.1  The California Department of Technology has developed an update to the Cloud Computing Policy, a Cloud Smart strategy that leverages modern technology and practices to deliver the full potential of cloud computing, driving digital transformation and improving operational efficiency, agility, and innovation.

To ensure alignment with this strategy, CDT has implemented a California Cloud Services Assessment to validate security, cloud architecture, workforce, and procurement requirements. This process will be applicable to Agencies and/or state entities that plan to either introduce new systems or modify and migrate existing systems into the cloud. The assessment scope extends to both commercial and government clouds provided in Off-Premises Cloud Services. Details on the process of completing the assessment will be in California Cloud Services Assessment Guidelines (SIMM 141). Document SIMM 141 is provided in the bidder’s library for reference. Once the request is complete, including all required documentation, a review will be initiated. The review is expected to take 14 business days. If documentation is missing or inadequate, your Agency/state entity may be contacted for additional information, which may extend the review time. Upon assessment approval, the Agency/State entity may proceed with their Cloud implementation.

DEL 2.1.1.1 The Contractor shall provide all necessary documentation artifacts to complete the various forms associated with the California Cloud Services Assessment per the SIMM 141 guideline documentation.

DEL 2.1.1.2 The Contractor shall complete all necessary forms and submit them for review and approval in accordance with SIMM 141 guideline documentation.

##### DEL2.1.2 –The Contractor shall provide the means to generate Data Model and Data Dictionary (DMDD) documents and the respective documents for the STARS Solution databases (transactional, data mart, and archive) and all stored data. The Deliverable shall be developed based on information in the Data Conversion and Migration Plan and shall administer the BOE Data Governance Policies for all old and new data. The data models presented in this Deliverable shall define all the data elements, relationships, constraints, access methods, and other related details for both the STARS Solution and the STARS Solution database or data marts. The Contractor shall collaborate with and seek input from the State to develop the data model for all STARS Solution databases, including, but not limited to, transactional, data mart, and archive databases. The STARS Solution data mart shall incorporate a denormalized data model that is optimized for tax and valuation computation, reporting generation, and data analytics.

The data dictionary portion of this Deliverable shall catalog the organization, content, and conventions of the STARS Solution transactional database, archive database and the data mart, including but not limited to the names and descriptions of all tables and columns and additional details such as the type and length of each data element, a list of permissible values for columns, and other related database schema details.

##### DEL2.1.3 The Contractor shall provide the Detailed System Design (DSD) documentation. The documentation shall provide a clear explanation of system and subsystem architecture as defined in DEL2.1 System Technical Architecture Documentation; files and database design as defined in DEL2.1.2 Provide The Means And Generate Data Model and Data Dictionary Deliverable, input formats, layouts, processing logic and External Interfaces to satisfy all the requirements. The DSD Specification Deliverable shall include the following at a minimum:

- Executive summary of the purpose of the DSD.

- The STARS Solution overview.

- Design considerations, including any assumptions, dependencies, integrations, interfaces, and guidelines followed in the detailed design and implementation of the STARS Solution.

- System design strategies describing the standards used for the STARS Solution.

- Detailed design consisting of the cloud services, software architecture and technical specifications as defined in DEL2.1 System Technical Architecture Documentation, including any existing architecture and communication infrastructures in place.

- Database design describing the database and data hosting environment, data security, and diagrams showing the database design and/or relationship between the database and all interfaces. This Deliverable shall provide the design for all database management systems associated with the STARS Solution in conformance with the DEL2.1.2 Provide The Means And Generate Data Model and Data Dictionary.

- Description of each application module function(s) expected input and output, conditions for use, and interface with other modules.

- A graphical representation of module processing, logic, flow of control, and algorithms using an accepted diagramming approach (e.g., flowchart).

- System security and integrity controls describing the measures included in the STARS Solution design to ensure the STARS Solution is secure and the integrity of the STARS Solution and data are maintained to meet the STARS Solution security requirements.

- Hierarchy and structure of role-based security and access permission.

- Audit procedures to meet control, reporting and retention period requirements for operational and management reports.

- Detailed description of the verification processes for reading, additions, edits, or updates of critical and confidential/sensitive data.

- Defined user experience providing a detailed design of the system and subsystem inputs and outputs relative to the user/operator.

- Wireframes that define the layout of all input data screens, graphical user interfaces (GUIs), and data elements associated with each screen/GUI.

- Edit criteria for data elements, including specific values, range of values, mandatory/optional, alphanumeric values, and length and data controls to prevent edit bypassing.

- Identification of the messages associated with user inputs.

- Wireframes that define the layout of all output screen contents and all data associated with the layout.

- Detailed interface design providing information about the interface requirements to correctly format, transmit, and /or receive data across the interface.  Information should include, but is not limited to, the data format requirements, specifications for hand-shaking protocols between the STARS Solution and external partner systems for error reports exchange between the systems, disposition of error reports, graphical representation of the connectivity between systems, showing the direction of the data flow; and

- Updated STA, where applicable.

The DSD shall document all system details for the State to be able to manage, maintain and enhance the STARS Solution.

##### DEL2.2 – PROVIDE A FULL SERVICE AND FULL-FEATURED E-FILE ASSESSEE TAX FILING WEB PORTAL AND MAKE ASSESSEE AND CUSTOMER READY FOR USE

The Contractor shall deliver the complete STARS Solution in Program Increments as outlined in EXHIBIT D: DELIVERABLES AND MILESTONES TABLE. The Contractor shall take feedback from the State Project Team and submit to the BOE STARS Project Sponsor, the STARS Solution Requirements planned to be completed in each Program Increment, for approval before starting each Program Increment. The Contractor shall not change the requirements planned in each Program Increment without prior written approval from the BOE STARS Project Sponsor or designee.

For each Program Increment, the Contractor shall perform the following:

- Requirements, use cases, business rules and flows reconfirmation.

- Develop user stories and tasks.

- Update Detailed System Design and Specifications.

- Development and integration.

- Data cleansing, conversion, migration, validation, integration, archival, and data mart.

- Code review, fixes and test cases for the fixes.

- System and unit test cases and results.

- Code security scan report.

- Regression testing.

- System integration testing, test cases, and results.

- Load and performance testing.

- Accessibility testing.

- Security testing.

- Third-party integration testing.

- User acceptance testing and results.

- Deployment.

The State has established a GitHub environment for the STARS Solution Project.

The Contractor shall meet with the State to verify requirements. Existing use cases are available for the Contractor. Each Deliverable shall provide the specifics of the overall system requirements that will govern the development and implementation of the STARS Solution.

The Contractor shall provide User Stories Documentation in accordance with the STARS PMP, and the Contractor’s Project Schedule for which the State has provided Acceptance. The User Stories shall reference and trace to all applicable system functions, user characteristics, constraints, assumptions, dependencies, business rules, and interfaces agreed upon by the State and the Contractor.

The Contractor shall provide the updated DSD for the Program Increment.

The Contractor shall transform and load all SAPD and PRC existing data into the new STARS Solution in all environments. The Contractor shall integrate the STARS data with the STARS Solution, validate the data, and conduct the necessary testing to ensure successful data transformation and integration into the STARS Solution. Issues and deficiency findings shall be corrected, and regression tested by the Contractor.

The Contractor shall be responsible for resolving all data quality issues that are identified during the end-to-end migration process during the Program Increment(s).

The Contractor shall be responsible for developing an automated ETL pipeline to periodically extract, transform, and load the STARS transactional data into the STARS centralized data storage repository or data mart and archive database.

System and Unit Testing shall meet at least 98% code coverage or other percentage approved by the State, and the Contractor shall provide the State with the Code Coverage Report showing compliance. Upon completion of all Contractor required testing for each Solution component, the Contractor shall have incremental and frequent structured code reviews and walkthroughs with the State TSD staff or designee during the development phase as specified in the Contractor’s Project Schedule to ensure coding standards and code quality are met.  Any issues and deficiencies identified by Contractor or the State team during code reviews and walkthroughs must be corrected, and regression tested before completion of the Program Increment. The Contractor shall provide the code review report and the Source Code to the State.

The Contractor shall conduct and complete System Integration Testing to include, at a minimum, Contractor’s Test Management Plan, Functional Testing, Interface Testing, Performance Testing, Load and Stress Testing, Acceptance Testing, Accessibility Testing, Security Testing, Requirements and Feature Testing (user audit logs, work task tracking, dashboarding, etc.), and Availability Testing.

For all code, including third-party software components introduced into the STARS Solution, a State application security scan shall be generated by the State. Any identified vulnerabilities involving a critical, very high, or high finding, along with any identified vulnerabilities existing on the Open Web Application Security Project (OWASP) current Top 10 vulnerabilities list or Common Weakness Enumeration (CWE) Top 25 most dangerous software weaknesses list, shall be remediated or mitigated by the Contractor in consultation with the State.

The Contractor shall review security findings from GitHub Advanced Security, or a similar tool as approved by the State, with the State and create a plan to resolve all findings as approved by the State. The Contractor shall modify the STARS code to achieve, if using CodeQL, a low CVSS score range of 0.1-3.9, and Software Composition Analysis (SCA) static scan score of 90, higher, or as agreed upon by the State and Contractor.

The Contractor shall review the code quality scan results using SonarQube, or similar tool as approved by the State, to achieve must achieve 70% or better with 85% code coverage and must pass the product's default code quality gates measures in the code coverage metric for all programming languages used in the application including achieving a cyclomatic/cognitive complexity score of no more than 25 or as agreed upon by the State and Contractor.

The Contractor shall provide necessary system training and work with the State STARS external stakeholders, and Electronic Filing Software Providers in conducting and completing the Integration Testing and User Acceptance Testing, including, at a minimum, Functional Testing, Requirements and Feature Testing, Interface Testing, Performance Testing, Load and Stress Testing, and Availability Testing. In addition, a Security Assessment will be conducted by the State or an independent third party through the State. Issues and deficiency findings shall be corrected, and regression tested by the Contractor.

Acceptance Criteria for this Deliverable shall also include a written confirmation from the State of the successful deployment, which meets STA and DSD to the Development, Testing, and Training environments for each Program Increment. Acceptance of this Deliverable shall not constitute the State's acceptance of the overall STARS Solution system.

The Deliverable shall include the following at a minimum:

- Source code.

- Associated user stories, and Tasks with traceability to STARS Requirements, use cases, business rules, bug fixes, and flows.

- Updated STA, DMDD, and DSD.

- Updated Test Plan with the detailed test cases, test scripts with test data, defect log, full regression testing report, and test result reports.

- Code reviews and walkthroughs completion report.

- System configuration documentation.

- Update STARS GitHub Repository with all details and artifacts for the Program Increment.

- STARS Solution data migration, integration, and quality reports.

The Contractor shall provide system configuration documentation detailing the configuration and deployment of the STARS Solution to all environments.  The Contractor shall work with the State to ensure the system configuration documentation provides the details necessary for the State TSD to successfully configure and deploy the STARS Solution in the STARS Solution environment(s) (including but not limited to Development, Test, and Training).

DEL2.2.1: The Contractor shall design, develop, and deploy a full-service, full-featured e-file assessee tax filing web portal. The portal will serve as the primary interface to the Board of Equalization, ensuring a seamless user experience, scalability, and security for submitting tax schedules and forms, as well as managing accounts for respective assessees.

To accomplish this tax filing web portal Deliverable, the Contractor shall deliver at a minimum the following in addition to the requirements in the EXHIBIT C: FUNCTIONAL AND NON-FUNCTIONAL REQUIREMENTS:

DEL2.2.2: The Contractor shall provide Full Featured (Includes all or a complete range of its available functions, capabilities, or technical specifications) Deliverables:

DEL2.2.2.1: The Contractor shall provide the ability to upload and download "CSV", "PDF", "TXT", and "JPEG" file types with the e-file portal, providing confirmation messages of the file upload or download via a BOE-branded email message or on-screen pop-up message.

DEL 2.2.2.1.1: The Contractor shall provide the ability to apply a predetermined set of flag indicators to any document or schedule for a specific special workflow, such as appeals, audit, etc.

DEL2.2.2.2: The Contractor shall provide the ability for the Assessee to manually enter and fill out tax schedule forms in the e-file web portal, while in real time, each field is checked for errors and validated without using any external data subscription services.

DEL2.2.2.2.1: The Contractor shall provide the ability to predetermine tax forms/schedules to be completed and the required supplemental filing statement attachments for submission by the Assessee business and respective industry type.

DEL2.2.2.2.2: The Contractor shall provide appropriate error markers such as a red asterisk or red highlighted box to erroneous fields for correction.

DEL2.2.2.2.3: The Contractor shall provide a “submit” or “next” button release only after the entire schedule or form is checked and validated without error.

DEL2.2.2.2.4: The Contractor shall provide auto save and multiple login work sessions to complete tax schedule or form work without the loss of prior work entry.

DEL2.2.2.3: The Contractor shall ensure all tax file upload field entries are checked and cleansed of any erroneous data entry, and then subsequently validated, where cleansing and validation are completed without using any external data subscription services.

DEL2.2.2.3.1: The Contractor shall provide appropriate error markers, such as a red asterisk or a highlighted red box, on the erroneous field for correction or provide an error log file containing data entry errors in the respective field entries.

DEL2.2.2.4: The Contractor shall provide Full journaling and chronological logging of the assessee session activity in the e-file web portal, including all account profile changes.

DEL2.2.2.5: The Contractor shall enable the e-file portal ready for use by assessees with the following, but not limited to:

DEL2.2.2.5.1: Prepopulating the predetermined schedules and forms fields per industry and jurisdictions with the respective prior lien year data for the current lien year data for updating, modification, and new entry.

DEL2.2.2.5.2: Prepopulating the assessee account profile information, such as entity name, industry type, entity address of record, responsible account owner, first delegate account login person user, phone number of record, at a minimum.

DEL2.2.2.6: The Contractor shall provide an e-File web portal that is modern, attractive, and yet fully Web Content Accessibility Guidelines (WCAG) Americans with Disabilities Act (ADA) Compliant to the WCAG 2.2 or the latest industry standards.

DEL2.2.3: Full Service (providing users with a comprehensive range of additional services and a higher level of attention) Deliverables:

DEL2.2.3.1: The Contractor shall provide the ability for the assessee to file for a tax submission extension and the extension to be workflow tracked

DEL2.2.3.2: The Contractor shall provide the ability for the e-file web portal to send a corresponding alert via email to the responsible account owner/user(s) and the State employee(s) of key account activity, such as and not limited to:

- Account login has occurred

- All Account profile and security changes

- Account file deletions

- Account file modifications

DEL2.2.3.3: The Contractor shall provide the ability to make a land or parcel map request for processing and approval workflow.

DEL2.2.4: The Contractor shall provide a secure e-file web portal.

DEL2.2.4.1: The Contractor shall provide Multi-Factor Authentication (MFA) using SMS codes or an authenticator application to verify user identity.

DEL2.2.4.2: The Contractor shall provide the provision of using "Pass Keys" such as the use of human biometrics, such as Facial Recognition, Fingerprint swipe, etc.

DEL2.2.4.3: The Contractor shall provide SSL/TLS Encryption to secure the connection between a user's browser and the State e-file portal, protecting data in transit from being intercepted.

DEL2.2.4.4: The Contractor shall provide data encryption to protect data stored on the portal's servers (at rest) and data being transmitted (in transit).

DEL2.2.4.5: The Contractor shall provide Role-Based Access Control (RBAC) to assign users specific roles (e.g., admin, customer, employee), which determine what data and features they can access, modify, or share within the portal.

DEL2.2.4.6: The Contractor shall provide strong password policies that include at least 12 to 14 characters long (more is better) with a combination of at least one uppercase letters, lowercase letters, numbers, and symbols. Additionally, provide a visual indicator of a strength meter to enforce the creation of complex passwords to prevent unauthorized access through brute-force attacks.

DEL2.2.4.7: The Contractor shall provide the provision with the option for the login person to view (the "eyeball") the password being typed in.

DEL2.2.4.8: The Contractor shall provide secure file sharing and storage that includes features for secure upload, download, version control, and sharing of documents, often with encryption for all file operations.

DEL2.2.4.9: The Contractor shall ensure e-file web portal compliance adherence to industry standards like SOC 2 (website backend systems meet SOC 2 [System and Organization Controls] standards for protecting customer data), which involves independent verification of data security practices.

DEL2.2.5: The Contractor shall provide a scalable e-file web portal to meet the current needs of 2,000 login users and the future needs of 6,000 BOE and customer login users.

To complete the State e-file web portal, all the above-specified requirements, including EXHIBIT C: FUNCTIONAL AND NON-FUNCTIONAL REQUIREMENTS, must be comprehended and implemented to satisfy the goal of reducing tax schedule submissions by email, United States Postal Service (USPS) mailings, and fax up to 97% in the current process.

In addition to this Deliverable, the Contractor shall also specify any proposed changes that the Contractor deems necessary to enhance the usability, manageability, and security of the e-file web portal.

##### DEL2.3 – IMPLEMENTING TAX AND VALUATION COMPUTATION ALGORITHMS PER STATE ASSESSED PROPERTIES DIVISION (SAPD) AND PRC BUSINESS RULES

DEL2.3.1: The Contractor shall provide a SAPD/PRC board roll tax and valuation computation workflow, as well as tax collection capability, for all of its assessee industries and jurisdictions, with the provision of absorbing at least three new and future industries or jurisdictions in accordance with their respective SAPD business rules and California statutes. This tax and valuation computation workflow capability shall replicate the current tax and valuation computations to the penny, with approximately 8 principal computation flows shared among 12 sub-computation flows or modules that together serve all SAPD industries and jurisdictions and manage intermediate files and data.

DEL2.3.2: The Contractor shall interpret and decode the current IBM ADABAS NoSQL database management system, utilizing the Natural programming language, which performs a portion of the tax valuation computation into the new enterprise software programming of choice. The results are then directed to a series of 45 linked Microsoft Excel spreadsheets with a total of 519 tabs, which additionally require their formulas and macros to be decoded, together, resulting in a seamless, end-to-end, user-interactive, real-time, and multi-featured computational flow.

DEL2.3.3: The Contractor shall provide the replicated tax and valuation computation workflow in an interactive visual manner such as a multi column and row ” accounting like ledger” or “table” format where each row can be an tax or valuation input or subtotal and the very last row, the final computed board roll value for SAPD AND PRC respectively as an illustration only and below with schema details in section EXHIBIT C: FUNCTIONAL AND NON-FUNCTIONAL REQUIREMENTS and with recommendations and suggestions from the Contractor.

Figure 4: Tax and Valuation Realtime Computation Interaction Visualization

DEL2.3.4: The Contractor shall provide for the tax valuation computation workflow to compute simultaneously in the three (3) State valuation methods: Cost, Income, and Market per business rules.

DEL2.3.5: The Contractor shall provide the ability for the tax and valuation computation workflow to interface with external data sources and system platforms to retrieve data and information to augment computation and complete its end result and self-identify (flag) any erroneous data entry elements that deviate or are contrary to normal expected values within predetermined business rules ranges. External Data sources include:

  - "RealQuest" (https://pro.realquest.com/) data source

  - CHARM (Car Hire Accounting Rate Master)

  - Rail Inc.

  - Official Railway Equipment Register Book (ORER)

To complete the SAPD tax and valuation computation flow, all specified requirements, including the EXHIBIT C: FUNCTIONAL AND NON-FUNCTIONAL REQUIREMENTS, must be comprehended and implemented to satisfy the goal of automating and streamlining tax Computations, Allocation Computations, and Tax Collections Per Business Rules up to 98%.

Along with this tax and valuation computation replication Deliverable, the Contractor shall also specify within this Deliverable any proposed changes that the Contractor deems necessary that may add to the automation, accuracy or ease of use of the interactive computation flow.

##### DEL2.4 – IMPLEMENTING BOE DATA GOVERNANCE REQUIREMENTS AND POLICY

The Contractor shall provide a suitable-sized data lake for the STARS Solution as needed with its corresponding DMDD documents for the State peripheral databases (transactional, data repository, and archive). The data models presented in this Deliverable shall define all the data elements, relationships, constraints, access methods, and other related details for the data lake and the STARS data repository. The Contractor shall collaborate and seek input from the State to develop the data model for all STARS Solution databases, including but not limited to transactional, data repository, and archive databases. The data lake and STARS data repository shall incorporate a denormalized data model optimized for reporting and data analytics.

The Contractor shall implement the State data governance plan and policies.

DEL2.4.1: The Contractor shall implement the BOE Meta Data Strategy: The extraction and organization of all metadata that includes a data dictionary that shall catalog the organization, content, and conventions of the State TSD centralized storage system, archive databases, and any data storage repository, including but not limited to the names and descriptions of all tables and columns and additional details such as the type and length of each data element, a list of permissible values for columns, and other related centralized storage schema details.

DEL2.4.2: The Contractor shall perform All Necessary Data Migration to complete the centralized storage for the operation of the STARS Solution system (see Figure 5: Solution Centralized Storage Diagram With Data Migration)

Figure 5: Solution Centralized Storage Diagram With Data Migration

DEL2.4.3: The Contractor shall implement the Metadata strategy and plan during the data migration

DEL2.4.4: The Contractor shall extract and apply metadata to existing BOE data and files that have not been scanned for their metadata

DEL2.4.5: The Contractor shall cleanse and validate migrated data fields without the use of external data subscription services.

DEL2.4.6: The Contractor shall catalogize all migrated appropriately per data governance cataloging specifications.

DEL2.4.7: The Contractor shall implement a continuous and ongoing capturing and updating of all metadata from all documents and data provided to or generated by the new STARS Solution per data governance rules and policy in the production mode of operation.

DEL2.4.8: The Contractor shall provide the ability for account data cleansing and validation per governance requirements and guidelines, real-time or as a workflow, without the use of external subscription data services.

DEL2.4.9: The Contractor shall enforce data and file/document retention per data governance policy:

  - File Retention

  - File Deletion/Erase

  - File Data Back-Ups

To deliver and complete the BOE Data Governance Strategy, plan, and policies, all specified requirements, including the EXHIBIT C: FUNCTIONAL AND NON-FUNCTIONAL REQUIREMENTS, must be comprehended and implemented to satisfy the goal of data governing up to 98% of the BOE’s data.

The Contractor shall also specify within this Deliverable any proposed changes that the Contractor deems necessary to enhance the completeness of the BOE’s data governance effort.

##### DEL2.5 – PROVIDE A CONTENT MANAGEMENT AND ACCESS INTERFACE TO ALL OF THE STATE’S CONTENT STORED IN THE CDTFA STORAGE INFRASTRUCTURE TO CREATE A SEARCHABLE, CENTRALIZED STORAGE SYSTEM

DEL2.5.1: The Contractor shall design, develop, optimize, implement, and seamlessly integrate a data enterprise content management and access interface to the existing CDTFA/TSD storage infrastructure and systems of all of the State’s data and files.

DEL2.5.2: The Contractor shall store the respective data types (blocked, unblocked, and structured, unstructured) in the appropriate cost-effective storage technology and type.

DEL2.5.3: The Contractor shall provide and develop a document UPC or QR coding management and classification system for all printed and electronically transmitted documents for tracking per data governance guidelines and policies. Subsequently, this UPC or QR coding management system will be able via a handheld reader read and translate the encoded data and display the encoded data in the solution tool. This encoded UPC or QR coding will include the following but not limited to:

  - Date the document was created

  - Date the document was printed or sent

  - Name of the BOE employee who drafted the document

  - Recipient SBE or account number

  - Form, schedule, letter. etc. template revision number and revision date

  - Means of delivery: FedEx, USPS, UPS (United Parcel Service), etc.

DEL2.5.4: The Contractor shall provide a storage location for the real property appraiser to store work product.

DEL2.5.5: The Contractor shall provide "RealQuest" (https://pro.realquest.com/) data research results download for storage per data governance requirements and guidelines of categorization and search per work assignment

DEL2.5.6: The Contractor shall implement data governance policy for file retention and accounts under litigation

DEL2.5.7: The Contractor shall implement data search capabilities as specified in the case management deliverables.

To complete the content management and access interface to all of the State’s content in the centralized storage system, all specified requirements, including the EXHIBIT C: FUNCTIONAL AND NON-FUNCTIONAL REQUIREMENTS, must be comprehended and implemented.

The Contractor shall also specify any proposed changes that the Contractor deems necessary to enhance the usability, manageability, and security of the enterprise content management and access interface centralized storage system.

##### DEL2.6 – PROVIDING THE CAPABILITY FOR FULL DATA VISUALIZATION FOR AD HOC REPORT AND LETTER GENERATION, WHILE PROVIDING DASHBOARDS OF WORKFLOW PROGRESS AND KEY BUSINESS/PERFORMANCE INDICATORS (KPI)

DEL2.6.1: The Contractor shall provide full data visualization capabilities for report and letter generation, in addition to utilizing the State historical and/or real-time data to create dashboards of selected workflow progress and key business or performance indicators. These dashboards can be creatively integrated in the respective solution modules, whether it be in the case management module, a standalone GUI module, or displayed in a new window.

DEL2.6.2: The Contractor shall provide ease of use with a friendly menu-driven user interface to generate documents, reports, and letters per the State format guidelines and output per the State required format (PDF, DOCX, TXT, etc.) to the following, but not limited to:

- The State Assessed Properties Division (SAPD) Board Roll

- The Board of Equalization "Appraisal Data Reports"

- PRC Inventory Letters

- End of Audit Closure Summary Letters

- Provide the ability to generate the statutory appeals results document electronically.

DEL2.6.3: The Contractor shall provide the ability to perform market research on the State internal data given certain keyword search parameters or a combination of Boolean word search parameters, to provide a written report or graphical data of the market research.

DEL2.6.4: The Contractor shall provide the ability to display Dashboarding of workflow progress and key business or performance indicators (KPI). The dashboard may be integrated into workflows or displayed as a separate graphic window. This includes the following but not limited to:

- Provide the ability to track all tax filing status and extensions progress and status via a dashboard for the key business segments of Unitary, Real Property, PRC, Audit, Appeal, and Appraisals.

- Provide the ability to track the State work task progress, review, and approval thereof from supervisors and managers.

DEL2.6.5: The Contractor shall provide the ability to budget and track any work or task assignments with CDTFA’s “Timekeeping Application” or equivalent, with the results appropriately displayed in the solution.

To complete the SAPD tax and valuation computation flow, all specified requirements, including EXHIBIT C: FUNCTIONAL AND NON-FUNCTIONAL REQUIREMENTS, must be comprehended and implemented to satisfy the goal of reducing manual intervention up to 98% in the current process.

The Contractor shall also specify within this Deliverable any proposed changes that the Contractor deems necessary to enhance the use of the data visualization capabilities, report and letter generation, and dashboarding of key workflows and KPI’s.

##### DEL2.7 - IMPLEMENTING A FULLY INTEGRATED CASE MANAGEMENT CAPABILITY TO ALL OF THE STATE’S ASSESSEES AND CUSTOMERS TO ADMINISTER, INVESTIGATE, AND TRACK ACCOUNT BUSINESS ACTIVITIES

DEL 2.7.1: The Contractor shall design, develop, and implement a seamless case management solution module to administer, investigate, and track all assessee or customer account business activities. This includes the following additional deliverables:

DEL2.7.1.1: The Contractor shall provide an Easy-to-use case management GUI with the assessee or customer account information prepopulated in the case management solution module.

DEL2.7.1.1.1: The Contractor shall provide a convenient assessee account information summary and tax valuation status “window’ of relevant information (To Be Determined)

DEL2.7.1.2: The Contractor shall ensure all Taxpayer addresses are stored in one searchable database or data repository.

DEL2.7.2: The Contractor shall provide the ability for the case management module to perform Assessee and Customer Account Administration. This includes the following additional Deliverables:

DEL2.7.2.1: The Contractor shall provide the ability to log and track assessee tax filing Extensions in the assessee account activity history log.

DEL2.7.2.2: The Contractor shall provide the ability to set an account audit flag manually or automatically per business rules or predetermined audit factor parameters and provide a comment box or “traveling note” with the audit flag initiation.

DEL2.7.2.3: The Contractor shall provide an electronic "traveling notes" page with every document for approval routing and specified workflows. Provide the appropriate read acknowledgments to the “traveling notes” with the corresponding traveling note initiator “to read” thread.

DEL2.7.2.4: The Contractor shall provide the ability to record and provide an audit trail, journaling of the State users throughout the solution.

DEL2.7.3: The Contractor shall provide the ability for the case management module to perform Assessee and Customer Account Communications. This includes the following additional Deliverables:

DEL2.7.3.1: The Contractor shall provide the ability to automate workflow assessee account notifications and reminders of tax filing obligations via email and/or USPS Mail per business rules.

DEL2.7.3.2: The Contractor shall provide the ability to transmit case management business communication via email or paper letter mail via the USPS per statutory laws

DEL2.7.3.3: The Contractor shall provide the ability to communicate with various counties via predetermined email distribution lists

DEL2.7.3.4: The Contractor shall provide a county login “side portal” to facilitate the State and county auditor email communication and document downloads and uploads

DEL2.7.4: The Contractor shall provide the ability for the case management module to perform Assessee and Customer Account investigations and tracking. This includes the following additional Deliverables:

DEL2.7.4.1: The Contractor shall provide the ability to track all electronic and/or paper correspondence, but not limited to: date of letter, date sent, notification type, means of delivery, etc.

DEL2.7.4.2: The Contractor shall provide the ability to perform intelligent search queries to access all the assessment and assessee account data

DEL2.7.4.3: The Contractor shall provide the ability to track the State and County document downloads and uploads

To complete the integrated case management, all specified requirements, including EXHIBIT C: FUNCTIONAL AND NON-FUNCTIONAL REQUIREMENTS, must be comprehended and implemented to satisfy the goal of reducing account research and management by up to 75% to the current process.

The Contractor shall also specify within this Deliverable any proposed changes that the Contractor deems necessary to enhance the features, usability, and manageability of the integrated case management capability.

##### DEL2.8 – IMPLEMENTING THE STATE EFFORTS TO “GO PAPERLESS” TO INCLUDE A UNITED STATES POSTAL SERVICE (USPS) MASS MAILINGS AND MASS E-MAIL SYSTEM, PER BUSINESS AND STATUTORY REQUIREMENTS

DEL2.8.1: The Contractor shall design, develop, and implement a seamless paperless business workflow for the State to reduce the use of paper and to automate paper workflow processes per statutory requirements or where paper cannot be eliminated. This includes the following additional Deliverables:

DEL2.8.2: The Contractor shall provide the ability to digitize the paper filings and subsequently store them in the central data storage repository per the data governance requirements of categorization, with metadata determined. Upon the digitizing process, it shall provide a special “flag” or designator with the digitized document the following “flags” or “designators”:

  - Enable Legal Flag or designator

  - Enable a Litigation Hold Flag or designator

  - Provide a pop-up bubble or message window to communicate an important legal case issue that is associated with the document

DEL2.8.3: The Contractor shall design, develop, and implement a fully integrated United States Postal Service (USPS) batch mass mailing process and system to include but not limited to:

- Provide a simple and easy unified mail distribution addressee selection to a letter template mail merge process to complete the letter with subsequent printing to paper with embedded UPC or QR coding.

- Provide the ability to seamlessly interface with the CDTFA mass mailing system to print, letter envelope insertion, and postage application mailing system, and mail to the State assessees, customers, and/or clients with the option to select the envelope type such as those with an address recipient transparent window and those without.

DEL2.8.4: The Contractor shall design, develop, and implement a fully integrated batch mass emailing process to transmit statutorily required letters, reports, and any communication electronically, including, but not limited to:

- Easily creating email distribution lists

- Creating a library to manage and edit email distribution lists

The Contractor shall provide and implement the State’s paperless workflow environment with its goal to reduce mailing costs up to 90%. The Contractor shall also specify within this deliverable any proposed changes that the Contractor deems necessary to enhance the paperless effort in the State usability, manageability, and security of the e-file web portal.

##### DEL2.9 – IMPLEMENTING THE AUDIT AND APPRAISAL BUSINESS WORKFLOW EFFICIENCIES REQUIREMENTS

DEL2.9.1: The Contractor shall design, develop, and implement a seamless visual audit and appraisal business workflow, including monitoring and progress tracking of the full effort and respective detail tasks and task owners, to improve efficiency and quality. Additionally, this audit and appraisal module shall be enabled to present and provide supplemental assessee account data to assist the auditors or appraisers and archive all final results. These Deliverables are to be done for the following audit and appraisal work functions:

- Audit case work

- Real Property appraisals

- Unitary appraisals

- PRC appraisals

- Appeal appraisals

DEL2.9.2: The Contractor shall provide the ability to access and modify all the respective annual audit and appraisal factors in the respective workflows

DEL2.9.3: The Contractor shall provide the ability to visually and graphically track the location of approximately 40,000 land parcels and geographically group parcels into work assignments.

DEL2.9.4: The Contractor shall provide the ability to visually track the PRC assessee billing and collection function and overall workflow.

To complete, enable, and improve the audit and appraisal process, tracking thereof, reporting, and archiving, all specified requirements, including the EXHIBIT C: FUNCTIONAL AND NON-FUNCTIONAL REQUIREMENTS, must be comprehended and implemented to satisfy the goal of increasing the quality of audits and appraisals up to 30% respectively.

The Contractor shall also specify, within this Deliverable, any proposed changes that the Contractor deems necessary to enhance the usability, tracking, manageability, and visual display of audit and appraisal efficiency and quality monitoring.

##### DEL2.10 – IMPLEMENT THE CAPABILITY FOR BROADBAND CONNECTIVITY TO THE SOLUTION FOR REMOTE UPLOAD OR DOWNLOAD OF CONTENT FOR REAL PROPERTY WORK

The Contractor shall enable and provide broadband connector via broadband provider to the solution to enable connectivity to perform and enable services and conveniences associated with broadband connectivity for real property work assignments such as the following, including but not limited to:

- Provide the ability to upload pictures from appraisers and auditors to the assessee account

- Provide the ability to upload work note files from appraisers and auditors to the assessee account Placeholder

To complete the Solution’s broadband connectivity, all specified requirements, including the EXHIBIT C: FUNCTIONAL AND NON-FUNCTIONAL REQUIREMENTS, must be comprehended and implemented.

The Contractor shall also specify within this Deliverable any proposed changes that the Contractor deems necessary to enhance the usability of the broadband connectivity must be approved by the State.

##### DEL2.11 – PROVIDES METADATA FOR ALL DATA NEEDED AND GENERATED BY THE STARS SOLUTION

The Contractor shall provide metadata fields for all data needed and generated by the STARS Solution. These corresponding metadata fields and corresponding data will be coordinated in consultation with respective State file end-users, Subject Matter Experts (SME), and the STARS Solution users.

##### DEL2.12 – DEVELOP STARS SOLUTION TRAINING MATERIALS AND COMPLETE TRAINING

The Contractor shall provide the STARS Solution and user training materials and curriculum, including but not limited to online training components and all other material identified in the State-approved STARS Training Plan. The Contractor shall provide application training to the State-identified team members and 10-30 users (requirement 2.16) with the following training as a minimum:

- STARS Solution System Administration and Security Training

- Overall STARS Solution platform training for other State users, up to thirty (30)

The State trainees may include system administrators, technical support team members, and State personnel on the usage, management, and enhancement of the STARS Solution as configured and deployed. The Contractor shall be responsible for delivering, video recording, and maintaining completed training, training materials, functional guides, and online training modules for all end-user-accessible Solution components, as well as user manuals, runbook(s), infrastructure, communication, and operational documentation for the STARS Solution. Training aids, administration guides, manuals, and other training materials shall be provided by the Contractor as part of the Solution. As part of the STARS Training, the Contractor shall provide complete knowledge transfer to the State for STARS Technical and Business Process information so that the State can manage, maintain, and enhance the STARS Solution via CD ROM or USB Key.

##### DEL2.13 - PERFORM SYSTEM FUNCTIONALITY TESTING

The Contractor shall deliver and execute the Test Management Plan (EXHIBIT D: DELIVERABLES AND MILESTONES TABLE and DEL1.9 Test Plan). The Contractor shall be responsible for all test-related plans. The Final Test Plan for each release is a document that details the strategy, objectives, resources, and processes for testing and provides a schedule/timeline for all capabilities within the testing phase. The Final Test Plan also includes details on the environment, types of testing, what is and is not being tested, the testing approach, and testing procedures that must align with industry standards, specifying each test case's preconditions, steps, and expected outcomes, required data, users, the eventual STARS tax/valuation calculations, the e-file web portal, functional modules, workflows, and end-to-end tests, etc. The Final Test Plan will be used as part of verifying and ensuring that STARS design specifications and requirements are fully met. The Final Test Plans for each release shall be reviewed and approved by the State.

A. PERFORMANCE SYSTEM FUNCTIONALITY TESTING

After approval by the State, the Contractor shall implement the TMP and recommend updates that align with the Contractor's test management approach. The Contractor shall complete all testing Deliverables as detailed in the TMP and the associated task Deliverables. These Deliverables must be completed and accepted using RFP ATTACHMENT 22: DELIVERABLE ACCEPTANCE DOCUMENT TEMPLATE.

The Contractor shall set up and configure at a minimum six (6) separate environments as follows:

- Development

- Solution Testing

- User Acceptance Testing (UAT)

- Staging

- Production

- Training

The Contractor shall incorporate the STARS Solution design with separate environments above to ensure the following:

- The non-production environments shall be kept separate from the production system.

- The system-testing and UAT environment shall include testing of new functionality/configuration, integration testing of each change, and full system integration testing once deployed in the production environment.

B. PERFORMANCE TEST SCRIPTS AND CASES

Specific test scripts and test cases shall be developed by the Contractor and approved by the State’s Project management and designated State personnel. Test scripts and test results shall be linked to requirements established in the RFP’s requirements (EXHIBIT C: FUNCTIONAL AND NON-FUNCTIONAL REQUIREMENTS) and the SOW. At a minimum, test scripts shall include the following:

- Entrance and exit criteria for each testing cycle.

- Steps necessary to run through the test scenarios.

- Dependencies

- Data and data source requirements

- Users needed

- Traceability between the test scenario and solution requirements (EXHIBIT C: FUNCTIONAL AND NON-FUNCTIONAL REQUIREMENTS) (i.e., the script should identify which detailed Solution requirements are being tested)

- Resource needs from interface or external partners, if any

- Performance, Capacity, and Load Testing

- Security and Business Continuity and Disaster Recovery

- Expected results.

The Contractor shall provide test results for each test phase to the State for Acceptance of the testing Deliverable for each Solution code release phase per RFP ATTACHMENT 21: DELIVERABLE EXPECTATION DOCUMENT TEMPLATE.

##### DEL2.14 – PERFORM SOLUTION TESTING

The Contractor shall deliver and execute to the Test Management Plan (EXHIBIT D: DELIVERABLES AND MILESTONES TABLE and DEL1.9 Test Plan). The Contractor shall be responsible for all test-related plans. The Final Test Plan for each release is a document that details the strategy, objectives, resources, and processes for testing. The Final Test Plan provides a schedule/timeline for all capabilities within the testing phase and includes details on the environment, types of testing, what is and is not being tested, the testing approach, and testing procedures that must align with industry standards, specifying each test case's preconditions, steps, and expected outcomes, required data, users, the eventual STARS Solution tax/valuation calculations, the e-file web portal, functional modules, workflows, and end-to-end tests, etc. The Final Test Plan will be used as part of verifying and ensuring that the STARS Solution design specifications and requirements are fully met. The Final Test Plans shall be reviewed and approved by the State.

A. SOLUTION TEST IMPLEMENTATION

After approval by the State, the Contractor shall implement the TMP and recommend updates that align with the Contractor's test management approach. The Contractor shall complete all testing Deliverables as detailed in the TMP and the associated task Deliverables. These Deliverables must be completed in order to be accepted by the State using RFP ATTACHMENT 22: DELIVERABLE ACCEPTANCE DOCUMENT TEMPLATE.

The Contractor shall set up and configure six (6) separate environments, including but not limited to the following:

- Development

- Solution Testing

- User Acceptance Testing (UAT)

- Staging

- Production

- Training

The Contractor shall incorporate the system design with separate environments above to ensure all of the following:

- The non-production environments shall be kept separate from the production system.

- The system-testing and UAT environment shall include testing of new functionality/configuration, integration testing of each change, and full system integration testing once deployed in the production environment.

B. SOLUTION TEST SCRIPTS AND CASES

Specific test scripts and test cases shall be developed by the Contractor and approved by the State’s Project management and designated State staff. Test scripts and test results shall be linked to requirements established in the RFP’s requirements (EXHIBIT C: FUNCTIONAL AND NON-FUNCTIONAL REQUIREMENTS) and the SOW. At a minimum, test scripts shall include the following:

- Entrance and exit criteria for each testing cycle.

- Steps necessary to run through the test scenarios.

- Tax and Valuation calculations at key to be determined (TBD), subtotal checkpoint or validation amounts exactly with known good values.

- Dependencies

- Data and data source requirements

- Users needed

- Traceability between the test scenario and solution requirements (EXHIBIT B) (i.e., the script should identify which detailed solution requirements are being tested)

- Resource needs from interface or external partners, if any

- Performance, Capacity, and Load Testing

- Security and Business Continuity and Disaster Recovery

- Expected results.

The Contractor shall provide test results for each test phase to the State for Acceptance of the testing Deliverable for each solution code release phase per RFP ATTACHMENT 21: DELIVERABLE EXPECTATION DOCUMENT.

Unless the Parties mutually agree to remove a functional or non-functional requirement and/or SOW Deliverable, all functional and non-functional requirements and SOW Deliverables defined in the RFP’s requirements (EXHIBIT C: FUNCTIONAL AND NON-FUNCTIONAL REQUIREMENTS) and EXHIBIT A: SOW Deliverables must meet and pass system, user acceptance, regression, and performance testing.

C. SOLUTION TESTING STARS SOLUTION

The Contractor will prepare and enable the STARS Solution to be tested according to the TMP described in the previous section which will include the testing that includes but is not limited to the following:

- Unit or Functional Block Testing.

- Solution configuration management testing.

- Solution Journaling and audit trail capabilities.

- Integration Testing of entire STARS Solution with the functional blocks.

- Tax and Valuation Computations are “to the penny” rounding with SAPD and PRC assesses.

- Integration testing with external data sources and service providers (i.e. payment processors).

- Connectivity and data transfers with external data sources.

- Performance testing search speed, Board Roll computation to input changes, Data Governance Policy administration and indexing.

- Regression Testing with code changes.

- Stress and load Testing. (need prospective load)

- Capacity Testing.

- Accessibility Testing.

- System End-to-End Testing.

- Data Integrity Testing.

- Security Testing.

- Availability Testing.

- Disaster Recovery and Failover Testing.

- Contractor Specific System Integration Testing.

- Performance Test Report (Per-TR)

Upon the completion of testing above, the Contractor shall publish the corresponding Deliverable reports:

DEL2.14.1: Security Acceptance Test Report (SA-TR)

DEL2.14.2: System Vulnerability Report

DEL2.14.3: Data Reconciliation, Cleanup and Conversion Report (DCCR)

DEL2.14.4: Updated RTM

DEL2.14.5: Configuration Management Activity Summary Report

DEL2.14.6: Release Readiness Checklist

The State reserves the right to identify any additional type of testing to be performed during the Project. The Contractor shall incorporate into their Test Management Plan any additional type of testing the State may perform.

##### DEL2.15 - ENABLE, ADMINISTER, AND FACILITATE USER ACCEPTANCE TESTING (UAT)

The Contractor shall enable, administer, facilitate, and support the User Acceptance Testing of the STARS Solution per the UAT test plan, to include but not be limited to the following Deliverables:

DEL2.15.1: The Contractor shall provide a separate pre-production version of the STARS Solution for UAT testing of all major functional blocks that include:

- E-File Web Portal

- Data Governance Operations and Functions

- Tax and Valuation Computations for SAPD and PRC Board Roll

- Case Management

- Data Visualization for report generation, KPI dashboarding and task tracking

- Paperless Effort and Mass Mailing (email and USPS paper mail)

- Broadband connectivity with file uploading

- Audit and Appraisal Efficiencies

- Centralize Storage with Search Capabilities

DEL2.15.2: The Contractor shall pre-populate UAT test accounts with respective data for testing as needed per various UAT TBD test scenarios

DEL2.15.3: The Contractor shall enable all automated processes and features within the STARS Solution for a full end-to-end SAPD Board Roll and PRC tax and valuation determination process for prior year(s) assessee(s) and a number (TBD) fictitious assessee test cases and scenarios

DEL2.15.4: The Contractor shall provide on-site personnel support of the user acceptance testers for the duration of the UAT test period or as needed for a successful UAT launch

Upon the completion of testing above, the Contractor shall publish the corresponding Deliverable reports and make STARS Solution changes per UAT tester feedback:

DEL2.15.5: The Contractor shall provide a detailed UAT Test Results Report

DEL2.15.6: The Contractor shall implement all agreed-upon UAT tester feedback changes to the STARS Solution.

DEL2.15.7: The Contractor shall perform STARS Solution regression testing to determine and verify whether code changes to address UAT fixes or enhancements have negatively impacted existing, previously functional features, with the main goal of ensuring the overall stability and quality of the system are maintained with the newly introduced modifications.

The State reserves the right to identify any additional type of UAT to be performed during the Project. The Contractor shall incorporate into their Test Management Plan any additional type of testing the State may perform.

## STAGE III: PROJECT CLOSE OUT AND WARRANTY PERIOD COMMENCEMENT

##### DEL3.0 – OPERATIONS AND CLOSE OUT

If State exercises the option for Maintenance and Operations, the Contractor shall provide the State with complete STARS system maintenance and technical support services, concurrently with the twelve (12) month warranty Deliverable that is confirmed by the State.

Required service levels for Stage III are defined in SECTION 33 SERVICE LEVEL AGREEMENTS (SLAs).

##### DEL3.1 – OPERATIONS SUPPORT AND PERFORMANCE TASKS AND ACTIVITIES

The Contractor shall provide Maintenance and Operations Support and Help Desk for the STARS system. Maintenance services shall include, but not be limited to, performing preventive maintenance such as repair and testing of application defects, application tuning, component upgrades, and database reorganizations.

DEL3.1.1: The Contractor shall set up a Help Desk and provide the following during Stage III – Close Out and Optional One-Year Maintenance and Operations on a continuing basis:

- Intake of deficiencies from the State.

- Correct all software deficiencies identified in the STARS Solution.

- Monitor STARS system performance.

- Track reports of system errors, problems, and issues.

- Provide and manage an issue log.

- Provide a change log of all outstanding and resolved changes.

- Provide an escalation process by which all reported problems can be managed until fully resolved.

- Provide technical support for problem resolution and troubleshooting for the duration of the maintenance period.

- Provide technical support reports (e.g., number of requests received, types of requests, time to resolution, outstanding calls/issues).

The Contractor’s Help Desk personnel shall be on call during business work days from 7:00 AM to 5:00 PM in order to meet the Incident Severity and Response Times stated in Table 9 (SECTION 33 SERVICE LEVEL AGREEMENTS (SLAs)).

There are two levels of Help Desk support:

- Tier 1 support represents the initial point of contact for end-users seeking technical assistance. The State will provide Help Desk support at this level. First level support staff will route incidents that cannot be resolved at first level support to second level support.

- Tier 2 support deals with issues beyond basic troubleshooting. The Contractor must provide Tier 2 Help Desk support and use the State 's Incident tracking system for triage and resolution.

  - If the issue results in a STARS Solution fix, the Contractor must be able to track the fix in the State ’s Incident tracking system, along with submitting a ticket within the Contractor’s electronic ticketing system, to track the Contractor’s resolution of the fix. All information regarding the Contractor's fix ticket must be entered into the State 's ticketing system within the Tier 2 ticket tracking the issue.

The State will categorize the tickets in alignment with SLAs in this Agreement. The Contractor will be responsible for resolving all the State submitted tickets in alignment with SECTION 33. SERVICE LEVEL AGREEMENTS (SLAs) and SECTION 34. LIQUIDATED DAMAGES.

DEL3.1.2: Ninety (90) calendar days before the scheduled submission of the last Deliverable and State’s Acceptance of such, a Transition Out Plan shall be submitted. The Plan shall describe the Contractor's approach for final knowledge transfer to the State, generating STARS Solution documentation, and STARS Help Desk setup.

DEL3.1.3: The Contractor shall deliver STARS Solution documentation at the close of the Project in both electronic soft copies (Adobe PDF format), in CD-ROM, and on file share as well as printed and bound format. The documentation should describe and support the entire STARS Solution, including but not limited to the following aspects: system design and architecture specifications; requirements; program design; programming and ancillary processing components; system help, information messages, and error messages; database schema, enterprise content management (ECM) architecture, system data model and data dictionary; hardware, equipment and software configuration settings; interface specifications and communication protocols; end-user usage and training materials; testing; STARS system operations; and help desk and operations support of the STARS Solution. Refer to SECTION 11: Contractor Role and Responsibilities for software license cost and transfer of ownership.

The STARS Solution documentation shall also include, but not be limited to the following types of documentation:

- System operations

- System technical documentation

- System operational recovery procedures

- System end users' documentation

- System technical schematics

- Updated general and Detailed System Design to reflect the applications as implemented

- Database(s) schema, data dictionary, and data catalog

- Enterprise Content Management Architecture and Schema

- Application program interfaces

- As-built documentation of all configurations, modification, and/or programming

- Deployment specifications and

- System maintenance documentation

- The portions of this Deliverable that constitute updated versions of documentation previously provided in Deliverables for Stage II.

- STARS source code and documentation shall include documentation of all changes made to the code since the submittal of Deliverable 2.2, and the STARS Solution’s twelve (12) Month Warranty, in a format approved by the State.

- All delivered source code, object code (or equivalent), source code documentation, and system documentation described above, shall reflect the state of the STARS Solution as of the end of Stage III – Closeout and Warranty Period Commencement including all changes necessitated by changes to the STARS Solution, materials, and procedures during Stage III.

- SECTION 33 SERVICE LEVEL AGREEMENTS (SLAs) outlines the criteria for each Severity Level. Each Severity Level specifies the Service Level Objectives for the Contractor’s Time to Respond upon identification of a Deficiency and/or the State notification of a deficiency and for the Contractor’s time to correct a deficiency. Refer to EXHIBIT B: Budget Detail and Payment Provisions for remedies to failure to meet the Service Level Objectives.

##### DEL3.2 – STARS FINAL SYSTEM AND INTERFACES INTEGRATION TESTING

The Contractor shall perform its final end-to-end system and full regression testing for the entire STARS Solution after all Program Increments are complete. The Contractor shall work with the State, external stakeholders, and Electronic Filing Software Providers in conducting and completing the Integration Testing to include at a minimum Functional Testing, Requirements and Features Testing, Interface Testing, Performance Testing, Load, Stress Testing, Security, and Failover Testing.

The Contractor shall provide System Configuration documentation detailing the configuration and deployment of the STARS Solution to the Development, Test, Training, and all other environments.

The Contractor shall work with the State to ensure the system configuration documentation provides the details necessary for the State to successfully configure and deploy the STARS Solution.

##### DEL3.3 – STARS FINAL END-TO-END ACCEPTANCE TESTING

The Contractor shall provide System Configuration documentation detailing the configuration and deployment of the STARS Solution User Acceptance Testing environments, in accordance with the approved System Technical Architecture Document (STA),  Detailed System Design Document (DSD) , STARS PMP, the Contractor’s Project Schedule, and the STARS Final End-to-End Acceptance Testing, Requirements and Feature Testing Completion and Final Deployment DED for which the  State has provided Acceptance. The Contractor shall work with the State to ensure the updated system configuration documentation provides the details necessary for the State to successfully configure and deploy the STARS Solution in the above-referenced environment (User Acceptance Testing).

The Deliverable shall include the following at a minimum (See also SECTION 25: System Acceptance Procedures)

- Updated System Configuration documentation.

- Updated Defect Log and Test Result Reports.

- Updated Source Code; and

- Updated STA and DSD.

Acceptance Criteria for this Deliverable shall include a written confirmation from the State of the successful deployment which meets the requirements of the STA and DSD corresponding to the STARS environment.

##### DEL3.4 TRANSITION OUT SERVICES

The Contractor shall provide transition-out support services, to include but not be limited to the following:

- Completion of all tasks identified in the Transition-Out Plan

- A Transition-Out Report that includes, but is not limited to, the following:

  - Documentation that shows all exit criteria was met.

  - Outstanding, unresolved transition issues.

  - Recommended additional transition activities and tasks.

The Transition Period may be modified as agreed upon in writing by the Parties in a Contract Amendment. Contractor agrees to compensate the State for damages or losses the State incurs as a result of Contractor’s failure to comply with this section in accordance with the Limitation of Liability provision set forth in INFORMATION TECHNOLOGY GENERAL PROVISIONS – CLOUD COMPUTING SERVICES DGS PD 402-ITGP CLOUD (REVISED 2/20/2025), SECTION 12, LIMITATION OF LIABILITY (SEE LINK IN SECTION 36).

# DELIVERABLES EXPECTATION DOCUMENT

The Contractor shall use a Deliverable Expectation Document (DED), RFP ATTACHMENT 21: DELIVERABLE EXPECTATION DOCUMENT (DED), to secure approval from the BOE STARS Project Director for the format and content of Deliverables.

The Contractor will not begin work on a Deliverable until the State and the Contractor have approved the DED. The DED will define the Deliverable specifications and Acceptance Criteria. The Deliverable will address all components required by the Contract and any areas agreed upon subsequently through meetings and planning sessions. The State expects all Deliverables to be presented sequentially at the Deliverable Project Stages. The Contractor shall provide Deliverables to the State Contract Representative by the due date specified on the approved Project Schedule unless the State has granted written permission on the DED to deviate from the schedule. Deliverable documents will be comprehensive in their level of detail and quality, be professional in presentation, and consistent in style and quality. If a document is the composite work of multiple individuals within the Contractor’s organization, the Contractor shall ensure consistency in the final document.

Completion of each Deliverable listed above is subject to the State approval, as described in this SECTION 19 DELIVERABLE EXPECTATION DOCUMENT.

In all cases, the Contractor shall verify application compatibility with the BOE STARS Project Director prior to creation or delivery of any electronic documentation. All interim diagrams, charts, or other graphics inserted into Deliverables shall be provided in the original file format used for their creation. An example might be a Microsoft Visio process flow inserted into a document; the original Visio source file shall also be provided electronically. Any deviations to these standards shall be approved in writing by the BOE STARS Project Director.

Deliverables shall be on a standard 8 ½” x 11” page. Electronic versions shall be stored in a State designated central repository and remain the sole property of the State. The delivery media shall be compatible with the State storage devices.

## TRANSMITTAL OF DELIVERABLES

The Contractor shall submit for review and approval a formal transmittal letter from the Contractor’s Project Manager addressed to the BOE STARS Project Sponsor or designee for each Deliverable. The Deliverable must contain an Approval Page, which indicates the date submitted, to whom submitted, the Deliverable author, and the title of the Deliverable. The DED prepared for the specific Deliverable approval must be attached to the transmittal.

In submitting a Deliverable for State Acceptance, the Contractor represents that, to the best of its knowledge, it has performed the associated tasks in a manner that will, in concert with other tasks, conform to the relevant terms and conditions of the STARS Contract and conform to and meet applicable Acceptance Criteria. Each Deliverable submitted to the BOE STARS Project Sponsor or designee for review and acceptance shall have a Deliverable Certification Cover Letter from the Contractor. The Deliverable Certification Cover Letter shall contain the following Certification: “I certify that this Deliverable has been prepared in accordance with the relevant terms and conditions of the STARS Contract and conforms to and meets its applicable Acceptance Criteria." The Deliverable Certification Cover Letter shall also contain a Certification that the Contractor has performed an internal quality assurance review of the Deliverable. Deliverables shall be signed as complete by a Contractor representative who is authorized to sign legal documents for the Contractor's firm or organization.

## DELIVERABLE ACCEPTANCE DOCUMENT

All concluded work must be submitted for review and Acceptance or rejection to the State Project Manager using the RFP ATTACHMENT 22: DELIVERABLE ACCEPTANCE DOCUMENT (DAD). A Deliverable will not be accepted by the State unless it is consistent with the DED approved by the State Project Manager.

Project work and Deliverables that involve software programs, as well as any implementation or installation activities, are subject to acceptance testing under the terms of this Agreement. Acceptance testing is intended to ensure that the services acquired under this Agreement result in successful implementation and continued satisfactory levels of performance. The products and services acquired must conform to the State’s business, technical, and performance requirements while meeting the Contractor's specifications, performance standards, and warranties.

Acceptance testing shall include verification by the State Project Manager and the Contractor that each applicable Deliverable meets the requirements identified within the DED. It shall be the State’s sole determination as to whether acceptance testing has been successfully completed and is acceptable to the State.

For document Deliverables, the Contractor’s ongoing performance will be evaluated by the State Project Manager by reviewing the Contractor’s Secure Application Integration and Continuous Deployment (DevSecOps) dashboard and weekly status reports and reviewing the quality and completeness of the relevant document(s).

Acceptance of the STARS Solution Deliverables will be governed by this Agreement. Acceptance occurs when (a) a Deliverable has met all specified Acceptance Criteria set forth for that Deliverable in the relevant DED and (b) the State has provided the Contractor with a formal written Acceptance using a DAD. The State Acceptance of each Contractor Deliverable submitted for the State review and Acceptance will be communicated exclusively through a DAD to the Contractor. No  STARS Solution Deliverable shall be considered accepted unless the State has provided such formal written Acceptance.

The Contractor shall ensure that all Deliverables be of sufficient quality prior to submission to the State, e.g., that each Deliverable is comprehensive, meets all DED criteria, is logically organized, well formatted, is clearly communicated, and free of grammatical and spelling errors that detract from the Deliverable's readability and comprehension. In addition, the Contractor shall ensure that the submitted Deliverable be as close to a final version as possible and that it reflects any subject matter expert collaboration and draft review required prior to formal Deliverable submission.

The Contractor shall collaborate with the State in developing all draft Deliverable Expectations Documents (DED). The Contractor shall submit a DED to the State for each Deliverable due under the Contract according to the description of the system, related information in the Final Proposal (if any), and the State and Contractor discussions. The DED for each Deliverable is itself a Deliverable and is due for delivery to the State in accordance with the agreed-upon schedule. The Contractor shall gain the State’s Acceptance of the DED before starting work on the Deliverable described therein. For each DED, the Parties will agree on Acceptance Criteria based on the Specifications during the course of the Project.

The DED for each Deliverable will be drafted by the Contractor, according to the format described in the RFP ATTACHMENT 21: DELIVERABLE EXPECTATION DOCUMENT (DED). This process will establish requirements regarding the appropriate standards, format, content, number of copies, and Acceptance Criteria for the Deliverables.

The State will review and provide Acceptance or reject the draft DED within ten (10) State business days of receipt. If the DED does not receive Acceptance, the State will notify the Contractor in writing to communicate the State’s feedback about the continuous Deficiencies in the draft DEDs. While the State feedback may include suggested revisions to improve DED content, the State is not responsible for providing revised DED language when providing feedback about DED Deficiencies. If the DED does not receive Acceptance, the Contractor will revise the DED to address the State feedback concerning Deficiencies within five (5) State business days and resubmit the revised DED to the State for review and Acceptance or rejection. The State has up to five (5) State business days to review the resubmitted DED and give Acceptance or identify additional or continuing Deficiencies. If the resubmitted DED does not receive Acceptance, the State and the Contractor will repeat the actions (within the number of business days specified) described for a new draft DED during continuing DED review for up to three (3) iterations, or the deadline for receiving Acceptance is not met, as provided below. If the State does give Acceptance, the DED will serve as the Acceptance Criteria by which the State will formally give Acceptance or rejection for applicable Deliverables.

Please note SECTION 33 SERVICE LEVEL AGREEMENTS (SLAs) regarding the number of iterations allowed.

Following the established change control process, the Contractor may recommend changes to the DED after the State Acceptance, as warranted to improve the content and/or submission of a particular Deliverable subject to approval by the State. The State may also propose changes to the approved DED to improve its content relative to a particular Deliverable, subject to agreement by the Contractor.

Each DED will contain the following:

- An annotated outline of the Deliverable, table of contents, sample format and sample pages and general description of the information that will be contained in the Deliverable.

- Time frames for activities related to the Deliverable, including without limitation, dates for the Deliverable consistent with the State-approved Contractor’s Project Schedule,  STARS PMP and with this Agreement.

- Proposed State review timeframes for the Deliverable consistent with the State -approved Contractor’s Project Schedule,  STARS PMP and with this Agreement.

- Contractor correction time frames for the Deliverable.

- Deliverable objectives.

- Acceptance Criteria which are consistent with the Specifications and other requirements of this Agreement and prior Deliverables and communications between the Parties.

## DELIVERABLE REJECTION & ACCEPTANCE

All concluded work shall be submitted for review and acceptance or rejection to the State Contract Official through the use of Deliverable Acceptance Documents (DAD), shown in RFP ATTACHMENT 22: DELIVERABLE ACCEPTANCE DOCUMENT, to be signed by the Contractor.

The Contractor must be the sole entity submitting Deliverables to the State. The State will not accept Deliverables from subcontractors. The Contractor must review, verify compliance of, and accept full responsibility for any subcontractor Deliverables before submission to the State.

If deemed necessary by the State, a formal walkthrough session will be conducted to review the submitted Deliverables. This does not remove the walkthrough requirements already designated in this Agreement. The State will identify the reviewers that will attend these walkthrough sessions. The walkthrough sessions will be organized and scheduled by the Contractor, with approval from the State.

The State will use the signed DED to assess whether the Contractor has met the criteria for Deliverables Acceptance.

Should the work performed, and/or the Deliverables produced by the Contractor, fail to meet the State’s conditions, requirements, specifications, guidelines, or other applicable standards as identified in this Agreement, the following resolution process will be employed, except as superseded by other binding processes:

## GENERAL DELIVERY AND REVIEW PROCESS

The Contractor shall provide the State with the Deliverables on or before the applicable delivery dates in accordance with the agreed-upon schedule, as mutually agreed upon in writing and described in this Agreement. The Contractor and the State shall utilize the Specifications, the DEDs, the Contractor’s Proposal, the Deliverables for which the State has previously granted Acceptance, the Contractor’s professional knowledge, and this Agreement as the basis for establishing and mutually agreeing to the DED for a Deliverable.

Upon delivery of a Deliverable and receipt of the Deliverable Certification Cover Letter from the Contractor, the State will, with the Contractor’s assistance, perform compliance review on the Deliverable to determine whether the Deliverable conforms to its Acceptance Criteria.

The State review time for document Deliverables submitted for acceptance will be determined at the time the Deliverable DED is developed and will be based on the type and complexity of said Deliverables and the times included in the agreed-upon schedule. The State will require ten (10) State business days for review, comment and approval on a Deliverable unless otherwise agreed upon by the State in the agreed-upon schedule. Document Deliverables that are more complex and/or over 100 pages may, in the State’s discretion, require twenty (20) State business days. Changes to these review times shall be discussed during the DED review period and mutually agreed upon by both Parties.

The times for review and testing times assume that the State will not conduct a concurrent review or test of multiple Deliverables submitted for Acceptance. If multiple Deliverables must be reviewed or tested concurrently, review and testing times will depend on the nature and complexity of the Deliverables, the availability of State and Contractor resources, and the number of Deliverables concurrently being reviewed and tested. However, the State will require ten (10) State business days or twenty (20) State business days, depending upon Deliverable size and complexity.

If the State requires a period of time that exceeds the number of days specified for the Deliverable in the corresponding DED or that exceeds the number of days specified for review/test of Deliverables when no such DED specification is established to complete its review or testing, then, on the sixth (6th) business day following the expiration of the review/test time period, the State shall initiate the Change Control process to evaluate the schedule and/or cost impact (if any) to the STARS Project and the Contractor.

For those Deliverables submitted for Acceptance, the State shall notify the Contractor of Deliverable Deficiencies that the State requires the Contractor to remedy prior to Acceptance, and the Contractor shall correct the Software Deliverable Deficiencies within five (5) State business days of receiving notice from the State. The State may, at its discretion, allow a period longer than five (5) State business days in consideration of the scope of the change required to address the Deliverable Deficiencies. The following applies to any Deliverable Deficiencies identified by the State:

A. Reproducibility of Deliverable Deficiencies

Any Deliverable Deficiency detected and reported for a Software Deliverable. A reproducible Deficiency is one that can be predictably re-created and/or demonstrated by a tester, a STARS Solution system end-user, and/or an operator once the conditions required to create the Deficiency have been identified. The State may request the Contractor’s staff to assist the State STARS testing resources, end-user, or operations staff to identify the conditions required in order to reproduce the Deficiency.

B. Deliverable Deficiency Severity Levels

The State will assign a Deliverable Deficiency Severity Level to each Deficiency identified during review of a STARS Deliverable submitted for the State’s review and Acceptance. The Deliverable Deficiency Severity Level assigned to a Deliverable Deficiency will be tied to the Acceptance Criteria specified in the Deliverable’s corresponding DED; and will reflect the impact or significance of the Deficiency based on the acceptance Criterion or Criteria that the Deliverable fails to meet due to the Deficiency.

Each STARS Deliverable’s DED will define applicable Acceptance Criteria. Depending upon the nature of the Deliverable, Acceptance Criteria will designate the previously specified requirements, objectives, standards, consistency with previous Deliverables and other criteria that the State and the Contractor agree are appropriate to use in order to determine that the Deliverable under review is accurate, complete, and appropriate. The DED for a Deliverable may also designate acceptance Criteria that represent general Deliverable attributes that could be applicable to multiple STARS Deliverables (e.g., spelling, grammar, etc.).

After Contract Execution and prior to the Contractor delivering a DED for any STARS Deliverable, the State and the Contractor will mutually agree to a consistent set of Deliverable Deficiency Severity Levels and definitions based on Acceptance Criteria specified in DEDs.

C. Unresolved Deliverable Deficiencies in Accepted Deliverables

The State expects that each Deliverable submitted to the BOE STARS Project Sponsor or designee for review and Acceptance will be determined to be free of Deliverable Deficiencies as a condition of the State providing Acceptance of the Deliverable. However, the State recognizes that for a minimal number of STARS Deliverables, the State and the Contractor may mutually agree that the Deliverable may be eligible for the State Acceptance despite containing as yet unresolved Deliverable Deficiency (or Deficiencies), which is agreed to have a low impact on the quality, accuracy, and completeness of the Deliverable and any subsequent Deliverables.

D. Remedies for Uncorrected Deliverable Deficiencies

If the Contractor is unable to correct Deficiencies reported to the Contractor within sixty (60) calendar days from either submission of the Deliverable Certification Letter or the first resubmission of the corrected, accepted Deliverable, the State may, at its option: (i) continue reviewing or performing acceptance tests on the Deliverable and require the Contractor to continue until Deficiencies are corrected or eliminated; (ii) request the Contractor to provide, at its expense, a replacement Deliverable for further review or acceptance tests; or (iii) accept a reasonable adjustment in the cost of the applicable Deliverable in an amount to reflect a reduction in the value of the Deliverable as a result of the noted Deficiencies that have not been corrected and/or provide full or conditional Acceptance for the applicable Deliverable. If the State determines that none of the options or remedies described in this Section (above) is appropriate, the State may, within seven (7) calendar days of the State’s cure notice, pursuant to the INFORMATION TECHNOLOGY GENERAL PROVISIONS – CLOUD COMPUTING SERVICES DGS PD 402-ITGP CLOUD (REVISED 2/20/2025) SECTION 16.3 TERMINATION FOR DEFAULT (SEE LINK IN SECTION 36) terminate this Agreement in whole or in part after rejecting the Deliverable without penalty or liability to State, and return to the Contractor the rejected Deliverable as well as any Successor Deliverable(s) that is Dependent upon the rejected Deliverable.

Failure by the Contractor to respond to the State’s problem notification within the required time limits may constitute a material breach of the Agreement result in immediate termination of the Agreement. The State may, at its discretion and in writing, allow a longer period than the five (5) business days in consideration of the scope of the change.

The State will, within five (5) State business days after receipt of the Contractor’s detailed explanation or proposed corrective action plan, notify the Contractor in writing whether it accepts or rejects the explanation or correction action plan. If the State rejects the explanation or the corrective action plan, the Contractor must submit a revised corrective action plan within three (3) business days of notification of the rejection. Failure by the Contractor to respond to the State's notification of the rejection by submitting a revised corrective action plan within the required time limits may constitute a material breach of the Agreement, resulting in immediate termination of the Agreement.

The State will, within three (3) business days of receipt of the revised corrective action plan, notify the Contractor in writing whether it accepts or rejects the revised corrective action plan proposed by the Contractor. Rejection of the revised corrective action plan may constitute a material breach, resulting in immediate termination of the Agreement.

- Lack of response on the part of the State does not constitute Acceptance of any Deliverable.

- Signed acceptance of the DAD will be by the State Contract Official identified in 
SECTION 7. CONTRACT REPRESENTATIVES.

- The Contractor may not change a Deliverable that has been accepted by the State without the State’s written approval.

It shall be the State’s sole determination as to whether a Deliverable has been successfully completed in accordance with this Statement of Work.

# DATA HANDLING AND OWNERSHIP

The Contractor is responsible for all data conversion, data cleansing, data migration, and preparation for the STARS Solution use per the State data governance policies. Once all data is converted, cleansed, validated, and migrated, the State will maintain continuous inbound and outbound assessee data handling for tasks requiring manual intervention, while automated processes will continue to run after the STARS Solution has stabilized in production.

Figure 6: Data Handling Process Per Data Governance

  - Scope and timing for data conversion, data cleansing, data migration and/or data handling:

In accordance with the State data governance policies and business rules, the Contractor shall handle and administer the data migration from the IBM mainframe into the appropriate TSD data storage medium as illustrated in Figure 7. As part of this data migration, the sequence of data handling steps is a minimum. In addition to any data migration, there is existing data stored in the TSD storage infrastructure that needs to run through the data handling steps. The Project is open to any Contractor recommendations and changes to improve data quality and integrity.

Figure 7: Data Quantities and Migration Flow

State matrix of current and projected capacity and growth rate with respect to the data storage locations:

Table 6 State Storage Matrix with Storage Growth Estimates

| BOE Storage Matrix with Project Storage Growth Estimates (20%/Year) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Storage Device | 2025 | 2026 | 2027 | 2028 |  | “n” Year |  |
| BOX | 0 | 0 | 0 | 0 |  | 0 |  |
| Number of Files | 350,116 | 420,139 | 504,167 | 605,000 |  | (n -1) (Prior Year) x 1.20 |  |
| Storage Used (GB) | 538 | 645.60 | 774.70 | 929.70 |  | (n -1) (Prior Year) x 1.20 |  |
| Microsoft SharePoint |  |  |  |  |  |  |  |
| Number of Files | 48,654 | 58,385 | 70,062 | 84,074 |  | (n -1) (Prior Year) x 1.20 |  |
| Storage Used (GB) | 54.4 | 65.39 | 78.47 | 94.16 |  | (n -1) (Prior Year) x 1.20 |  |
| AWS/AZURE Network Storage | 0 | 0 | 0 | 0 |  | 0 |  |
| Number of Files | 7,091 | 8,509 | 10,211 | 12,253 |  | (n -1) (Prior Year) x 1.20 |  |
| Storage Used (GB) | 4.97 | 5.96 | 7.16 | 8.59 |  | (n -1) (Prior Year) x 1.20 |  |
| IBM Teale Data Center |  |  |  |  |  |  |  |
| Natural/ADABAS DB Storage for All 3 Databases Below: | 116 | 116 | 116 | Migrated OFF IBM |  |  |  |
| DB29 | 72 Files; 157K Records |  |  |  | 0 |  | 0 |
| DB19 | 73 Files; 123K Records |  |  |  | 0 |  | 0 |
| DB49 | 79 Files; 134K Records |  |  |  | 0 |  | 0 |

## DATA SOURCES, DATA ENTRY, AND HANDLING

The inbound data sources to the State tax and evaluation appraisal process primarily come from the following:

- Assessees, “A”, in the illustration below, utilizing various tax schedule forms containing their required tax data elements, are received via the State e-filing web portal, “B”, in the illustration below. The e-filing portal, upon receiving the tax schedule forms, would perform an e-file service to extract the necessary data elements from the tax schedule and store them in the assessee’s account database for tax or valuation computation.  However, there may be ad hoc communication between the assessee and the State that require data and file management, including paper mail, email, faxes, and Microsoft Teams voice mail messages.

- The State utilizes external data sources, “C”, in the illustration below, to assist in doing its business. The external data sources comprise the following via the World Wide Web:

  - RealQuest (Ad hoc Data Downloads for Comparable Land or Property Values)

  - Rail Inc.

  - ORER (Official Railway Equipment Register Book)

  - CHARM (Car Hire Accounting Rate Master)

- The State employee audit and appraisal work file could be in various forms of Microsoft Word Documents, Plain Text Files (Microsoft Notepad), Microsoft Excel Spreadsheets, and Microsoft Outlook emails for account archival uploads to the solution, with the key appraisal and/or audit data elements extracted and entered into the calculation algorithm for its valuation board roll computation.

- Secondary inbound data sources include the following:

  - Assessee Communication: Fax, Paper Letters, e-Mail, TEAMS voice mail messages, etc.

  - The State Employee Broadband File Uploads: Appraisal Pictures and/or Work Note Files.

Figure 8: State Data Management Plan and Flow

The Contractor will implement the data management plan illustrated in the diagram above, Figure 8, with the Deliverable 2.0 of designing and implementing an enterprise content management interface, “D”, in the illustration below, to the State centralized storage solution, “E”, the illustration below, of its respective elements including an SQL Database, BOX Storage, Microsoft SharePoint Site(s), and/or cloud network storage, all utilizing the State’s data governance policies. Additionally, it is expected that this Deliverable 2.0 will include prudently and cost-effectively managed data storage, recognizing that unstructured data will require a non-relational system rather than a relational one, and larger datasets will necessitate more computing power to manage, and sort compared to smaller ones.

## DATA ADMINISTRATION AND MANAGEMENT

All of the State’s inbound data is to be actively and continuously managed 24 hours a day, 7 days a week, and 365 days a year. In this active and continuous data management, all metadata policies related to extraction, as outlined in the State Data Governance Policies, must be administered before storing files and data in their designated storage device or medium. Additionally, in accordance with metadata administration, the data catalog must be updated appropriately if new data items emerge. Lastly, before final storage, the file or data element must be checked, validated, and cleansed as necessary to ensure its data quality.

## DATA SHARING, ACCESSIBILITY, AND ACCESSIBILITY PERFORMANCE

All data stored in the State centralized storage array of devices (“E”) will primarily be accessed by the STARS Solution as working data and the State employees (“F”), as illustrated above, with accessibility privileges determined by Managers, Supervisors, and the Data Owner, as per data governance policies. Additionally, as restricted by Managers and the data owner(s) according to data governance policies and business rules, certain documents and data elements are shared with the 58 counties of the State of California. This shared data with the respective 58 counties is done through a to-be-designed special login “side portal” (Requirement 3.10), which will be tracked, and all communications and data sharing will be recorded.

While there are many platform system variables, such as server hardware and configuration, CPU, RAM, disk I/O speed, and network infrastructure, Data Volume combined with query complexity, database design and indexing and further compounded with concurrency and workload with network traffic, the Project is open to the Contractor’s suggestions and recommendations to optimize this performance or better with cost.

## RELATIONAL DATABASE OR SQL QUERIES

The typical response time for an SQL query latency should be between 2 and 10 milliseconds, with a maximum latency of 50 milliseconds for “simple and easy” queries, such as single-table and single-value lookup.

## RANDOM UNSTRUCTURED DATA SEARCH

Typical latency response time should be between 10ms and 50ms, with a maximum latency response time of 100 milliseconds.

# SYSTEM REPORTING

The STARS Solution system shall meet all reporting requirements detailed in EXHIBIT C: FUNCTIONAL AND NON-FUNCTIONAL REQUIREMENTS. In addition, the STARS Solution shall report the following system reports:

- Assessee and State activity log to the STARS Solution

- County “side portal” activity journal log per county assessee with all communication and file uploads and downloads

- All State employee journal log per account

- STARS Solution user, performance, and system utilization metrics

The Contractor is responsible for meeting all mandatory requirements.

# SECURITY

## SECURITY AND DATA PROTECTION

The Contractor certifies to the State compliance with applicable industry standards and guidelines, including, but not limited to, relevant security provisions of the California State Administrative Manual (SAM), California Statewide Information Management Manual (SIMM), the National Institute of Standards and Technology (NIST) 800-53 v5 and the most current version at the time of Contract award, 800-171 Revision 2 (2023) and the most current version at the time of Contract award and Federal Information Processing Standard (FIPS) Publication 199 which protect and minimize risk to the State. At a minimum, provisions shall cover the following:

- The Contractor assumes responsibility for the confidentiality, integrity, and availability of the data under its control. The Contractor shall implement and maintain all appropriate administrative, physical, technical, and procedural safeguards at all times during the term of the Agreement to secure such data from data breach or loss, protect the data and information assets from breaches, introduction of viruses, disabling of devices, malware, and other forms of malicious or inadvertent acts that can disrupt the State’s access to its data or affects the integrity of that data.

- Confidential, sensitive, or personal information shall be encrypted in accordance with SAM § 5350.1 and SIMM § 5305-A.

- The Contractor shall comply with statewide policies and laws regarding the use and protection of information assets and data. The unauthorized use of data by Contractors or third parties is prohibited.

- The Contractor shall obtain and maintain a signed Security and Confidentiality Statement for all Staff assigned during the term of the Agreement.

- The Contractor shall apply security patches and upgrades and keep virus protection software up to date on all STARS Solution and Contractor-owned information assets on which data may be stored, processed, or transmitted.

- The Contractor shall follow secure coding practices consistent with industry accepted standards (e.g. OWASP Top 10, NIST 800-53).

- The Contractor shall notify the State immediately if a security incident involving the Contractor’s or the State’s information assets occurs.

- The State shall have the right to investigate a security incident involving its data and/or conduct its own independent investigation. The Contractor shall allow the State reasonable access to security logs, latency statistics, and other related security data that affect this Agreement and the State's data at no cost to the State.

- The Contractor shall be responsible for all costs incurred by the State due to security incidents resulting from the Contractor's failure to perform or negligent or intentional acts of its Staff resulting in unauthorized disclosure, release, access, review, destruction, loss, theft, or misuse of an information asset. If the Contractor experiences a data loss or breach, the Contractor shall immediately report the loss or breach to the State. If the State data owner determines that notice to the individuals whose data has been lost or breached is appropriate, the Contractor will bear any and all costs associated with the notice or any mitigation selected by the data owner. These costs include, but are not limited to, staff time, material costs, postage, media announcements, and other identifiable costs associated with the breach or loss of data. Costs are limited to the aggregate value of the Contract, in accordance with INFORMATION TECHNOLOGY GENERAL PROVISIONS – CLOUD COMPUTING SERVICES DGS PD 402-ITGP CLOUD (REVISED 2/20/2025), SECTION 21 DATA PROTECTION PROVISIONS (SEE LINK IN SECTION 36)The Contractor shall immediately notify and work cooperatively with the State data owner to respond timely and correctly to requests pursuant to Government Code §7920.0000, et seq. (i.e., the Public Records Act).

- The Contractor will dispose of records of State data as instructed by the State during the term of this Agreement. No data shall be copied, modified, destroyed, or deleted by the Contractor other than for normal operation or maintenance during the Agreement period without prior written notice to and written approval by the State.

- Remote access to data from outside the territorial United States, including remote access to data by authorized support staff in identified support centers, is prohibited unless approved in advance by the State.

- The physical location of the Contractor's data center where the Data is stored shall be within the territorial United States.

- The Contractor shall provide a written Security Attestation certifying that industry-standard security testing has been performed and that all critical, high, and medium vulnerabilities have been remediated prior to delivery of the STARS Solution and that any remaining findings are documented with risk ratings and remediation plans.

## PROTECTION OF CONFIDENTIALITY

Federal and State confidentiality laws, regulations, and administrative policies classify all the State information provided under this Agreement as confidential. The federal and State laws prohibit disclosure of the State's confidential information to the public and mandate its protection against loss and unauthorized access, use, disclosure, modification, or destruction. The Contractor and the State must, therefore, agree to the following security and confidentiality requirements identified in subsections below.

## ADMINISTRATIVE SAFEGUARDS

The Contractor shall:

- Adopt policies and procedures to ensure the use of the State’s confidential information solely for purposes specifically authorized under this Agreement that meet the requirements of Section §603.10, Title 20 of the Code of Federal Regulations.

- Warrant by execution of this Agreement that no person or State agency has been employed or retained to solicit or secure this Agreement upon any understanding or Contract for a commission, percentage, brokerage, or contingent fee. In the event of a breach or violation of this warranty, the State shall have the right to annul this Agreement without liability, in addition to other remedies provided by law.

- Warrant and certify that in the performance of this Agreement, the Contractor and the State will comply with all applicable statutes, rules and/or regulations, and Agreement information security requirements, including but not limited to the following:

- California Unemployment Insurance Code §1094 (Disclosure Prohibitions)

- Title 20, Code of Federal Regulations §603.9 and §603.10 (Federal Safeguards and Security Requirements)

- California Civil Code §1798, et seq. (Information Practices Act)

- California Penal Code §502 (Computer Fraud Act )

- California Revenue and Tax Code §19542, et seq. (Disclosure of Information)

- Title 5, U.S. Code §552a (Federal Privacy Act Disclosure Restrictions)

- Title 42, U.S. Code §503 (Social Security Act)

- Title 18, U.S. Code §1905 (Disclosure of Confidential Information)

- Be responsible for any loss, cost, damage or liability resulting from their own personnel’s violations of these applicable statutes, rules and/or regulations.

- Protect all working data and the State's information against unauthorized access at all times in all forms of media.

- Access and use the information obtained under this Agreement only to the extent necessary to assist in the valid administrative needs of the project receiving such information and only for the purposes defined in this Agreement.

- Keep all the Project working data and the State’s confidential information completely confidential.

- Make Project working data and the State's confidential information available to authorized personnel on a "need-to-know" basis and only for the purposes authorized under this Agreement. "Need-to-know" refers to those authorized personnel who need information to perform their official duties in connection with using the information authorized by this Agreement.

- Notify the State Information Security Officer (ISO) at (916) 309-1710 immediately upon discovery of a breach and possible breach in security that has or may have resulted in compromising confidential information. For purposes of this Section, "immediately" is defined as within 24 hours of discovery of the breach. The notification to the State’s ISO shall be by phone and email. It is not sufficient to simply leave a message. The notification must include a detailed description of the incident (such as time, date, location, and circumstances) and identify responsible personnel (name, title, and contact information). The verbal notification shall be followed with an email notification to InformationSecurity@BOE.ca.gov, David.Kelley@cdtfa.ca.gov, and ExecutiveOffice@boe.ca.gov.

## MANAGEMENT SAFEGUARDS

The Contractor acknowledges that the confidential information obtained from the State under this Agreement remains the property of the original owner, the State. Instruct all personnel assigned to work with the information provided under this Agreement regarding the following:

- Confidential nature of the State information pursuant to sections 7056, 7056.5, 9255, 30455, 32455, 38705, 43651, 45982, 46751, 55381, 60609 and 55381 of the Revenue and Taxation Code, section 15570.84 of the Government Code.

- Requirements of this Agreement.

- Sanctions and prohibitions specified in federal and State unemployment compensation laws, sections 7056.5, 9255, 30455, 32554, 38803, 43605, 45954, 46704, and 55364 of the Revenue and Taxation Code, section 15570.84 of the Government Code, and any other relevant statutes against unauthorized disclosure of confidential information provided by the State.

The Contractor shall require that all personnel assigned to work with the information provided by the State complete the RFP ATTACHMENT 6: Confidentiality. The State Contractor shall maintain a system of records sufficient to allow an audit of compliance with the requirements described under this Agreement. The Contractor shall permit the State to make on-site inspections to ensure that federal and State privacy and confidentiality requirements are being met.

## USAGE, DUPLICATION, AND REDISCLOSURE SAFEGUARDS

The Contractor shall use the State's confidential information only for purposes specifically authorized under this Agreement. Extraction or use of the State information outside the purposes stated in this Agreement is strictly prohibited. The information obtained under this Agreement shall not be reproduced, published, sold, or released in original or any other form not specifically authorized under this Agreement. Disclosure of any the State information to any person or entity not specifically authorized in this Agreement is strictly prohibited. Personnel assigned to work with the State's confidential information shall not reveal or divulge to any person or entity any of the confidential information provided under this Agreement except as authorized or required by law.

## PHYSICAL SAFEGUARDS

Notify the State ISO at (916) 309-1710 immediately upon discovery of a breach and/or possible breach in security that has or may have resulted in a compromise of confidential information. For purposes of this Section, "immediately" is defined as within 24 hours of discovery of the breach. The notification to the State's ISO shall be by phone and email. It is not sufficient to simply leave a message. The notification must include a detailed description of the incident (such as time, date, location, and circumstances) and identify responsible personnel (name, title and contact information). The verbal notification shall be followed with an email notification to InformationSecurity@boe.ca.gov and david.kelley@cdtfa.ca.gov.

The Contractor shall secure and maintain any computer systems (network, hardware, and software applications) used to perform this Agreement. The Contractor shall ensure that all security patches, upgrades, and antivirus updates are applied as appropriate to secure data that may be used, transmitted, or stored on such systems in the performance of this Agreement.

The Contractor shall employ the State's endpoint protection tools during the system's development and operation. The developed system shall exhibit full compatibility with these tools, ensuring seamless installation, conflict-free operation, and efficient communication for security monitoring and incident response. Any compatibility issues shall be rectified within 24 hours of discovery in order to uphold the State's security protocols.

The Contractor shall store all the State's confidential documents in a physically secure manner at all times to prevent unauthorized access.

The Contractor shall store the State's confidential electronic records in a secure central computer facility. Where the State's confidential electronic records are in use on a shared computer system and/or any shared data storage system, the Contractor shall ensure appropriate information security protections are in place. The State shall ensure that appropriate security access controls, storage protections, and use restrictions are in place to keep the confidential information in the strictest confidence and shall make the information available to its own personnel on a "need-to-know" basis only.

The Contractor shall store the State's confidential data in an encrypted format when recorded on removable electronic storage media or on mobile computing devices such as a laptop computer.

The Contractor shall maintain an audit trail and record data access of authorized users and authorization level of access to the State's data based on job function.

The Contractor shall direct all personnel permitted to use the State's data to avoid leaving the data displayed on their computer screens where unauthorized users may view it. Authorized personnel should retrieve computer printouts as soon as they are generated so that the State's data is not left unattended in printers where unauthorized personnel may access them.

The Contractor shall dispose of confidential information obtained from the State and any copies thereof made by the Contractor after the purpose for which the confidential information is disclosed is served. Disposal means return of the confidential information to the State or destruction of the information utilizing an approved method of confidential destruction, which includes electronic deletion, shredding, burning, or certified or witnessed destruction.

# DISASTER RECOVERY

The Contractor shall abide by provisions in SECTION 36 INFORMATION TECHNOLOGY GENERAL PROVISIONS – CLOUD COMPUTING SERVICES DGS PD 402-ITGP CLOUD (REVISED 2/20/2025)and EXHIBIT C: FUNCTIONAL AND NON-FUNCTIONAL REQUIREMENTS to ensure business continuity in the event of a disaster.

The Contractor must work with the State staff to ensure processes and systems are in place to ensure that data, application software, and configurations are backed up and can be restored in the event of a failure by Final State Acceptance. The Contractor must ensure these processes and systems are operating correctly by performing the following services:

- Verifying logs and backup outputs to detect deficiencies in the backup and restore processes to ensure that deficiency conditions are corrected.

- Verifying backup and recovery processes are complete and correct following software or configuration changes by conducting one exercise during the Warranty period.

- Backup and restore in the event of a failure must be conducted by the State with assistance as needed from the Contractor in the event of a disaster, with regular updates on its status, including contingencies.

- Complete one disaster recovery exercise with the relevant State staff members.

# DELIVERY (HARDWARE AND SOFTWARE)

The STARS Solution will use a cloud-based infrastructure, cloud-based version control software, and software subscriptions. There will not be any physical delivery requirements.

## HARDWARE AND SOFTWARE NEEDS

All the hardware and software components of the STARS Solution will be implemented within the State's cloud tenant. The State’s cloud tenant space provides all necessary infrastructure, including computing, network, database services, data storage, system configuration utilities, identity management, and monitoring tools, as well as a disaster recovery management tool. The State's cloud tenant space has secure connectivity to the existing State systems.

The State recognizes that the Contractor may have integrated third-party software within the STARS Solution. The Contractor will identify any proposed Third-Party software within their RFP response for the STARS Solution. Use of any third-party software requires written State approval. If a third-party software needs to have access to the State’s data, this shall require pre-approval by the State Information Security Division. The Contractor is responsible for all third-party software solution licenses and will assign them to the State during the initial purchase/designation of the licenses at no additional cost to the State.

### LICENSING

If the Contractor’s proposal for the STARS Solution uses licensing, the STARS Solution must leverage a role-based licensing model to account for the varied user roles anticipated within the Contractor’s Solution. User roles will be determined during the Requirements phase. Examples of the varied licensing desired are businesses and corporations to access the front-end modules and their account information, and internal and external staff users to access front and back-end modules, with varying access privileges.

The STARS Solution must leverage a capacity or subscription-based licensing model. The Contractor must provide the details on Licensing, Subscription and Third-Party Software / Tools as part of EXHIBIT E: COST WORKBOOK.

The Contractor shall bear the license cost for all application software, libraries, accelerants, third party applications and other STARS Solution components through end of the contract. At the start of Stage III: First Year Operations and Closeout, the Contractor shall work with the State on transfer of ownership and licenses to the State.

### SOLUTION VARIANCE

Any variance in the Contractor’s proposed Third-Party Software, not originally defined in the Contractor's RFP response, requires written pre-approval by the State STARS Contract Manager and the State STARS Project Manager. Use of any Third-Party Software requires written State approval. The Third-Party software must follow an approval-of-use process through the State Technology Services Branch.

- If a Third-Party Software has access or needs to have access to the State’s data, pre-approval is required by the State Information Security Division.

- All software solution licenses will be assigned to the State during the initial purchase/designation of the licenses at no additional cost to the State.

### INTERFACE REQUIREMENTS

The proposed STARS Solution will need to interface with all systems outlined in SECTION 24.3. COMPATIBILITY AND INTERFACE.

### SOFTWARE UPGRADES

Information regarding upgrades can be found in SECTION 24.5. TECHNOLOGY REFRESH.

### SOFTWARE MANUALS

The implementation of the proposed Solution must be accompanied by user manuals as outlined in SECTION 28. KNOWLEDGE TRANSFER AND/OR TRAINING. All subsequent software releases/upgrades must be accompanied by user manuals as outlined in SECTION 29. MAINTENANCE AND OPERATIONS (M&O). If the base of the proposed solution is used by multiple customers, the Contractor must create user manuals specific to the STARS Solution or provide specific user instructions for the STARS Solution within the general user manuals.

### SOFTWARE SUBSTITUTION

The Contractor may propose a software product substitution at no additional cost to the State if the substituted product meets or exceeds the requirements specified in EXHIBIT C: FUNCTIONAL AND NON-FUNCTIONAL REQUIREMENTS, identified in the SOW or attached thereto and incorporated in this Agreement. The Contractor must submit a written request, ninety (90) calendar days prior to the proposed substitution, to the State Contract Manager for State approval and acceptance. The written request must include the following information:

- The reason for the substitution.

- An analysis of how the substituted product will impact the STARS Solution.

- A specifications list of the original product and a specifications list for the replacement product.

- An analysis that shows the substituted product meets all the impacted requirements including performance standards of the original product.

## ESCROW SOURCE CODE

For the purposes of this section and for clarification, “source code, configurations, and customizations” developed by the Contractor as part of this Agreement shall be treated as “Software and other materials” as specified in INFORMATION TECHNOLOGY GENERAL PROVISIONS – CLOUD COMPUTING SERVICES DGS PD 402-ITGP CLOUD (REVISED 2/20/2025), SECTION 9 RIGHTS IN WORK PRODUCT & GOVERNMENT PURPOSE RIGHTS (SEE LINK IN SECTION 36) which is referenced in SECTION 2 PURPOSE.

The Contractor agrees to use a unified source code, configuration, and customization repository for all development of the STARS Solution and during deployment into other STARS environments, as determined by the State, and to keep the repository up to date with the latest STARS source code, configurations, and customizations.

Contractor agrees to save any and all source code, any and all configurations, any and all customizations of the STARS Solution software product(s) developed and/or used in the implementation, operation, and maintenance support with documentation of the STARS Solution into the repository.

The Contractor shall deliver to the State complete, human-readable source code with full comment lines, especially in those sections for tax computation and operational administration adjustments, build instructions, a Software Bill of Materials (SBOM) in a recognized standard format (e.g. SPDX, CycloneDX) and related documentation for all custom software developed under this Agreement.  The SBOM shall enumerate all open-source, third-party, and proprietary components and their versions. All such Deliverables shall be the property of the State, except for pre-existing components or third-party libraries, which must be clearly identified with licensing terms disclosed.

The Contractor agrees to save into repository all source code (which is Pre-Existing Material), configurations, and customizations, including but not limited to infrastructure, as code.

The State shall be entitled to receive a copy of such software source code, any and all configurations, any and all customizations saved into the repository in the event the Contractor has ceased all business activities or has filed for bankruptcy protection and/or if there is a material breach of the Agreement. The State has the right to audit the products kept in the repository during regular business hours upon sufficient notice to the Contractor.

The State reserves the right to host the source code in its own repositories and to subject it to independent security scanning. The Contractor shall cooperate with the State to address vulnerabilities identified through independent review.

## COMPATIBILITY AND INTERFACE

The STARS Solution must integrate and support data exchange via endpoints for internal and external to existing State systems utilized by State. The STARS Solution must also be compatible with Microsoft Office Suite, such as Microsoft Word, Excel, and data visualization/business intelligence Tools (e.g., Tableau, Power BI), as listed within EXHIBIT C: FUNCTIONAL AND NON-FUNCTIONAL REQUIREMENTS. In addition, the Contractor shall implement industry best-practice data exchange approaches to support all STARS Solution data exchange requirements. Refer to SECTION 20 DATA HANDLING AND OWNERSHIP for data conversion information. The Contractor shall provide documentation and integration support as defined in Stage 1 and Stage 2 and EXHIBIT D: DELIVERABLES AND MILESTONES TABLE.

The STARS Solution will leverage REST API's to ensure the various applicable State software components and data sources can interact in a simple, standardized way over HTTPS protocols.

The STARS Solution should support the system interfaces defined in SECTION 23.3 COMPATIBILITY AND INTERFACE and Deliverable 1.6 SYSTEM CONFIGURATION MANAGEMENT PLAN AND Deliverable 1.7 STARS SOLUTION IMPLEMENTATION PLAN as it is intended to possibly connect to multiple State applications, databases, and external APIs in a decoupled architectural way. Accurate account data must be shared with county agencies per the secured data sharing requirements via the to be designed “county side portal’ EXHIBIT C: FUNCTIONAL AND NON-FUNCTIONAL REQUIREMENTS: requirement 3.10. The system and data architecture must be designed to accommodate future changes in policy and/or regulation of property assessments and taxation of such properties including computations and exclusions.

### INTERFACES

The STARS Solution is intended to connect multiple services (such as client applications, databases, and external APIs) in a to-be-determined decoupled architecture. The STARS Solution shall support the system interface defined in Section 20 and respective Figure 10, item “C” and Deliverable 1.6 SYSTEM CONFIGURATION MANAGEMENT PLAN AND Deliverable 1.7 STARS SOLUTION IMPLEMENTATION PLAN INTERFACE CONTROL DOCUMENT.

The Contractor will clearly define all interfaces required for the integration of the STARS Solution. This includes but is not limited to:

- Application Programming Interfaces (APIs): The Contractor must design and document all RESTful APIs, ensuring they comply with modern standards for security (e.g., OAuth, JWT), error handling, and data formats (e.g., JSON, XML).

- User Interfaces (UIs): The Contractor will specify the user interfaces (web, mobile, or desktop applications) that will interact with the backend system, including how the frontend systems will communicate with the APIs.

- Database Interfaces: Any interface between the STARS Solution and legacy or third-party databases must be clearly defined. This includes schemas, data mapping, and access protocols.

- Hardware Interfaces: The Contractor must define how the STARS Solution will interface with any hardware devices (e.g., printers, barcode scanners, IoT devices) or external systems, including necessary protocols and communication standards.

- File Import/Export Interfaces: If the STARS Solution requires importing or exporting data in bulk, the Contractor must define interfaces for handling file-based data exchange (e.g., CSV, Excel, XML, etc.).

The Contractor shall collaborate with the State and any State Third-Party Contractors to analyze interface requirements and determine the best approach for interfacing between the STARS Solution and Third-Party systems.

The Contractor shall have system integration responsibility for the STARS Solution, and in this role shall analyze and determine the resolution of any problems involving all system interfaces.

The Contractor is responsible for the design, integration, system modification, and delivery to make certain that integration requirements are met.

The interface specifications must include the minimum requirements listed below:

- Third-party Contractor name

- Contact information

- Release history/status

- Support availability

- Interface name (technical and business name)

- Description

- Associated business process

- Business purpose

- Incoming/outgoing or real-time Application Programming Interface (API) (data flow)

- Target audience and security roles

- Detailed functional description

- Assumptions

- File layout with data elements including type, lengths, and valid values (if applicable)

- Frequency/timing

- Transfer method/process

- Dependencies/prerequisites

- Required configuration

- Troubleshooting/error handling

- Data reconciliation process

- External system considerations

- Future/retro transactions allowed

- Resource names

- Estimated data volume

## SYSTEM INSTALLATION

The Contractor shall perform all system installation and configuration tasks on the Cloud hosting solution provider. This includes meeting the system installation prerequisites, system installation processes, timelines, and resources to be used for setting up the State required environments for the STARS Solution. See SECTION 9. State DATA CENTER OR CONTRACTOR HOSTED FACILITY ENVIRONMENT and EXHIBIT C: FUNCTIONAL AND NON-FUNCTIONAL REQUIREMENTS.

### SYSTEM IMPLEMENTATION OR INTEGRATION

The Contractor will implement the STARS Solution that provides all mandatory functionality specified in EXHIBIT C: FUNCTIONAL AND NON-FUNCTIONAL REQUIREMENTS in accordance with all applicable federal and State laws, and the State-specified business rules.

A pilot will be conducted with key taxpayers and private car railroad taxpayers and a second pilot with a few select counties to test their “side portal” (see Figure 9: State system pilot).

The pilot shall start once the key module sections outlined with the red dashed box in Figure 9 “State System Pilot” below are in solid working order. The pilot participants, including select SAPD and PRC assessees, select county officials, and the State employees, will test these modules and provide feedback to the Contractor regarding issues, user experience, and enhancements to fix and implement. The Contractor will create a separate “Pilot” version of the system to accommodate, administer, and facilitate the pilot testing with prepopulated data as needed.

Figure 9 State System for Pilot

### SYSTEM ROLL OUT TIMELINE

The Contractor shall complete System roll out to the State assessees no later than 
April 30, 2028.

The State will provide a communications plan regarding the new the State tax filing system to all the State Assessed Properties and Private Rail Car assessees before the “go live” date of April 30, 2028, for assessees to set up their accounts on the e-File website and learn the new system. Advanced communication materials will include:

- Preview of the new pending tool in the State newsletter

- Information on the new tool on the State main website

- Introduction Announcement Letter of the pending new system

- The State press release and press release kit

- A one page “Info-gram” of the new system

- Training guidebook to use the system

- Quick reference card of key usages

The State will provide a separate State communications plan for California’s 58 counties regarding the special “side portal” for the respective counties to upload and download relevant tax data for the county auditors and appraisers for county tax purposes.

## TECHNOLOGY REFRESH

The Contractor shall provide access to any software updates utilized to fulfill the requirements, tasks, and Deliverables of this Agreement. The software updates shall be made available free of charge and include any relevant software release notes. The State shall receive notification at least thirty (30) calendar days in advance of any planned software release. Failure to notify the State in advance of any planned software release may result in system downtime or defects associated with functionality. Any system downtime or defects resulting from failure to notify the State prior to a planned software release shall be subject to the Service Level Agreement timelines documented in SECTION 33. SERVICE LEVEL AGREEMENTS (SLAs).

The Contractor shall update the software components through the length of the Agreement at no cost to the State to stay in compliance with the security requirements as specified in SECTION 22. SECURITY and supporting typical refresh needs, such as but not limited to:

- Need to improve performance

- Incompatibility with new software

- System OS patches and migrations

- Driver Updates

In addition, the Contractor shall comply with requirements in SECTION 36 INFORMATION TECHNOLOGY GENERAL PROVISIONS – CLOUD COMPUTING SERVICES DGS PD 402-ITGP CLOUD (REVISED 2/20/2025) regarding technology refresh.

# SYSTEM TESTING AND ACCEPTANCE PROCEDURES

The Contractor is responsible for conducting and managing STARS system integration testing, penetration testing, performance testing, load and performance testing, security testing, interface testing, user acceptance testing, accessibility testing, and final test plan. The STARS Solution must meet and pass system, user acceptance, regression, and performance testing.

The Contractor is responsible for, executing various levels of system integration testing, and identifying and resolving defects to deliver a high-quality Solution. The system integration testing procedures will support system functionality validation, data quality validation and reporting, and system performance verification. The following outlines the System integration Testing and Acceptance Procedure requirements and Deliverables:

The Contractor shall conduct necessary STARS testing during the iterative development cycles to ensure the System aligns with the planned System design and meets the requirements defined in EXHIBIT C: FUNCTIONAL AND NON-FUNCTIONAL REQUIREMENTS prior to delivering completed capabilities for the State’s review and Acceptance. The Contractor’s testing approach shall include, but not be limited to, the following:

- Execute testing during unit/module and interface development to confirm functional compliance with the STARS Solution requirements.

- Execute System Integration Testing to test module interactions and end-to-end functionality against the requirements and ensure calculations, interfaces, data exchange accuracy, including integration with required State internal and external systems and data sources.

- Support and manage the STARS Solution capability validation and acceptance with the State, including demonstrating and testing the capability functionality.

- Support and manage the Implementation Stage UAT process, including tracking State reported defects, triaging defects, remediating and redeploying resolved defects for retesting, supporting and assisting in creating test data and test scripts, conducting daily UAT check-in meetings during the UAT cycle, and communicating and coordinating UAT deployment with State UAT resources.

- Support and manage parallel testing, when required, in the pre-production environment to validate reported incidents, validate resolved incidents, performance testing, and verify new the STARS Solution processes against the STARS Solution and processes.

- Test STARS Solutions’ performance under maximum operational load conditions, anticipating the volume of users and reports.

- Test to ensure the STARS Solution responds to user input within specified timeframes under expected workloads.

- Storage times that are within the manufacturer’s specifications and deliverables of the SOW.

- Database search and retrieval times that are within the specifications and deliverables of the SOW.

- Test to ensure the STARS Solution completes after-hours and 24/7 processing during allotted timeframes under expected workloads as defined in EXHIBIT C: FUNCTIONAL AND NON-FUNCTIONAL REQUIREMENTS.

- Execute penetration and security testing as defined in EXHIBIT C: FUNCTIONAL AND NON-FUNCTIONAL REQUIREMENTS. Security testing will include, but is not limited to the following:

  - Perform a software security review and system security scan, as required, to verify the STARS Solution compliance with the identified State security requirements and standards.

  - Coordinate with the State to test user permissions and access.

  - Correct any security flaws, anomalies, and defects identified during regular security tests during the Contract term, unless the State provides an explicit written waiver for a given flaw, anomaly, or defect.

  - Conduct quarterly and on-request security tests.

- Conduct business continuity and technology recovery testing prior to Implementation Stage deployments to production in the pre-production environment and quarterly after Final System Acceptance. Document the execution procedures and activities and ensure the STARS Solution meets the requirements of Disaster Recovery per EXHIBIT C: FUNCTIONAL AND NON-FUNCTIONAL REQUIREMENTS, and SECTION 23: DISASTER RECOVERY.

- Prepare test scenarios and test cases that comply with the DEL 1.9 Test Plan for all phases of testing. The Contractor may utilize automated test scripts, with prior approval by the State Project Manager. The Contractor will update test scenarios, cases, and scripts, as appropriate, when changes are made to the STARS Solution.

- Document, manage, and resolve all defects identified at any stage of testing.

The Contractor shall not use current year production data in any non-production environment or during development and testing. The Contractor shall enter and track defects found during all phases of Development Operational (DevOps) testing. The Contractor shall categorize defects by severity. During User Acceptance Testing associated with the Implementation Stage or Final System Acceptance validation, the Contractor shall categorize the STARS Solution defects as outlined in the Acceptance Test Defect Exit Criteria below.

## ACCEPTANCE TEST DEFECT EXIT

Table 7 Acceptance Test Defect Exit Criteria describes the rubric applicable to the severity level of the test defect.

Table 7 Acceptance Test Defect Exit Criteria

| Severity Level | Descriptions | Acceptance / Testing Exit Criteria |
| --- | --- | --- |
| Severity 1 - Critical | Defect stops all business processes of the system. (e.g. users cannot log into the system). | No Severity 1 defects/issues. |
| Severity 2 - High | Defects affect all business processes within a functional area. (e.g. cannot submit facility data). | No Severity 2 defects/issues. |
| Severity 3 - Medium | Defects affect some business processes, but a majority of business processes can be performed within a functional area. | No more than three open Severity 3 defects/issues remain. The remaining Severity 3 defects/issue disposition and resolution timeline must be agreed upon by the State. |
| Severity 4 - Low | No impact on business processes, however, may discourage use or present confusing user experience. | Open Severity 4 defects/issues have been prioritized and scheduled for a future release as agreed upon by the State. |

All critical-severity level defects must be resolved by the Contractor and Accepted by the State before the go-live of each the STARS Solution production release.

Test results for all phases of testing will be reported by the Contractor Project Manager during daily and weekly Project status meetings. Test results shall be presented using the State’s DevOps, documented, and submitted in Microsoft Office format (Microsoft Word or Microsoft Excel).

The Parties shall schedule modifications based on test results within the agreed-upon timeframe. Issues arising from testing shall follow the escalation procedure identified in SECTION 13. ESCALATION PROCESS.

Refer to EXHIBIT D: DELIVERABLES AND MILESTONES TABLE; DEL2.13  SYSTEM PERFORMANCE FUNCTIONALITY TEST AND DEL2.14 SOLUTION TEST.

These include the following:

- Final Test Plan (for each release)

- Consolidated Master Test Scripts and Scenarios (for each release)

- System Test Results Report (for each release)

- Integration Test Results Report (for each release)

- Load and Performance Test Results Report (for each release)

- User Acceptance Test Results Report (for each release)

- Accessibility Test Results Report (for each release)

- Security Test Results Report (for each release)

# FINAL STATE ACCEPTANCE

The State will require an "Acceptance Period". The "Acceptance Period" must include sixty (60) consecutive calendar days for production validation. During the Acceptance Period, the Contractor is responsible for maintaining and supporting the STARS Solution and monitoring functionality against State-approved metrics that confirm the Solution stage has met the Project requirements. Service-level agreements will apply upon go-live of each release. Refer to SECTION 33. Service Level Agreements (SLAs) for details.

At the end of the Acceptance Period, the Contractor will receive Stage or Phase Acceptance Certification from the State upon completion of the following criteria:

- Load Results Reporting (Production)

- All State user accounts are set up for use

- All State SAPD and PRC Assessee historical and current tax year data loaded into and for the STARS Solution to access

- Deployment Assessment Report

- Key software modules have the required code commenting for key sections of the program code has been completed per deliverables and requirements

- All software has been validated to contain no embedded unauthorized/hidden BOTs

- Penetration testing (pen testing) is completed with a simulated cyberattack on the STARS Solution computer system, network, and associated applications by a 3rd party, and all issues are resolved.

- All project risk log items resolved to the State’s satisfaction and approval

- Updated Project and Operations Plans, Configuration Documentation, Disaster Recovery Plans, and Artifacts

- The Contractor has met all Performance and Availability SLAs defined in SECTION 33. Service Level Agreements (SLAs) that apply during the Acceptance Period.

- The Solution is deemed stable for the full Acceptance Period. Stability is achieved when the Solution operates for forty-five (45) calendar days while meeting both of the following criteria:

  - No Severity Level 1 or 2 defects during the Acceptance Period and

  - Five (5) or fewer Severity Level 3 defects persist.

The State will follow the staged approach outlined above. Refer to RFP ATTACHMENT 21: DELIVERABLE EXPECTATION DOCUMENT(S) submission and Acceptance/rejection of Deliverables for the Deliverable Acceptance procedures.

# TRANSITION OF OPERATION TO STATE

During the term of the Agreement, the Contractor shall provide the State with Solution transition services and software licenses. The State shall provide Contractor thirty (30) calendar days’ written notice for the Contractor to begin executing a 'Transition Period' that will be ninety (90) calendar days prior to the State’s Final Acceptance Date, in accordance with INFORMATION TECHNOLOGY GENERAL PROVISIONS – CLOUD COMPUTING SERVICES DGS PD 402-ITGP CLOUD (REVISED 2/20/2025)SECTION 21.12 TRANSITION PERIOD (SEE LINK IN SECTION 36).

# KNOWLEDGE TRANSFER AND/OR TRAINING

The Contractor shall provide technical STARS Solution instruction and guidance (Job Shadowing) to the State Staff, provide a continuous transfer of STARS Solution configuration and maintenance knowledge, and complete the knowledge transfer and/or training activities specified as specified below and in the DEL1.10 STARS Training Plan and DEL2.12 DEVELOP STARS SOLUTION TRAINING MATERIALS.

The Contractor shall provide a fully functional STARS Solution Training environment that is separate from the STARS Solution Development, Test, and Production environments. (This Training environment shall have been described in Contractor’s DEL2.1 – SYSTEM Technical Architecture(STA).

## Technical STARS Solution Training, Instruction, and Guidance

The Contractor will provide resources for technical instruction and knowledge transfer to various Operational areas within the State organization (e.g., CDTFA Technology Services Division). This instruction must include how to configure and properly add and maintain various system fields, lists, and table content, functions, or components to accommodate business processing rules, workflow, notices/forms, reports, analytics, and other operational resource functions. See EXHIBIT C: FUNCTIONAL AND NON-FUNCTIONAL REQUIREMENTS (10.03).

## Train-the-Trainer

The Contractor will provide all end user training materials and will instruct the State Training staff (Train-the-Trainer) to provide training needed. The Contractor’s instruction will consist of defining categories of training (e.g., Admin, end user, technical, UAT, etc.), defining timeline for training based upon recommended length of each training class, development and loading of training materials into the State ’s training tools, providing written user manuals, training guidelines and desk aids, along with Maintenance & Operation manuals (both in soft and hard copies).

The Contractor will support various methods of training (classroom, web-based, computer-based, one-on-one, train-the-trainer, etc.) and in-person training at State Headquarters, 160 Promenade Circle, Sacramento, CA 95834.

The Contractor will ensure training content incorporates the latest version of the STARS Solution being provided to the State. If a system upgrade is provided by the Contractor, training materials will be provided to the State for instruction of the latest features.

The Contractor will define the timing of each training with the State, based upon the recommended implementation timeline and approved Training Plan.

The Contractor shall provide input to the State and the State designated Organization Change Management Lead on Organization Change Management and business process re-engineering and business process training.

The Contractor shall coordinate with State on developing an integrated training approach to include the Contractor’s System Training to all stakeholders and knowledge transfer.

# MAINTENANCE AND OPERATIONS (M&O)

If the State exercises this option, Maintenance and Operations (M&O) will commence upon final State Acceptance of the STARS Solution.

M&O services and associated costs throughout the life of the Agreement include:

- STARS Solution updates.

- Resolving STARS Solution-related problems and deficiencies.

- Solution changes to improve efficiencies.

- Break-fix, upgrades, and patches; and,

- If required, perform unanticipated tasks per SECTION 35: UNANTICIPATED TASKS.

Additionally, if during the M&O period, a hypercare event occurs, the hypercare action list in the SECTION 39: HYPER CARE ACTION LIST must be enacted and adhered to for 60 days.

Release notes describing each upgrade must be provided along with documentation for the appropriate user manuals and training materials. The system updates and/or software releases must follow State’s change management and release procedures.

The Contractor shall perform the following:

- Provide M&O services necessary to ensure the continuing operation of each Release into Production according to EXHIBIT C: FUNCTIONAL AND NON-FUNCTIONAL REQUIREMENTS and in accordance with the Service Level Agreements specified in SECTION 33 SERVICE LEVEL AGREEMENTS (SLAs).

- Ensure the STARS Solution components in this Agreement are operational (functioning and/or available for use), as described in SECTION 33 SERVICE LEVEL AGREEMENTS (SLAs)

- Follow all protocols and procedures established and used during Production implementation (i.e., version control processes, testing procedures, issue resolution, etc.).

- Be responsible for compliance with the Service Level Agreements, as specified in SECTION 33 SERVICE LEVEL AGREEMENTS (SLAs), throughout the term of the Agreement.

- Be responsible for software/application updates and maintain cloud environment updates, such as patches, fixes, rolling releases (if applicable) as required.

- Provide M&O service reports.

# HELP DESK

In alignment with the Deliverables described in the base Contract Agreement, the Contractor will provide second-level (Tier 2) support (see DEL3.1.1) and help desk resources. The Contractor will also provide shadowing and knowledge transfer on how to support all the STARS Solution features released into the production environment as specified in SECTION 18.11. STAGE III: PROJECT CLOSE OUT AND WARRANTY PERIOD.

# INSURANCE REQUIREMENTS

- The Contractor shall deliver applicable Insurance certificate(s) to CDFTA at the following address:

Attn: Contract Services

California Department of Tax and Fee Administration

651 Bannon Street, Suite 100, Sacramento, CA 95811

- Contractor agrees that the insurance requirements herein provided for shall be in effect at all times during the term of this Agreement. The Contractor shall provide evidence of insurance within ten (10) calendar days of Contract award. ).

- General provisions applying to all policies:

  - Contractor agrees the insurance herein provided for shall be in effect at all times during the term of this Agreement. In the event said insurance coverage expires at any time during the term of this Agreement, Contractor agrees to provide at least thirty (30) days prior to said expiration date, a new certificate of insurance evidencing insurance coverage as outlined below for not less than the remainder of the term of this Agreement, or for a period of not less than one year. New certificates of insurance are subject to the approval of the DGS-ORIM and Contractor agrees that no work or services shall be performed prior to the giving of such approval. In the event Contractor fails to keep in effect at all times insurance coverage as herein provided, the State may, in addition to any other remedies it may have, terminate this Agreement upon the occurrence of such event. The Contractor shall provide written notice to the State within five (5) business days of any cancellation, non-renewal, or material change that affects required insurance coverage.

  - Deductible: Contractor is responsible for any deductible or self-insured retention contained within their insurance program.

  - Primary Clause: Any required insurance contained in this Agreement shall be primary, and not excess or contributory, to any other insurance carried by the State.

  - Insurance Carrier Required Rating: All insurance companies shall carry a rating acceptable to the DGS-ORIM. If the Contractor is self-insured for a portion or all of its insurance, review of financial information including a letter of credit may be required.

  - Endorsements: Any required endorsements requested by the State shall be physically attached to all requested certificates of insurance and not substituted by referring to such coverage on the certificate of insurance.

  - Inadequate Insurance: Inadequate or lack of insurance does not negate the Contractor’s obligations under the Contract.

  - Subcontractors: In the case of Contractor’s utilization of subcontractors to complete the contracted scope of work, Contractor shall include all subcontractors as insured under Contractor’s insurance or supply evidence of insurance to the State equal to policies, coverages, and limits required of Contractor.

- Insurance Requirements

  - Commercial General Liability: The Contractor shall furnish to the State a certificate of insurance stating that commercial general liability insurance with limits of not less than $1,000,000 per occurrence for bodily injury and property damage liability combined. The policy shall include coverage for liabilities arising out of premises, operations, independent Contractors, products, completed operations, personal and advertising injury, and liability assumed under an insured Contract.

  - Automobile Liability: Contractor shall maintain business automobile liability insurance for limits not less than $1,000,000 combined single limit. Such insurance shall cover liability arising out of a motor vehicle including owned, hired and non-owned motor vehicles. The policy must name the State, State of California, its officers, agents, employees and servants are included as additional insureds, but only with respect to work performed under this Agreement. Auto Liability: By signing this Agreement, the Contractor certifies that the Contractor and any employees, subcontractors or servants possess valid automobile coverage in accordance with California Vehicle Code Sections 16450 to 16457, inclusive. The State reserves the right to request proof at any time.

  - Cyber Liability: The Contractor shall furnish to the State a certificate of insurance stating cyber liability insurance with limits of not less than $5,000,000. The policy shall include coverage for claims involving notification costs, privacy violations, information theft, damage to or destruction of electronic information, intentional and/or unintentional release of private information, and alteration of electronic information, extortion, and network security.

  - Technology Professional Liability / Error and Omissions Insurance: The Contractor shall furnish to the State a certificate of insurance to the Contractor’s profession and work hereunder, with limits not less than $5,000,000 per occurrence. Coverage shall be sufficiently broad to respond to the duties and obligations as is undertaken by the Contractor in this Agreement and shall include, but not be limited to, claims involving infringement of intellectual property, copyright, trademark, invasion of privacy violations, information theft, release of private information, extortion and network security. The policy shall provide coverage for breach response costs as well as regulatory fines and penalties as well as credit monitoring expenses with limits sufficient to respond to these obligations.

- The Policy shall include or be endorsed to include property damage liability coverage for damage to, alteration of, loss of, or destruction of electronic data and/or information “property” of the State in the care, custody, or control of the Contractor. If not covered under the Contractor’s liability policy, such “property” coverage of the State may be endorsed onto the Contractor’s Cyber Liability Policy as covered property as follows: Cyber Liability coverage in an amount sufficient to cover the full replacement value of damage to, alteration of, loss of, or destruction of electronic data and/or information “property” of the State that will be in the care, custody, or control of Contractor, including, but not limited to, losses caused by employees or subcontractors of Contractor, and cost to restore the data and/or information, as determined by the State.

- If the policies provide claims-made coverage, the following additional terms shall apply:

  - The Retroactive Date must be shown and must be before the date of the Contractor the beginning of Contract work, whichever occurs first.

  - Insurance must be maintained, and evidence of insurance must be provided for at least five (5) years after completion of the Contract of work.

  - If coverage is canceled or non-renewed and not replaced with another claims-made policy form with a Retroactive Date prior to the Contract effective date, the Contractor must purchase “extended reporting” coverage for a minimum of five (5) years after completion of work.

    - The above types of insurance shall apply separately to each insured against whom claim is made or suit is brought subject to the Contractor’s limit of liability. The policy for each type of insurance shall include the following endorsement: the State, State of California, its officers, agents, employees and servants are included as additional insureds, but only with respect to work performed under this Agreement.

    - The State will not be responsible for any premiums or assessment on the insurance policy.

    - Workers’ Compensation: The Contractor shall maintain Workers' Compensation insurance as required by the State of California, with Statutory Limits, and Employer's Liability Insurance with limit of no less than $1,000,000 per accident for bodily injury or disease. Policy shall be endorsed to include a waiver of subrogation in favor of State of California. The Contractor agrees to furnish the State satisfactory evidence thereof at any time the State may so request.

# WARRANTY

The Warranty Period shall commence upon SECTION 26: FINAL STATE ACCEPTANCE as defined in SECTION 11. CONTRACTOR ROLES AND RESPONSIBILITIES and in accordance with INFORMATION TECHNOLOGY GENERAL PROVISIONS – CLOUD COMPUTING SERVICES DGS PD 402-ITGP CLOUD (REVISED 2/20/2025), SECTION 8 WARRANTIES AND REPRESENTATION (SEE LINK IN SECTION 36).

The Contractor shall provide a twelve (12) month warranty period commencing immediately after Final State Acceptance (SECTION 26: Final State Acceptance and the State Implementation and Go Live). During the twelve (12) month warranty period, at the release of the STARS Solution “go live” date or a major code release event, the contractor shall enable, execute, and support SECTION 39 : HYPER CARE ACTION LIST items for period of 60 (sixty) days.

# SERVICE LEVEL AGREEMENTS (SLAs)

This section describes the SLAs the Contractor shall meet for the life of the contract. SLAs and liquidated damages will be assessed on a monthly basis. If imposed, Liquidated Damages will not exceed ten percent (10%) of the total Agreement award price for the STARS Solution. A workaround is a temporary fix to either a Hardware or Software failure such that core business functionality is restored and there are no significant impacts that prevent the business from operating as intended. All workarounds must be approved by the State, in writing, prior to implementation.

The State and Contractor will decide on a triage process during the Project's implementation.

Table 8 Service Level Agreements and Liquidated Damages

| SLA Category/ SLA Title | Performance Description (SLA Performance Standard) | Performance Target (Expected SLA) | Liquidated Damages |
| --- | --- | --- | --- |
| Key Staff Replacement | Key Staff must be replaced within the time frame and in accordance with the process outlined in SECTION 12 KEY STAFF CHANGES. The start date of the measurement begins on the date the Contractor provides notification of any proposed changes, or on the date the State requests the Contractor to replace key staff plus the number of days as defined in SECTION 13 KEY STAFF CHANGES. Key staff positions must not be filled by state employees to fulfill the roles and responsibilities of the position in a temporary capacity and/or maintain responsibility for a Contractor's key staff position. The State shall report delays in the key staff fulfillment to the Contractor’s Project Manager. | Daily, for each Key Staff position that has not been filled within the number of days required. | $2,500 per State business day, or portion thereof, for each calendar day over twenty (20) that a new candidate has not been provided following a State request for Key Staff change |
| Project Management/ Scheduled Deliverable | To avoid costly delays, all Deliverables must be approved according to mutually approved dates or according to the Project schedule. | 100% of all Deliverables are approved on schedule or by mutually approved dates. | $1,000 per working day per schedule or mutually approved dates not to exceed $120,000 per year |
| Project Management/ Deliverable Quality | The Deliverables submitted to the State by the Contractor will conform to the approved Deliverable Expectations Document (DED). The Deliverables should be to a quality standard that allows for one State review, two updates and approval, unless there is a change requested by the State. | 100% approved within three (3) review cycles of the approved associated DED | $1,000 per working day of the Deliverable that does not conform to the approved associated DED, not to exceed $120,000 per year |
| STARS Solution SLA/Defect Management - Root Cause Analysis (RCA) Submission | The Contractor shall submit to the BOE STARS Project Sponsor, or designee, as defined in the Project Management Plan, an initial Root Cause Analysis (RCA) document for every Severity Level 1 and Severity Level 2 deficiency, within 24 hours of identification. The initial RCA document shall provide, as it is understood at the time of submission, the deficiency identification time and date, an estimate of solution and user impacts, an estimate of the duration, actions taken and planned, and a timeline for submission of a completed RCA. | The Contractor shall submit an initial root cause analysis to the State within 24 hours of identification. The Contractor shall submit the complete analysis within ten (10) business days of the identification of the issue. | $1,000 per each late submission. |
| STARS Solution SLA/Defect Management — Solution Deficiency Correction | The Contractor shall maintain the Production Warranty Deficiencies by Severity below the thresholds identified in the Minimum and Expected Service Level Agreements. Solely for the purposes of this Section, Solution Deficiency Correction, the term “Production Warranty Deficiencies” means Deficiencies in the STARS Solution (identified in either the production environment, solution test or another higher environment) that are identified by the State as an Incident during the applicable Warranty Period under the Agreement. The Contractor and the State shall work to mutually prioritize and schedule Production Warranty Deficiencies. Deficiency Severity Levels are defined as: Severity Level 1 Production Warranty Deficiency: - Renders the STARS Solution is totally inoperable, or there is a critical the STARS Solution outage, or - Degrades performance such that the STARS Solution is effectively unavailable. Examples include but are not limited to, the user cannot log into the STARS Solution, or the Tester is unable to access the test environment. Severity Level 2 Production Warranty Deficiency: - Results in critical functions, components, or features being down or unusable or - Prevents the accomplishment of a critical function where there is no alternate procedure by which the function can be performed. Examples include but are not limited to: the STARS Solution errors preventing users from completing critical functions, and/or causing data corruption. Critical functions are limited to the following, where at least 50% of the STARS Solution total users and/or associated transactions are unable to process to successful completion. Severity Level 3 Production Warranty Deficiency: A component, application or procedure is difficult to use, causing some operational impact, but where an alternate procedure is acceptable to the state in its reasonable judgment, it is available to avoid operational impacts on the users. Examples include but are not limited to: a page within the STARS Solution is not working, but other avenues are available to complete the business process, albeit less conveniently; a functional component or service outage with an alternative workaround where the workaround degrades the operation of the STARS Solution from the user perspective; preferred method for completing business process is blocked, but alternate method is available; test script can be executed and completed with workaround. Severity Level 4 Production Warranty Deficiency: Any disruption in service that has a minor business or job impact affects multiple users or customers where those people affected are still able to perform their functions. A service component or procedure which is not critical is unusable where an alternate procedure acceptable to the State is available. Examples include but are not limited to: a degradation in the STARS Solution performance, data element is mislabeled, or a data element is misplaced on the page, test scripts can be completed without having to alter the page flow. | Severity Level 1 Production Warranty Deficiencies: Deployed to Production within 24 hours of classification as Severity Level 1. Severity Level 2 Production Warranty Deficiencies: Deployed to Production within 48 hours of classification as Severity Level 2. Severity Level 3 Production Warranty Deficiencies: None more than 20 calendar days old. Severity Level 4 Production Warranty Deficiencies: None more than 30 calendar days old. Measurement Process: On the last day of every month, the Contractor shall measure all Production Warranty Deficiencies by Severity that have not reached the Passed Test, Passed User Acceptance Testing (UAT), or Rejected by the State. If the Production Warranty Deficiencies in any of the severity categories are above the expected threshold, the SLA as a whole shall be defined as not meeting the Expected Performance Standard. Further, if Production Warranty Deficiencies in any Severity category are above the minimum threshold, the SLA as a whole shall be defined as not meeting the Minimum Performance Standard. | For each month the Contractor’s performance falls below the Expected Service Level Agreement, the Contractor’s invoice payment amount shall be reduced to $2500.00 per Severity Level 1 and Severity Level 2 Deficiency and reduced by $1000.00 per Severity Level 3 and Severity Level 4 Deficiency. |
| STARS Solution SLA/Solution Deficiency Identification | The Contractor shall be required to notify the State upon identification of a Solution Deficiency. The notifications shall be made through the use of e-mail and distribution lists. The State can also make direct inquiries to the Contractor as to the status of an individual incident and associated response actions at any time. The Contractor should respond to such escalated inquiries within the timeframes specified for each type of incident. The Contractor shall resolve all Solution Deficiencies (Contractor or State identified) within the timeframes shown in the Performance Target column for the level of severity of the deficiency. | Expected SLA: 98.0% of deficiencies resolved within Performance Standard. The Contractor shall report to the State a Deficiency for the STARS Solution, in whole or in part (“Solution Deficiency”). The Contractor shall report and resolve all Solution Deficiencies according to the following criteria and within the following timeframes: - Severity Level 1 (Critical Impact) Deficiency reported to the State upon inquiry within fifteen (15) minutes of the State’s request or identification and resolved within two (2) hours of identification. Root-cause analysis shall be performed with findings and resulting actions documented in the appropriate reports. - Severity Level 2 (Major Impact) Deficiency reported to the State upon inquiry within one (1) hour of request and resolved within 24 hours of identification. Root-cause analysis shall be performed with findings and resulting actions documented in the appropriate reports. - Severity Level 3 (Significant Impact) Deficiency reported to the State upon inquiry within two (2) State business hours of request and resolved within thirty (30) calendar days of identification. The Contractor shall resolve the problem or implement a workaround accepted by the state. Appropriate documentation shall be included in the reports. - Severity Level 4 (Minor Impact) Deficiency reported to the State upon inquiry within two (2) State business hours of request and resolved within an agreed-upon schedule between the Contractor and the State, which shall be measured on a schedule defined by the State and documented by the Contractor in the M&O Plan Deliverable. The Contractor shall provide the fix in a subsequent release of relevant and appropriate Software or operational processes. Appropriate documentation shall be included in the M&O reports. | For each month the Contractor’s performance falls below the Expected Service Level Agreement, the Contractor’s invoice payment amount shall be reduced to $1000.00 per Severity Level 1 and Severity Level 2 Deficiency identification and reduced to $500.00 per Severity Level 3 and Level 4 Deficiency identification. |
| STARS Solution Application Programming Interface (APIs) | The Contractor shall ensure 99.9% uptime for each System APIs (inbound and outbound), measured over a consecutive 24-hour period by a State-approved monitoring tool. Uptime shall mean that all System APIs are up, running, and functioning in accordance with the specifications in the Agreement. Unscheduled downtime resulting from infrastructure controlled and managed by the State or third parties or due to failure by the State or third parties to execute on its responsibilities related to maintenance or oversight of the STARS Solution or related systems, will not be considered as a measured SLA event. Unscheduled downtime resulting from use that is over and above the expected number of users of the STARS Solution will not be considered as a measured SLA event. The Contractor will be responsible for coordinating and working with third-party software and tools to help them find a resolution that can be integrated into the STARS Solution. Please note that this SLA comes into effect when the STARS Solution is in production. | The Contractor achieves the SLA uptime. | $5,000 per consecutive 24-hour period that the Contractor’s performance falls below the minimum SLA. |
| STARS Solution SLA/ Solution Transaction Time | STARS Solution developed by the Contractor, the Contractor shall ensure a transaction response time of one (1) second or less from user initiation (e.g., lookup, save, etc.) from an application screen on the user device at least 95.00% of the time, unless there are mutually agreed upon exceptions, as measured by a State-approved monitoring tool. Data, document, or processing intensive transactions will not be included in this SLA (i.e., uploading documents or data, processing data, manipulating documents). Transaction response time shall be calculated monthly in minutes rounded to the nearest hundredth of a percent. Average end-to-end response time from the user perspective. Delayed response time resulting from infrastructure controlled and managed by the State or third parties or due to failure by the State or third parties to execute on its responsibilities related to maintenance or oversight of the STARS Solution or related systems, will not be considered as a measured SLA event. Delayed response time resulting from use that is over and above the expected number of users of the system will not be considered as a measured SLA event. The Contractor will be responsible for coordinating and working with third-party software and tools to help them find a resolution that can be integrated into the STARS Solution. Please note that this SLA comes into effect when the STARS Solution is in production. | Expected SLA: 95.00% of the total number of transactions are to complete processing within one (1) second within a given month. Also, 99.5% of transactions are to complete processing within three (3) seconds. | $10,000 per month that the Contractor’s performance falls below the minimum SLA, not to exceed $30,000 annually. |
| STARS Solution SLA/ Release Deployment | To ensure timely creation and release of functionality, releases must be deployed within a committed timeframe as agreed with the State. All customizations/ configurations for the STARS Solution shall be checked-in into source control for every release. Continuous Integration and Continuous Deployment may be used to automate processes. Please note that this SLA comes into effect when the STARS Solution is in production. | ≥ 95.0% within the identified timeframe. | $500 per workday that the Contractor’s performance falls below the minimum SLA, not to exceed $5,000 per release. |
| STARS Solution SLA/ Availability | The percentage of actual uptime with planned uptime for each application and API. Unscheduled downtime resulting from infrastructure controlled and managed by the State or third parties or due to failure by the State or third parties to execute on its responsibilities related to maintenance or oversight of the STARS Solution or related systems, will not be considered as a measured SLA event. Unscheduled downtime resulting from use that is over and above the expected number of users of the STARS Solution will not be considered as a measured SLA event. The Contractor will be responsible for coordinating and working with third-party software and tools to help them find a resolution that can be integrated into the STARS Solution. Please note that this SLA comes into effect when the STARS Solution is in production. | 99.5% 24/7/365 days. | $10,000 per month that the Contractor’s performance falls below the minimum SLA, not to exceed $120,000 annually. |
| STARS Solution SLA/ Stability | The number of unplanned outages for users to access the production environment of the STARS Solution. Unscheduled downtime resulting from infrastructure controlled and managed by the State or third parties or due to failure by the State or third parties to execute on its responsibilities related to maintenance or oversight of the STARS Solution or related systems, will not be considered as a measured SLA event. Unscheduled downtime resulting from use that is over and above the expected number of users of the system will not be considered as a measured SLA event. The Contractor will be responsible for coordinating and working with third-party software and tools to help them find a resolution that can be integrated into the STARS Solution. | No unplanned outages per month. | $10,000 per month that the Contractor’s performance falls below the minimum SLA, not to exceed $120,000 annually. |
| STARS Solution SLA/ Reliability | Number of unplanned outages for users to access the production environment of the STARS Solution in consecutive months. Unscheduled downtime resulting from infrastructure controlled and managed by the State or third parties or due to failure by the State or third parties to execute on its responsibilities related to maintenance or oversight of the STARS Solution or related systems, will not be considered as a measured SLA event. Unscheduled downtime resulting from use that is over and above the expected number of users of the STARS Solution will not be considered as a measured SLA event. The Contractor will be responsible for coordinating and working with third-party software and tools to help them find a resolution that can be integrated into the STARS Solution. | No outages in back-to-back months (e.g., if an outage occurs in July, no outage can occur in August). | $10,000 per month that the Contractor’s performance falls below the minimum SLA, not to exceed $120,000 annually. |
| STARS Solution SLA/ Average Response Time | Average end-to-end response time from the user perspective. Delayed response time resulting from infrastructure controlled and managed by the State or third parties or due to failure by the State or third parties to execute on its responsibilities related to maintenance or oversight of the STARS Solution or related systems, will not be considered as a measured SLA event. Delayed response time resulting from use that is over and above the expected number of users of the STARS Solution will not be considered as a measured SLA event. The Contractor will be responsible for coordinating and working with third party software and tools to help them find a resolution that can be integrated into the STARS Solution. | Average of two (2) seconds over one (1) month. | $7,500 per month that the Contractor’s performance falls below the minimum SLA, not to exceed $30,000 annually. |
| Content Management/ Quality Assurance | Ensure converted data meets quality expectations set in the specifications. | Five (5) or fewer tickets verified to be a unique data quality/completeness issue in the first Twelve (12) months from the go-live date. | $500 per ticket over five (5), not to exceed $120,000. |
| Contract Management/ Key Staff | The Contractor shall provide Key Staff pursuant to the staffing requirements contained in this Agreement. | In cases where the State is not satisfied with the performance of a Contractor Key Staff person, the Contractor will provide an alternative candidate within twenty (20) calendar days and work iteratively with the State until the State is satisfied with Key Staff's performance. | $2,500 per State business day, or portion thereof, for each calendar day over twenty (20) that a new candidate has not been provided following a State request for Key Staff change. |
| Disaster Recovery/ Recovery Time Objective | In the event of a Disaster or an Unplanned Interruption, the Contractor shall restore and synchronize with Salesforce all production data, such that no history is lost within two (2) hours of the start of the Disaster or Unplanned Interruption. The Recovery Time Objective (RTO) shall be calculated from the start of a disaster or unplanned interruption until full system restoration. Disaster shall mean a riot, insurrection, civil unrest, terrorist attack, natural disaster (e.g., earthquake, fire, flood, hurricane), or similar event that causes the System to be not Available. Unplanned Interruption means any interruption to the STARS Solution outside the State-approved maintenance period. Please note that this SLA comes into effect when the STARS Solution is in production. | Contractor achieves the SLA. | $1,200 per hour or a portion thereof that the Contractor’s performance exceeds the 2 hour limit. |
| Disaster Recovery/ Recovery Point Objective | In the event of a Disaster or an Unplanned Interruption, the Contractor shall restore and synchronize with Salesforce all production data, such that no history is lost within two (2) hours of the start of the Disaster or Unplanned Interruption. The Recovery Point Objective (RPO) shall be calculated as the time between the start of the Disaster or Unplanned Interruption and the most recent preceding data backup. Disaster shall mean a riot, insurrection, civil unrest, terrorist attack, natural disaster (e.g., earthquake, fire, flood, hurricane), or similar event that causes the STARS Solution to be not Available. Unplanned Interruption means any interruption to the STARS Solution outside the State-approved maintenance period. Please note that this SLA comes into effect when the STARS Solution is in production. | Contractor achieves the SLA. | $1,200 per hour or a portion thereof that the Contractor’s performance falls below the minimum SLA. |
| General Performance (Customer Satisfaction)/ Customer Satisfaction Survey: Usability | Customer (the STARS Solution users) satisfaction surveys developed by the State in collaboration with Contractor staff and to be mutually agreed upon by both Parties, provide insight into the usability of the STARS Solution. | 90% of respondents rate it 7 out of 10. | $1,000 per response below the 90% threshold. |
| General Performance (Customer Satisfaction)/ Customer Satisfaction Survey: Internal | The Contractor is responsive to State staff and data partner feedback and concerns collected via surveys. Any enhancements that are outside the scope of work and associated requirements will only be addressed if mutually approved through the State change process; otherwise, responding to enhancements outside the scope of work will not be considered as a measurable SLA event. | 90% of respondents rate it 7 out of 10. | $250 per customer satisfaction survey with substantive feedback or suggestions that have not been properly addressed by the Contractor. |
| General Performance (Customer Satisfaction)/ Speed to Answer | Elapsed time to answer call/chat. These services will be provided from 7 AM to 5 PM, Monday–Friday, on all days that are not recognized as State holidays. | ≥ 85.0% within 45 seconds. | $7,500 per month that the Contractor’s performance falls below the minimum SLA, not to exceed $30,000 annually. |
| Tier 2 Technical / Application Support (Call and Email Responsiveness) | The percentage of calls and emails received, including tickets, on a monthly basis was unanswered. | The Contractor’s technical support staff shall respond to a minimum of 99% of the Level 2 calls and emails received, including tickets. | For each month the Contractor’s performance falls below the Performance Standard set forth in this SLA, the Contractor’s invoice payment amount shall be reduced by the following: $5,000 for unanswered call rates between 1% and 25% per month. $10,000 for an unanswered call rate between 25% and 50% per month; $20,000 for an unanswered call rate greater than 50% per month. |
| Tier 2 Technical / Application Support (Call Hold Time) | Call hold time for all calls in a given month of one (1) minute or more. | The Contractor’s technical support staff shall maintain an average call hold time of less than one (1) minute for all calls in a given month. | $5,000 for call hold times exceeding one (1) minute per month against total call hold average. |
| Tier 2 Technical / Application Support (Knowledge Provision) | Response time for questions or issues is greater than 48 hours. | The Contractor’s technical support time between identification of the question or issue and the response with a new or previously identified knowledge article to resolve the issue shall be no greater than two (2) days (48 hours). | $500 per question requiring more than two (2) days (48 hours) to answer. |
| Tier 2 Technical / Application Support (Ticket Resolution) | Percentage of response times greater than the following: For Severity Level 1 incidents, within two (2) hours of ticket receipt. For Severity Level 2 incidents, within three (3) hours of ticket receipt. For Severity Level 3 incidents, within four (4) hours of ticket receipt. For Severity Level 4 incidents, within 48 hours of ticket receipt. Level 3 and 4 services will be provided from 7 AM to 5 PM, Monday–Friday, on all days that are not recognized as State holidays. Please note that this SLA comes into effect when the STARS Solution is in production. | The Contractor’s technical support response time to respond via email or call providing resolution steps to ninety percent (90%) of tickets escalated to the Contractor’s technical support must occur no later than the following: For Severity Level 1 incidents, within two (2) hours of ticket receipt. For Severity Level 2 incidents, within three (3) hours of ticket receipt. For Severity Level 3 incidents, within four (4) hours of ticket receipt. For Severity Level 4 incidents, within 48 hours of ticket receipt. | $500 per ticket for a given month when response times exceed the time allowed to answer for 10% or more of tickets received in that month. |
| Security Services/ Severity 1* Incident Response | Percentage of Severity 1 security incidents responded to within 15 minutes of identification of any suspected security incident (including State’s notification). | At least 95.0% of Severity 1 security incidents responded to within 15 minutes. | $2,000 per incident per month. |
| Security Services/ Severity 1* Incident Containment | Percentage of Severity 1 security incidents contained within identified time from the mitigation and/or corrective actions plans provided to the CDTFA’s Information Security Officer or designee. | At least 95.0% of Severity 1 security incidents contained within two (2) hours of notifying the State of any potential or actual severity incident (containment plan publication) and meeting the mutually agreed-upon containment timeframe in the mitigation and/or corrective action plans (contained). | $4,000 per incident per month |
| Security Services/ Severity 2** Incident Containment | Percentage of Severity 2 security incidents contained within identified time from the mitigation and/or corrective actions plans provided to the CDTFA’s Information Security Officer or designee. | At least 95.0% of Severity 2 security incidents contained within four (4) hours (containment plan publication) & eight (8) hours (contained). | $2,000 per incident per month. |
| STARS Solution Security SLA/Data Breach SLA | The Contractor shall report a Data Breach to the BOE STARS Project Sponsor within one (1) hour of the Breach and provide a full detailed report to the BOE STARS Project Sponsor within four (4) hours of the Breach. The State and the Contractor shall jointly determine what constitutes a Data Breach. The agreed-upon criteria and format of reports shall be documented with the STARS Solution Security Management Plan. | Expected Service Level Agreement: 100% The reporting time of the breach shall be measured from the time of the identification by either party of the breach until the delivery of the full detailed report has been delivered and confirmed as received by the BOE STARS Project Sponsor. | $20,000 per incident per month. |

*Severity 1 is defined as a vulnerability which, if exploited, would allow malicious code to execute, potentially without a user being aware.

**Severity 2 is defined as a vulnerability which, if exploited, would compromise data security, potentially allowing access to confidential data, or could compromise processing resources.

The following Impact and Urgency table describes the classification and definition of the STARS Solution SLA Level 1, Level 2, Level 3, and Level 4.

Table 9 Service Level Agreements (SLA) and Liquidated Damages for Defect

| Urgency | Impact |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | State-Wide | Specific Location | Multiple Users | Single User |
| A full outage of multiple services or all services and/or noncompliance with regulations. | Level 1 | Level 1 | Level 2 | Level 3 |
| An issue completely affecting a service, no workaround available. | Level 1 | Level 2 | Level 2 | Level 3 |
| An issue affecting a service; workaround is available. | Level 2 | Level 3 | Level 3 | Level 3 |
| An issue that has no impact to the availability of the affected service; redundancy is available. | Level 3 | Level 4 | Level 4 | Level 4 |

# LIQUIDATED DAMAGES

Liquidated Damages are intended to encourage timely completion of critical project milestones and the provision of reliable and responsive services from the Contractor. The purpose of this Liquidated Damages provision is to ensure adherence to the requirements of the Agreement and to set an amount in advance of contractual non-compliance to compensate the State for damages that are impractical or extremely difficult to estimate, but which would be sustained by the State in the event the Contractor fails to perform services as agreed. The Liquidated Damages are intended to be a reasonable estimate of the damages and costs the State would sustain as a result of non-compliance with the terms of the Agreement. These amounts are not punitive. The State and Contractor, therefore, agree that in the event the Contractor fails to perform certain agreed upon services in a timely manner as specified in SECTION 33. SERVICE LEVEL AGREEMENTS (SLAs), the State may assess the Contractor for such amounts as Liquidated Damages, and not as a penalty.

The liquidated damages that may be assessed by the State as a result of the Contractor's delay or failure to perform its obligations in accordance with the terms of this Agreement are as described in the SLAs. Contractor shall pay Liquidated Damages as set forth in the Agreement.

The State shall calculate Liquidated Damages owed to the State on a monthly basis. The State may deduct Liquidated Damages from Contractor’s fees as earned or may assess such Liquidated Damage fees via a separate invoice at any time during the Agreement or within thirty (30) days after the Agreement ends.

The Parties agree that any delay or failure by Contractor to timely perform its obligations under this Agreement will interfere with the proper and timely implementation of the STARS Solution, to the loss and damage to the State. The State will incur costs to maintain the functions that would have otherwise been performed by the Contractor. Delays caused by the State will not result in damages charged to the Contractor.

The Assessment of liquidated damages is subject to the dispute resolution process in accordance with the INFORMATION TECHNOLOGY GENERAL PROVISIONS – CLOUD COMPUTING SERVICES DGS PD 402-ITGP CLOUD (REVISED 2/20/2025)SECTION 17, DISPUTE RESOLUTIONS (SEE LINK IN SECTION 36).

## LIQUIDATED DAMAGES CAP

If imposed, Liquidated Damages shall be no more than $100,000 per day, from notice and total Liquidated Damages shall not exceed ten percent (10%) of the total Contract amount.

## PAYMENT OF LIQUIDATED DAMAGES

The State may deduct Liquidated Damages from Contractor’s invoices or may assess such Liquidated Damages via a separate invoice at any time during the Agreement or within thirty (30) days after the Agreement ends. The State will notify the Contractor Representative SECTION 7. CONTRACT REPRESENTATIVES in writing of any claim for Liquidated Damages pursuant to this section on or before the date the State deducts such sums from money payable to the Contractor. If the State imposes Liquidated Damages, upon notification by the State, the Contractor shall show the Liquidated Damages as a subtracted item from its invoice(s) to the State.

Imposition of Liquidated Damages does not constitute a waiver of the State’s right to issue a Stop Work Order in accordance with THE INFORMATION TECHNOLOGY GENERAL PROVISIONS – CLOUD COMPUTING SERVICES DGS PD 402-ITGP CLOUD (REVISED 2/20/2025), SECTION 18, STOP WORK or terminate the Agreement pursuant to INFORMATION TECHNOLOGY GENERAL PROVISIONS – CLOUD COMPUTING SERVICES DGS PD 402-ITGP CLOUD (REVISED 2/20/2025), SECTION 16.3, TERMINATION FOR DEFAULT (SEE LINK TO SECTION 36). In the event of such a termination, the State shall be entitled, at its discretion, to recover actual damages caused by the Contractor’s failure to perform its obligations under this Agreement.

## CALCULATION OF LIQUIDATED DAMAGES

The calculations for Liquidated Damages are defined in SECTION 33. SERVICE LEVEL AGREEMENTS (SLAs).

# UNANTICIPATED TASKS

During the Contract period, legislative and/or program changes may necessitate changes to the STARS Solution System and/or software. These changes may result in unanticipated tasks and be structured based on the Contractor’s hourly labor rates identified in the cost worksheet. These rates will be used to support change requests for changes and enhancements to the Agreement.

Unanticipated tasks are additional work performed within the scope of the Contract but were not identified in the State's solicitation document or SOW. Both the State and the Contractor must agree upon the work to be performed, which may result in unanticipated costs. No work can be performed in advance of the State's approval of unanticipated task work; the Contractor will use the same hourly labor rates per staff classification as identified in the Base Contract Term and pricing portion of the cost worksheet.

The State limits the budget for unanticipated tasks not to exceed ten percent (10%) of the sum of the base Contract for services identified in the EXHIBIT E: COST WORKBOOK.

If additional work must be done, the procedures outlined in this section will be followed.

For each unanticipated task, the Contractor shall prepare a Work Order Authorization (WOA) Form in RFP ATTACHMENT 19: WORK ORDER AUTHORIZATION FORM.

It is understood and agreed by both Parties to this Agreement that all the terms and conditions of this Agreement shall remain in force with the inclusion of any such WOA. Such WOA shall in no way constitute an Agreement other than as provided pursuant to this Agreement nor in any way amend or supersede any of the other provisions of this Agreement.

Each WOA shall consist of a detailed statement of the scope, purpose, objective, and/or goals to be undertaken by the Contractor, including but not limited to the following:

- The job classification(s), or approximate skill level(s), and name of the staff to be assigned as available by the Contractor.

- An identification of all significant material to be developed by the Contractor and delivered to the State.

- An identification of all significant materials to be delivered by the State to the Contractor.

- An estimated time schedule of the fulfillment of these services by the Contractor.

- Completion criteria for the work to be done.

- The Contractor’s estimated work hours required to accomplish the scope, purpose, objective, and/or goals.

- The Contractor’s billing rates as identified in EXHIBIT E: COST WORKBOOK and the Contractor’s estimated total cost on the WOA.

All WOA must be in writing and signed by the Contractor and State prior to beginning work. The Contractor shall not begin work on a WOA until the authorized State staff has approved the WOA.

The State has the right to require the Contractor to stop or suspend work on any WOA with three (3) State business days' notification.

If, in the performance of the work, the Contractor determines that a WOA to be performed under this Agreement cannot be accomplished within estimated work hours, the Contractor shall immediately notify the State in writing of the Contractor’s estimate of additional work hours and cost which will be required to complete the WOA in full. Upon receipt of the notification, the State in its discretion may choose any of the following actions:

- Authorize the Contractor to expend the estimated additional work hours or service more than the original estimate necessary to accomplish the work.

- Terminate the WOA; or

- Alter the scope of the WOA to define tasks that can be accomplished within the remaining estimated work hours and cost.

- Notify the Contractor in writing of its decision within seven (7) State business days after receipt of the notification.

Upon successful completion of the work to be performed for an approved WOA, the State will provide a WOA acceptance form in RFP ATTACHMENT 20: WORK ORDER AUTHORIZATION ACCEPTANCE FORM, indicating that the acceptance criteria of the WOA have been met and signed to indicate approval. The Contractor must receive the acceptance document before invoicing the State.

# INFORMATION TECHNOLOGY GENERAL PROVISIONS – CLOUD 	COMPUTING SERVICES DGS PD 402-ITGP CLOUD (02/20/2025)

The Contract awarded as a result of this solicitation shall automatically incorporate by reference the Information Technology General Provisions – Cloud Computing Services DGS PD 402-ITGP Cloud (Revised 2/20/2025)

https://www.dgs.ca.gov/%7E/media/Divisions/PD/Acquisitions/Solicitation-Document-Attachments/IT-General-Provisions-Cloud-DGS-PD-402ITGP-Revised-02202025.pdf

# MISCELLANEOUS

CONTRACTOR’S QUALIFICATIONS AND STATEMENT OF ECONOMIC INTEREST

The Contractor covenants that its previous representations to the State regarding its qualifications to perform the services provided for herein are true and accurate.

Within thirty (30) days of the execution of the Agreement or commencement of any services, whichever is later, under this Agreement, the Contractor’s employees and subcontractors performing services under this Agreement (“Designated Filers,” as determined by the State)  shall complete and file a Statement of Economic Interest (Form 700) as required by State’s Conflict of Interest Code and section 87300 et seq. of the Government Code. At a minimum, any and all, sub-interests or entities, including those of their spouse, or dependent children, which the Contractor may be working with in the course of this Agreement, must be identified by the Contractor's employees, as applicable. Each Designated Filer shall also timely complete and file a Statement of Economic Interests annually and upon leaving office, as applicable. The Contractor shall provide, and represent that it has provided, to the State the names and responsibilities of those employees and agents who will provide services under this Agreement. If, during the term of this Agreement, the Contractor desires to have different or additional employees or agents provide services under this Agreement, the Contractor shall provide such names and other information requested to State so that the State may determine whether such persons must comply with this provision.

In the event the Contractor or Designated Filer fails to return the completed Statement of Economic Interests to the State within thirty (30) calendar days from the date this Agreement is executed or fails to complete and file an annual or leaving office statement or fails to complete ethics training if required under this Agreement, within the times required, the State reserves the right to withhold payment for any services performed and reserves the right to cancel this Agreement.

In the event any of the Statement of Economic Interests reveals a conflict of interest which, as determined by the State, could impair the Contractor's ability to properly or legally perform the services contemplated by this Agreement, the State reserves the right to request immediate removal of the individual from the Agreement or cancel this Agreement.

## SUBCONTRACTORS

Nothing contained in this Agreement, or otherwise, shall create any contractual relation between the State and any subcontractors, and no subcontract shall relieve the Contractor of its responsibilities and obligations hereunder. The Contractor agrees to be as fully responsible to the State for the acts and omissions of its subcontractors and of persons either directly or indirectly employed by any of them as it is for the acts and omissions of persons directly employed by the Contractor. The Contractor’s obligation to pay its subcontractors is an independent obligation from the State’s obligation to make payments to the Contractor. As a result, the State shall have no obligation to pay or to enforce the payment of any money to any subcontractor.

# GLOSSARY OF TERMS

See RFP ATTACHMENT 23 for the State glossary of terms.

# HYPERCARE ACTION LIST

STARS Solution Hypercare Action List

The Hypercare Plan Checklist is a guide designed to ensure smooth and effective support during the hypercare period of a project or a major code release. It outlines the necessary activities, staff, roles, responsibilities, and processes required to manage and resolve issues that may arise after the project goes live.

- Team & Roles

- Dedicated Support Team:

- STARS Solution System Administrator

- System Owner

- Data Owner

- Project Manager(s) [Vendor and Client Project Managers]

- Technical Manager

- Subject Matter experts

- Contractor Technical Lead

  - Lead Code Programmers

  - Lead Testers

- Responsibilities:

- Define Required Key Staff as Part of the Hypercare Team

- Define clear Team Roles (above)

- Define Responsibilities

- Make Clear the Escalation Paths to Solve the Issue

- Define Hypercare Mode Exit Criteria

      - Zero high-severity bugs

      - System stability for “X” Days As Jointly Agreed Upon

      - Success benchmarks defined

      - Performance metrics defined and met to return to business as usual (BAU)

- Team Training:

- Ensure the team is trained in new systems and response processes.

- Ensure the team is trained for hypercare support

- Issue Management (Incident Response)

- Issue Tracking:

- Set up “Service Team” system to log, classify, and prioritize issues

- Obtain TSD Help Desk Log on STARS support

- Set up Issues log spreadsheet on TEAM share

- Provide a Code roll back strategy

- Perform Daily Stand Up Status Meetings

- Define and establish hypercare exit criteria and period

- Prioritization: Use a clear severity matrix and defined SLAs for response/resolution.

- Expected SLA:

      - Severity Level 1 Production Deficiencies: Deployed to Production within 24 hours of classification as Severity Level 1.

      - Severity Level 2 Production Deficiencies: Deployed to Production within 48 hours of classification as Severity Level 2.

      - Severity Level 3 Production Deficiencies: None more than 20 calendar days old.

      - Severity Level 4 Production Deficiencies: None more than 30 calendar days old.

- The Team Member shall report and resolve all Solution Deficiencies according to the following criteria and within the following timeframes:

      - Severity Level 1 (Critical Impact) Deficiency reported to the System Owner upon inquiry within fifteen (15) minutes of the System Owner’s request or identification and resolved within two (2) hours of identification. Root-cause analysis shall be performed with findings and resulting actions documented in the appropriate reports.

      - Severity Level 2 (Major Impact) Deficiency reported to the System Owner upon inquiry within one (1) hour of request and resolved within 24 hours of identification. Root-cause analysis shall be performed with findings and resulting actions documented in the appropriate reports.

      - Severity Level 3 (Significant Impact) Deficiency reported to the System Owner upon inquiry within two (2) System Owner business hours of request and resolved within thirty (30) calendar days of identification. The Team Member shall resolve the problem or implement a workaround accepted by the System Owner. Appropriate documentation shall be included in the reports.

      - Severity Level 4 (Minor Impact) Deficiency reported to the System Owner upon inquiry within two (2) State business hours of request and resolved within an agreed-upon schedule between the Team Member and the System Owner, which shall be measured on a schedule defined by the System Owner and documented by the Team Member. The Team Member shall provide the fix in a subsequent release of relevant and appropriate Software or operational processes. Appropriate documentation shall be included in the M&O reports.

A workaround is a temporary fix to either a Hardware or Software failure, restoring core business functionality and preventing significant impacts that would otherwise prevent the business from operating as intended. All workarounds and code roll backs must be approved by the State, in writing, prior to implementation.

- Monitoring & Performance:

- System Health:

  - Monitor Availability: Uptime Hours; Maintenance Hours; Downtime Hours

  - Performance: Peak load; Number of Concurrent Users

  - Data Governance Policy Applied

    - Metadata Extracted

    - Data Catalog Updated

- Resolution: Plan for rapid fixes, testing, and deployment of hotfixes.

- Adoption Metrics:

  - Track State and Assessee user adoption rates via account creations

  - Engagement via user login in times and durations

  - Monitor common user challenges via feedback emails and user experiences assessments via 5 star rating

- Dashboards: Implement live dashboards for real-time visibility regarding:

  - Uptime Hours

  - Number of Logged on Users

  - Number of File or Document Uploads and Downloads

  - System Usage CPU Minutes; I/O Traffic

- Communication:

- Stakeholder Updates:

  - Establish regular, standardized communication for leadership and users.

    - Weekly Project Update Meetings

    - Weekly Status Reports

- Proactive Outreach:

  - Reach out to users experiencing issues.

- Feedback Loop:

- Create channels for user feedback.

Table 10 Hyper Care Service Level Agreement (SLA)

| SLA Title | Performance Description (SLA Performance Standard) | Performance Target (Expected SLA) |
| --- | --- | --- |
| Defect Management - Root Cause Analysis (RCA) Submission The initial RCA document shall provide, as it is understood at the time of submission, the deficiency identification time and date, an estimate of solution and user impacts, an estimate of the duration, actions taken and planned, and a timeline for submission of a completed RCA. | The Team Member shall submit to the BOE STARS Project Sponsor, or designee, as defined in the Project Management Plan, an initial Root Cause Analysis (RCA) document for every Severity Level 1 and Severity Level 2 deficiency, within 24 hours of identification. | The Team Member shall submit an initial root cause analysis to the System Owner within 24 hours of identification. The Team Member shall submit the complete analysis within ten (10) business days of the identification of the issue. |
| STARS SLA/Solution Deficiency Identification | The Team Member shall be required to notify the System Owner upon identification of a Solution Deficiency. The notifications shall be made through the use of e-mail and distribution lists. The System Owner can also make direct inquiries to the Team Member as to the status of an individual incident and associated response actions at any time. The Team Member should respond to such escalated inquiries within the timeframes specified for each type of incident. The Team Member shall resolve all Solution Deficiencies within the timeframes shown in the Performance Target column for the level of severity of the deficiency. | Expected SLA: 98.0% of deficiencies resolved within Performance Standard. The Team Member shall report to the System Owner a Deficiency for STARS, in whole or in part (“Solution Deficiency”). The Team Member shall report and resolve all Solution Deficiencies according to the following criteria and within the following timeframes (see above table). |
| STARS Application Programming Interface (APIs) | The Team Member shall ensure 99.9% uptime for each System APIs (inbound and outbound), measured over a 24-consecutive hour period by a System Owner-approved monitoring tool. Uptime shall mean that all System APIs are up, running, and functioning in accordance with the specifications in the Agreement. Unscheduled downtime resulting from infrastructure controlled and managed by the System Owner or third parties or due to failure by the System Owner or third parties to execute on its responsibilities related to maintenance or oversight of STARS or related systems, will not be considered as a measured SLA event. Unscheduled downtime resulting from use that is over and above the expected number of users of STARS will not be considered as a measured SLA event. The Team Member will be responsible for coordinating and working with third-party software and tools to help them find a resolution that can be integrated into STARS. | The Team Member achieves the SLA uptime. |
| STARS SLA/ Solution Transaction Time | The Team Member shall ensure a transaction response time of one (1) second or less from user initiation (e.g., lookup, save, etc.) from an application screen on the user device at least 95.00% of the time, unless there are mutually agreed upon exceptions, as measured by a System Owner-approved monitoring tool. Data, document, or processing intensive transactions will not be included in this SLA (i.e., uploading documents or data, processing data, manipulating documents). Transaction response time shall be calculated monthly in minutes rounded to the nearest hundredth of a percent. Average end-to-end response time from the user perspective. Delayed response time resulting from infrastructure controlled and managed by the System Owner or third parties or due to failure by the System Owner or third parties to execute on its responsibilities related to maintenance or oversight of STARS or related systems, will not be considered as a measured SLA event. Delayed response time resulting from use that is over and above the expected number of users of the system will not be considered as a measured SLA event. The Team Member will be responsible for coordinating and working with third-party software and tools to help them find a resolution that can be integrated into STARS. | Expected SLA: 95.00% of the total number of transactions are to complete processing within one (1) second within a given month. Also, 99.5% of transactions are to complete processing within three (3) seconds. |
| STARS SLA/ Availability | The percentage of actual uptime with planned uptime for each application and API. Unscheduled downtime resulting from infrastructure controlled and managed by the System Owner or third parties or due to failure by the System Owner or third parties to execute on its responsibilities related to maintenance or oversight of STARS or related systems, will not be considered as a measured SLA event. Unscheduled downtime resulting from use that is over and above the expected number of users of STARS will not be considered as a measured SLA event. The Team Member will be responsible for coordinating and working with third-party software and tools to help them find a resolution that can be integrated into STARS. | 99.5% . |
| STARS SLA/ Stability | The number of unplanned outages for users to access the production environment of STARS. Unscheduled downtime resulting from infrastructure controlled and managed by the System Owner or third parties or due to failure by the System Owner or third parties to execute on its responsibilities related to maintenance or oversight of STARS or related systems, will not be considered as a measured SLA event. Unscheduled downtime resulting from use that is over and above the expected number of users of the system will not be considered as a measured SLA event. The Team Member will be responsible for coordinating and working with third-party software and tools to help them find a resolution that can be integrated into STARS. | No unplanned outages per month. |
| STARS SLA/ Reliability | Number of unplanned outages for users to access the production environment of STARS in consecutive months. Unscheduled downtime resulting from infrastructure controlled and managed by the System Owner or third parties or due to failure by the System Owner or third parties to execute on its responsibilities related to maintenance or oversight of STARS or related systems, will not be considered as a measured SLA event. Unscheduled downtime resulting from use that is over and above the expected number of users of STARS will not be considered as a measured SLA event. The Team Member will be responsible for coordinating and working with third-party software and tools to help them find a resolution that can be integrated into STARS. | No outages in back-to-back months (e.g., an outage occurs in July, no outage can occur in August). |
| STARS SLA/ Average Response Time | Average end-to-end response time from the user perspective. Delayed response time resulting from infrastructure controlled and managed by the System Owner or third parties or due to failure by the System Owner or third parties to execute on its responsibilities related to maintenance or oversight of STARS or related systems, will not be considered as a measured SLA event. Delayed response time resulting from use that is over and above the expected number of users of STARS will not be considered as a measured SLA event. The Team Member will be responsible for coordinating and working with third party software and tools to help them find a resolution that can be integrated into STARS. | Average of two (2) seconds over one (1) month. |

DevSecOps is a tactical trifecta that connects three disciplines: development, security, and operations. The goal is to seamlessly integrate security into the continuous integration and continuous delivery (CI/CD) pipeline in both pre-production (dev/test/staging) and production (ops) environments. In the end, DevSecOps practices will release secure software faster, and detect and respond to security flaws (like vulnerabilities) faster and more efficiently.