## TasksDels
ID | Task/Deliverable Description | Resulting Work Product(s) / Outputs | Timing | Milestone/Payment Point | Contractor Agrees to Meet (Yes/No)
Category 1: Project Planning Tasks and Deliverables
1.1 | Kick Off Project | • Kickoff Meeting Materials • Kickoff Meeting • Kickoff Meeting Notes | Within 30 10 calendar days of contract execution | State acceptance of Project Kick Off and deliverable components identified in Column C.
1.1a | Plan and schedule Project Kickoff Meeting: The Project Kickoff Meeting will introduce the project team and communicate project objectives, approach, timeline, assumptions, constraints, management, project organization, roles and responsibilities, and deliverables to Project Stakeholders.
1.1b | Develop Kickoff Meeting presentation and any other materials
1.1c | Conduct the Project Kickoff Meeting
1.1d | Document and distribute notes from Project Kickoff Meeting
1.2 | Initial Project Schedule | • Baselined Project Schedule | Within 30 45 calendar days of contract execution | State acceptance of initial Project Schedule
1.2a | Finalize the Project Schedule that outlines the project activities and tasks using a Work Breakdown Structure (WBS) that includes Phases, Activities, Tasks, Deliverables, Dependencies, and Milestones, in Microsoft Project. The Project Schedule will: • Identify all WBS components needed to complete all project deliverables. • Identify both Contractor and State staff resources responsible for key project activities and deliverables. • Identify Task ownership and assigned resources. • Identify planned and actual start and end dates, with % of project complete by major task. • Identify the critical path for project completion. • Include Organizational Change Management (OCM) tasks.
1.3 | Create Product Roadmap | • Product Roadmap | Within 30 45 calendar days of contract execution | State acceptance of Product Roadmap
1.3a | Create Product Roadmap, a visual representation of the iterative Agile approach to develop the CAB Online product that represents the flexible plan to achieve the product vision and strategy. The Product Roadmap will: • Include a high-level timeframe. • Identify likely growth of the product over time. • Reflect development and project priorities. • Identify measurable goals and key performance indicators.
1.4 | Create Contractor Project Management Plan | • Contractor PMP | Within 30 45 calendar days of contract execution | State acceptance of Contractor PMP
1.4a | Develop the Contractor Project Management Plan (PMP) that will serve as the comprehensive guide that outlines how the project will be planned, executed, monitored, and controlled. The PMP will address management topics that include, at a minimum: • Project vision, objectives, and critical success factors. • Approach to ensure successful implementation and delivery of all system components in accordance with the Contract. • Approach to conduct required activities and produce required project deliverables in each Project Category. • Project organization structure and governance. • Key project management and leadership roles and responsibilities. • Key stakeholders and their roles and responsibilities. • Project management status reporting and schedule update frequency. • Escalation process for internal project decisions within the scope of project activities. • Key Stakeholders and roles and responsibilities. • Project expectations, constraints, dependencies, and challenges.
1.4b | Comply with the policies and procedures, and perform tasks as requested by the State Project Manager, in support of the State-produced Management Plans: • Project Management • Governance • Schedule Management • Cost Management • Implementation Management • Communication Management • Requirements Management • Scope Management • Risk Management • Issue Management • Contract Management • Change Control Management • Resource Management • Stakeholder Management • Quality Management • Security Management • Testing Management • Configuration Management • Data Management • M&O Transition
1.5 | Create Deliverable Management Plan | • Deliverable Management Plan • Deliverable Expectation Documents • Deliverable Acceptance Documents | Within 30 45 calendar days of contract execution | State acceptance of Deliverable Management Plan
1.5a | The Deliverable Management Plan will serve as the comprehensive guide that outlines how the project deliverables will be developed, submitted, and reviewed, and executed and monitored throughout the duration of the project, in accordance with the Deliverables defined in EXHIBIT A: STATEMENT OF WORK. The Deliverables Management Plan will include, at a minimum: • Schedule of planned deliverables. • Roles and responsibilities. • Naming convention. • Repository organization. • Deliverable Expectation and Deliverable Acceptance documentation management and processes. • Deliverable version control.
1.6 | Organizational Change Management Plan | • Organizational Change Management Plan | Within 30 45 calendar days of contract execution | State acceptance of Organizational Change Management Plan
1.6a | The Contractor shall provide an OCM Plan that shall clearly: • Identify changes moving from as-is to the to-be and their alignment to CAB Online business goals and objectives • Define the expected benefits and outcomes • Define metrics to measure OCM effectiveness and user readiness. • Define stakeholder assessment and management approach • Define the OCM roles and responsibilities • Summarize any potential organizational changes and impacts
1.7 | Organizational Change Management Communication Plan | • Organizational Change Management Communication Plan | Within 30 45 calendar days of contract execution | State acceptance of Organizational Change Management Communication Plan
1.7a | The Contractor shall develop and implement the OCM Communication Plan to promote the execution and rollout of the project and phases. This plan will help ensure the organization’s messaging about project-related changes are clear, concise and consistent. Contractor shall develop the Communications Plan based on the following required actions: • Conduct stakeholder surveys • Conduct interviews with stakeholders • Perform stakeholder analysis • Develop Communication Matrix • Define the Contractor’s communications methodology • Describe Contractor’s communications approach • Identify Internal and external project stakeholders • Identify communication tools. For examples; fact sheet, newsletters, presentations. • Identify methods to measure the effectiveness of communications
1.8 | Technology Recovery Plan | • Technology Recovery Plan | Within 30 45 calendar days of contract execution | State acceptance of the Technology Recovery Plan
1.8a | The Contractor shall develop the Technology Recovery Plan which outlines the steps and procedures needed to restore the CAB Online system after a disruptive event.
1.9 | Disaster Recovery Plan | • Disaster Recovery Plan | Within 30 45 calendar days of contract execution | State acceptance of the Disaster Recovery Plan
1.9a | The Contractor shall develop the Disaster Recovery Plan that outlines how to respond to and recover from unplanned incidents, ensuring business continuity. The Disaster Recovery Plan, at a minimum, shall have the following: • Risk Assessment: Identifying potential threats and vulnerabilities that could disrupt operations. • Business Impact Analysis: Determining the potential impact of a disaster on critical business functions. • Recovery Objectives: Defining specific, measurable, achievable, relevant, and time-bound (SMART) goals for recovery. • Backup and Recovery Procedures: Establishing clear steps for backing up data and restoring systems. • Communication Plan: Outlining how to communicate during and after a disaster. • Team Roles and Responsibilities: Clearly defining the roles and responsibilities of individuals involved in the recovery process.
1.1 | Knowledge Transfer Plan | • Knowledge Transfer Plan | Within 30 45 calendar days of contract execution | State acceptance of the Knowledge Transfer Plan
1.10a | The Contractor shall develop the Knowledge Transfer Plan which will define the knowledge transfer methodology, timing, and topics.
Category 2: CAB Online Design Tasks and Deliverables
2.1 | Validate Requirements | • Updated Requirements Traceability Matrix | One time after Project Planning (Category 1), prior to System Development | State acceptance of RTM
2.1a | Organize and facilitate requirements sessions to validate and create the baselined set of all functional and nonfunctional requirements.
2.1b | Review and confirm existing processes.
2.1c | Maintain the CAB Online Requirements Traceability Matrix (RTM)
2.2 | Create Architecture Design Specifications | • Architecture Design Specifications • Baseline Configured System | One time after Project Planning (Category 1), prior to System Development | State acceptance of Architecture Design Specifications and Baseline Configured System
2.2a | Create Architecture Design Specifications that show system architecture, system components, data flows, and integration points and guide the development of the CAB Online solution. The Architecture Design Specifications will include, at a minimum: • Descriptions with diagrams of the CAB Online system architecture and subsystems that reflect a view of the CAB Online from an enterprise perspective, including integration with other systems. • A narrative description of each system function, conditions for use, security requirements, and how they will interface with other CDPH or external systems. • Assumptions, dependencies, general constraints, goals, guidelines, and development methods. • Identification of any cloud infrastructure impacts due to any design consideration. • A process and data flow document that graphically represents major system process flows, key data flows, identification of key CAB Online subsystems, and key integrations and interfaces using a CDPH-approved diagramming approach. • Key system integrity controls (e.g., internal security, audit procedures, application audit trails, field validation, verification processes). • Configuration of application, environment instances, and Active Directory on all system environments. • Configuration of system access granted at various levels in accordance with the user roles and permissions. • A dependency map that shows how configuration items (e.g., Software modules) are controlled • A description of how changes to the baseline configuration items will be requested, evaluated, tested, approved, and implemented. • A description of tools to be utilized to support configuration management.
2.2b | Establish the baseline configuration of the CAB Online system.
2.3 | Create Database Design Specifications | • Database Design Specifications | One time after Project Planning (Category 1), prior to System Development | State acceptance of Database Design Specifications
2.3a | Create the Database Design Specifications to support all business functionality identified in the functional and non-functional requirements. The Database Design Specifications will include, at a minimum: • Approach to database design for all CAB Online databases and data storage. • Data retention processes and procedures. • Data volumes. • Logical and physical data models. • Documented Business Rules. • Data Flow Diagrams. • Entity Relationship Diagrams. • Database schemas. • Database standards and conventions. • Data Dictionary. • Database management and administration. • Naming standards. • A description of the data management strategy that addresses data governance, data architecture, storage architecture, data sharing architecture, and business intelligence. • A description of the incremental development and deployment of functionality over time while ensuring data consistency and design integrity across CAB Online
2.4 | Create Integration and Interface Specifications | • Integration and Interface Specifications | One time after Project Planning (Category 1), prior to System Development | State acceptance of Integration and Interface Specifications
2.4a | Create the Integration and Interface Specifications to include, at a minimum: • A description of the approach to integrate CAB Online with other applications and systems. • Identification of other systems and a high-level work plan that delineates each system’s team activities and milestones. • Description of how the Contractor will coordinate with other systems for design and development, testing, release management, implementation, and post-implementation support. • For each integration or interface point: identification of source and destination systems, interface directionality, transmission methods and protocols, frequency and timing of transmissions, transmission volumes, interface format and data elements, processing methods and rules, messages and response messages, interface service availability monitoring for both automated and manual interfaces, error handling controls and methods for restart, interface testing methods, key test cases, test environment requirements, interface file names and processing rules, interface security controls with encryption and decryption capabilities that will ensure secure data transfer between systems, administration and operational processes and considerations, interconnectivity service agreements, and escalation procedures to identify, report, and address interface-related production problems.
2.5 | Create CAB Online Implementation Plan | • CAB Online Implementation Plan • Business Impact Analysis (BIA) Report | One time after Project Planning (Category 1), prior to System Development | State acceptance of CAB Online Implementation Plan and BIA Report
2.5a | Create the CAB Online Implementation Plan that describes the Contractor’s development approach, implementation stages, and sequence of activities and capabilities deployed to production for each stage. The Implementation Plan will include, at a minimum: • Identification and description of implementation stages, the key objectives, dependencies, and roll-out plan for each. • Incorporation of selected data migration, training, interfaces, and integrations. • Contractor and State roles and responsibilities. • The approach to demonstrate completion of and obtain CDPH acceptance for each implementation stage. • Description of the release process and procedures, including naming conventions, release type, release cadence, release calendar, release management tools, release communications, and release notes. • An escalation process for release issues. • A release validation process. • The tasks and schedule for roll-out activities and transition that include data conversion, data transfer and migration to CAB Online. • The approach and steps to cutover from CalREDIE to CAB Online. • Development of necessary documentation. • Contingency and rollback plans in the event of adverse operations or data failures during implementation of each stage. • Plans for production support following Go-Live.
2.5b | Perform a Business Impact Analysis.
Category 3: CAB Online Solution Development Tasks and Deliverables
3.1 | Create System Development Plan | • System Development Plan • System Development Schedule • The initial Product Backlog • Sprint progress reports • Functional software from each sprint | After Design (Category 2), and before Implementation | State acceptance of System Development Plan and Schedule
3.1a | Create the System Development Plan that describes how the Contractor will use an Agile development framework to develop the CAB Online System. The System Development Plan will include, at a minimum: • Contractor’s approach to configure, modify, and customize the CAB Online in accordance with functional and non-functional requirements, using an Agile development framework. • A description of the implementation stages the Contractor will use to develop the CAB Online solution. • A list of tasks Contractor will undertake to plan and prepare for the execution of functionality sprints, execute each sprint, and create the initial preliminary product and sprint backlog. • How the Contractor will provide interactive demonstrations that verify functionality implemented during each sprint. • Contractor’s approach to establish a foundation for smooth and efficient development in subsequent sprint iterations. • Utilization of team resources, workspaces, and remote collaboration tools. • Identification of project development standards (e.g., coding, SharePoint) the Contractor will use to implement the CAB Online. • Identification of the tools and software to develop and operate the CAB Online. • Contractor’s approach for software support, maintenance, and operations. • How Contractor will deliver all source code to the State.
3.1b | Create a system development schedule with milestones
3.2 | Create User Stories (for each release) | • User stories | After Project Planning, before each release | State acceptance of the release User Stories
3.2a | Work with CDPH staff to develop user stories that describe desired features and functionality from the end-user perspective.
3.3 | Configure and Build the CAB Online system (for each release) | • Product Backlogs • Sprint Progress Reports • Sprint Backlogs • Product Increments • Interactive Demonstrations • Implemented CAB Online System | After Design completion, prior to each release | State acceptance of each CAB Online system release
3.3a | Implement the CAB Online system in accordance with the System Development Plan, Architecture Design Specifications, Database Design Specifications, and Integration and Interface Specifications.
3.3b | Conduct a Daily Scrum that includes key Contractor staff and State staff.
3.3c | Create and manage sprint releases.
3.3d | Produce and deliver all Agile artifacts (e.g., product backlog, sprint progress reports, sprint backlog, and product increments).
3.3e | Provide interactive demonstrations to State staff to verify implemented system functionality.
3.4 | Create Defect Resolution Plan | • Defect Resolution Plan | After Design completion | State acceptance of Defect Resolution Plan
3.4a | Create the Defect Resolution Plan to include, at a minimum: • The Contractor’s approach to resolve system defects identified during system development and testing, UAT, and following system implementation. • Procedures to capture, respond to, track, prioritize, analyze, and resolve defects. • The method for reporting and communicating all defects, their status, and resolution.
3.5 | Resolve all identified defects according to the Defect Resolution Plan (for each release) | • Defect-free System | Ongoing through Final System Acceptance | State acceptance of each release
3.6 | Create Overall System Test Plan | • System Test Plan • Test Schedule | After Design completion | State acceptance of System Test Plan and Schedule
3.6a | Create the System Test Plan to describe the testing approach for the CAB Online solution implementation, and the methods, objectives, resources, timeline, and test management for each environment. The System Test Plan will include, at a minimum: • The Contractor’s testing approach for all testing cycles, including unit, integration, interface, system, end-to-end, load capacity, stress, regression, production simulation, accessibility, security, white hat, and penetration testing. • Approach to create and maintain test scenarios, acceptance criteria, test cases, test scripts, and their formats. • Approach and description of processes, procedures, and protocols to perform CAB Online system, data, and documentation quality assurance. • Identification and description of any tools the Contractor will use for testing, including automated testing. • The plans to prepare for, facilitate, and support User Acceptance Testing (UAT). • Testing roles and responsibilities. • Identification of test environments, test database, and data requirements for each test phase. • How Contractor will report on test status, identify issues, and take corrective actions to ensure resolution. • Description of the test results reports and how Contractor will certify that the system is fully tested and satisfies all functional and non-functional requirements, complies with all CDPH security requirements, and meets established performance metrics.
3.7 | Phase Test Plan (for each phase) | • Phase Test Plan • Phase Test Schedule • Phase Test Scenarios, Cases, and Scripts | After Design completion, prior to each release | State acceptance of Phase Test Plan and deliverable components identified in Column C.
3.7a | Create the Phase Test Plan to describe the testing approach for the current release, including the methods, objectives, resources, timeline, and test management for the functionality included in that release. The Test Plan will include, at a minimum: • The Contractor’s testing approach for the specific release, including unit, integration, interface, system, end-to-end, load capacity, stress, regression, production simulation, accessibility, security, white hat, and penetration testing. • Creation of release-specific test scenarios, acceptance criteria, test cases, test scripts, and their formats. • Approach and description of processes, procedures, and protocols to perform the release testing. • Identification and description of any tools the Contractor will use for testing, including automated testing. • Testing roles and responsibilities required for the specific release. • Identification of test environments, test database, and data requirements for the specific release. • How Contractor will report on test status, identify issues, and take corrective actions to ensure resolution. • Description of the specific release test result reports and how Contractor will certify that the release is fully tested.
3.7b | Create the testing schedule, milestones, and dependencies for the UAT
3.7c | Work with CDPH to plan, support, and document User Acceptance Testing
3.7d | Develop test scenarios, cases, and scripts
3.8 | Test the System (for each phase) | • System Tests • Test Results Reports • User Acceptance Testing Readiness Report • UAT Corrective Action Plan | After Design completion, prior to each release | State acceptance of testing for each release
3.8a | Test the system (excluding UAT) in accordance with the System Test Plan
3.8b | Produce test result reports for all system tests (excluding UAT).
3.8c | Produce the UAT Readiness Report and provide confirmation that: • The system has been fully tested by the Contractor and is ready for User Acceptance Testing. • The Test environment and test data has been established and the test team provided access. • Test Team users have been trained and provided all resources necessary to perform the UAT.
3.8d | Develop the UAT Corrective Action Plan
3.8e | Execute the UAT Corrective Action Plan, as needed
3.9 | System Management Plan | • System Management Plan | At the end of the Planning Phase. | State acceptance of the System Management Plan
3.9a | The Contractor shall develop a System Management Plan which will, at a minimum, cover the following items: • Mechanisms to keep security patches current. • Monitoring systems and procedures to detect attempted and actual attacks on or intrusions into CDPH data. • Procedures to monitor, analyze, and respond to security alerts. • Use and complete regular updates of commercial state-of-the-art anti-malware software. • Procedures to regularly verify the integrity of installed software.
Category 4: CAB Online Solution Implementation Tasks and Deliverables
4.1 | CAB Online System | • CAB Online System | After Training Complete Milestone for Phase 1, Phase 2, and Phase 3. | State acceptance of the CAB Online System
4.1a | The Contractor will deliver a completed, functional, and operational system that has been fully tested and has meet all the mandatory and State-opted mandatory optional requirements for Phase 1 facility types, Non-Long-Term Care (NLTC).
4.1b | The Contractor will deliver a completed, functional, and operational system that has been fully tested and has meet all the mandatory and State-opted mandatory optional requirements for Phase 2 facility types, Long-Term Care (LTC).
4.1c | The Contractor will deliver a completed, functional, and operational system that has been fully tested and has meet all the mandatory and State-opted mandatory optional requirements for Phase 3 facility types, Home Health Agency (HHA) and Hospice.
4.2 | Create Operational Readiness Plan | • Operational Readiness Plan • Operational Readiness Checklist | After Training Complete Milestone for each Phase 1, Phase 2, and Phase 3. | State acceptance of Operational Readiness Plan and Checklist
4.2a | Create the Operational Readiness Plan to identify all necessary activities and outcomes that will prepare the system and users for Go-Live. The Operational Readiness Plan will include, at a minimum: • Identification of all activities that are precursors to operational readiness. • Entrance and exit criteria for implementation stages and Go-Live. • The process to determine state, Contractor, LHJ and other stakeholder readiness. • Activities the Contractor must undertake to prepare business operations and program staff to begin using the CAB Online. • Roles, responsibilities, and staffing for the roll-out. • The process to coordinate and time training, data conversion and migration, and start-up at all sites. • Approach to create and submit operational readiness reports to the State that address readiness of all elements for all stakeholders.
4.2b | Create Operational Readiness Checklists.
4.2c | Create Operational Readiness Checklists.
4.3 | Create CAB Online Training Plan | • CAB Online Training Plan • Training Needs Assessment Report • Training Materials • Training Schedule • Training Remediation Plans | After Development (Category 3), and before System Go-Live | State acceptance of CAB Online Training Plan and deliverable components identified in Column C.
4.3a | Create a Training Plan that identifies all necessary activities and testing approaches the Contractor will take to train all audiences to use or manage the CAB Online. The Training Plan will include, at a minimum: • Identification of training audiences. • Training strategy and objectives • Detailed descriptions of the training methods, tools, courses, and formats the Contractor will use to train each audience. • Approach to evaluate Training effectiveness. • Knowledge Transfer approach, steps, and timing to transition the completed system from the Contractor responsibility to CDPH. • Process to ensure all audiences receive the training necessary to fully use all CAB Online functionality necessary for their job functions.
4.3b | Perform training needs assessment describing role-based training for all audiences.
4.3c | Develop training schedule and training courses.
4.3d | Develop and maintain Training Materials.
4.3e | Develop training remediation plans.
4.3f | Maintain the training environment, including training data creation and data refreshes.
4.4 | Train End Users | • Training Evaluation Surveys • User Training • Training Completion Report | After Development (Category 3), and before System Go-Live (and through Final System Acceptance) | State acceptance of training and delivery of Training Completion Report
4.4a | Work with CDPH to train end users in accordance with the CAB Online Training Plan.
4.4b | Develop surveys for trained users to ensure they achieved the desired level of system proficiency to be able to perform their business functions following training.
4.4c | Perform training mediation in accordance with training remediation plans, if needed.
4.4d | Create and deliver a Training Completion Report.
4.5 | Release Management Plan | • Release Management Plan | After Development (Category 3), and before System Go-Live. | State acceptance of Go-Live
4.5a | The Release Management Plan will detail the process for deploying completed system functionality up the pipeline during implementation stages through all pre-production and production environments. The Release Management Plan will include, at a minimum: • Description of the release process and procedures. • Release roles and responsibilities. • Criteria for entry into the release process, reconciliation, and sign-off. • Release naming conventions. • Schedule and activities to occur within the release period. • An escalation process for release issues. • A release validation process. • Release contingency plans.
4.6 | Conduct CAB Online System Go-Live | • Tested and Operational CAB Online System | After Development (Category 3), and before System Go-Live | State acceptance of Go-Live
4.6a | Deliver a complete, functional, and operational CAB Online system that has been fully tested and meets all functional and nonfunctional requirements and is in accordance with the Release Management Plan.
4.7 | Create Help Desk Plan | • Help Desk Plan | After Development (Category 3), and before System Go-Live | State acceptance of Help Desk Plan
4.7a | Create a Help Desk Plan to describe how the Contractor will manage the Help Desk from implementation through M&O. The Help Desk Plan will include, at a minimum: • Description of Help Desk tiers. • Roles and responsibilities of Contractor and State Help Desk staff. • Help Desk policies, processes, and procedures. • Help Desk ticket submission mechanisms, resolution, documentation, and reporting. • Approach to transfer Help Desk to CDPH staff following System Acceptance. • Plan to make sure all Help Desk SLAs are met.
4.8 | Perform Help Desk Services | • Help Desk Services | After System Go-Live of each Phase | Monthly after system go- live throughout term of the Contract
4.8a | Initiate Help Desk services in accordance with SECTION 10.4.1. Help Desk located in the Statement of Work (SOW)
4.8b | Perform Help Desk Services in accordance with +SECTION 10.4.1. Help Desk
4.9 | Update CAB Online Documentation | • Updated Requirements Traceability Matrix • Updated Architectural Design Specifications • Updated Database Design Specifications • Updated Configuration Specifications • Updated Integration and Interface Specifications •Updated Training Materials | After System Go-Live, and before Final System Acceptance | State acceptance of CAB Online updated documentation
4.9a | Update relevant CAB Online documentation to reflect “as-built” specifications as well as changes made to the system, processes, procedures, and training since they were originally created, The Updated Documentation will include, at a minimum: • Requirements Traceability Matrix • Architectural Design Specifications • Database Design Specifications • Configuration Specifications • Integration and Interface Specifications • Training Materials
4.1 | Transfer CAB Online Knowledge to State | • Knowledge Transfer Materials • Knowledge Transfer • Knowledge Transfer Completion Report | After Development (Category 3), and before System Go-Live | State acceptance of Knowledge Transfer activities
4.10a | Create Knowledge Transfer materials to support the formal training, shadowing, information-sharing, and other activities necessary for CDPH program, Help Desk, and technical teams to fully run and operate CAB Online without Contractor assistance, in accordance with the Training Plan. Knowledge transfer materials will address, at a minimum: • CAB Online technical operations. • Help Desk. • CAB Online configuration and programming.
4.10b | Perform Knowledge Transfer activities for CDPH program, Help Desk, and technical staff.
4.11 | Create and Deliver System Manuals | • CAB Online User Manual • CAB Online Quick Reference Tool • CAB Online Operations Manual • CAB Online Technical Manual • CAB Online Help Desk Manual • CAB Online Errors and Resolution Manual • CAB Online Programming Guide • CAB Online Information System Security Plan • System Technology Recovery and Business Continuity Plans | After Development (Category 3), and before System Go-Live | State acceptance of System Manuals and Plans
4.11a | Create and deliver System Manuals and reference materials that trained audiences may use as reference when using the CAB Online to perform their job functions. System Manuals include, at a minimum: • CAB Online User Manual • CAB Online Quick Reference Tool • CAB Online Operations Manual • CAB Online Technical Manual • CAB Online Help Desk Manual • CAB Online Errors and Resolution Manual • CAB Online Programming Guide • CAB Online Information System Security Plan • System Technology Recovery and Business Continuity Manual
4.12 | Create Production Support Plan | • Production Support Plan | After Phase 1 and Phase 2 Testing Complete. | State acceptance of Production Support Plan
4.12a | Create a Production Support Plan which defines the Contractor’s methodology to provide system maintenance, monitoring, and support after Phase 1 and Phase 2 go-live of the CAB Online system. This will serve as a temporary support plan until the final Maintenance & Operations (M&O) Plan is in place. • The Production Support Plan will address, at a minimum: • Approach to support day-to-day CAB Online operations. • Tools and processes used to detect and resolve system-related issues and errors. • Approach to receive, acknowledge, monitor, respond to, escalate, and resolve incidents. • Roles and responsibilities for the Contractor, CDPH staff, and Help Desk staff. • Procedures and processes to accept, review, approve, and prioritize change requests. • Approach to identify and deliver system improvements and minor functional enhancements to meet state or federally mandated system changes. CDPH communications and reporting Contractor work, accomplishments, system performance and SLA metrics, system update progress and status, and incident metrics.
4.13 | Create Stabilization Plan | • Stabilization Plan • Stabilization Status Reports | After Development and before System Go-Live | State acceptance of Stabilization Plan
4.13a | Create a Stabilization Plan that will detail the Contractors approach to stabilize the CAB Online, and ensure the system remains stable throughout the Go-Live process. The Stabilization Plan will include, at a minimum: • Roles and responsibilities of Contractor and State staff during stabilization • Timelines and schedules • Process for upgrades, unanticipated tasks, and maintenance • Process for problem resolution
4.13b | Create and deliver Stabilization Status Reports.
4.13c | Ensure System Stabilization
4.14 | Final System Acceptance | •Contractor System Certification | After Go-Live, and before Post-Implementation | State approval of Contractor System Certification
Category 5: Post-Implementation Tasks and Deliverables
5.1 | Close Out Project | • Project Closeout Plan • Project Closeout • Project Closeout Report • Final Project Schedule • Post-Implementation Assessment Report • Lessons Learned Report | After Final System Acceptance | State acceptance of Close Out artifacts
5.1a | Create a Project Closeout Plan that will detail the steps and prerequisites to formally end and close out the project. The Project Closeout Plan will include, at a minimum: • Description and timing of all Project Closeout tasks and prerequisite activities and system functionality necessary to begin them. • Identification all project closeout artifacts. • Approach to confirm that all project tasks and activities have been completed to CDPH satisfaction. • Procedures to archive product documents and artifacts. • Plan to create and deliver a Post-Implementation Assessment Report and a Lessons Learned Report.
5.1b | Close out Project in accordance with the Project Closeout Plan.
5.1c | Create a Project Closeout Report that will detail all CAB Online Project closeout tasks, final metrics, and reporting successful system turnover to CDPH. The Project Closeout Report will include, at a minimum: • Project summary and metrics. • Verification of system turnover. • Summary of knowledge transfer activities and materials given to the State.
5.1d | Create and deliver a Post-Implementation Assessment Report.
5.1e | Create and deliver a Lessons Learned Report.
5.1f | Update the Final Project Schedule.
5.2 | Maintenance & Operations Plan | • Maintenance & Operations (M&O) Plan • System Maintenance and Operations | Before Final System Acceptance | State acceptance of Maintenance & Operations Plan
5.2a | Develop a M&O Plan that will define the Contractor’s methodology to provide system maintenance, system improvements, functional enhancements, and environment monitoring across all CAB Online components and operations after Final System Acceptance. The M&O Plan will address, at a minimum: • Approach to support day-to-day CAB Online operations. • Tools and processes used to detect and resolve system-related issues and errors. • Approach to receive, acknowledge, monitor, respond to, escalate, and resolve incidents. • Roles and responsibilities for the Contractor, CDPH staff, and Help Desk staff. • Procedures and processes to accept, review, approve, and prioritize change requests. • Approach to identify and deliver system improvements and minor functional enhancements to meet state or federally mandated system changes. • CDPH communications and reporting Contractor work, accomplishments, system performance and SLA metrics, system update progress and status, and incident metrics.
5.2b | Maintain the M&O Plan through the M&O period so that it reflects current procedures and information at the end of the M&O period.
5.3 | Perform Maintenance & Operations | • Maintain and Operate the CAB Online System | After Final System Acceptance | Monthly after Final System Acceptance
5.3a | Perform maintenance and operations in accordance with the M&O Plan and SECTION 15. Maintenance and Operations (M&O) located in the Statement of Work (SOW).
5.3b | Support all system components through Stabilization, M&O, and any Optional Year Extensions exercised by the State.
Category 6: Organizational Change Management
6.1 | Develop an Organizational Change Management (OCM) Plan | • OCM Plan | After System Planning | State acceptance of OCM Plan
6.1a | Develop an OCM Plan that will define the Contractor's steps to collaborate with CDPH to gain stakeholder buy in, prepare for system adoption, and create system champions. Schedule management. The OCM Plan will address, at a minimum: • Approach to OCM communication. • Approach to identify OCM needs and outcomes. • Major OCM milestones and schedule. • Issues, risks, and decisions as they relate to OCM.
6.2 6.1 | Develop OCM Materials | • OCM Guide • OCM Report • OCM Presentations | During System Development | State acceptance of OCM Materials
6.2a 6.1a | Create and deliver OCM materials that will be used to complete the OCM task. OCM materials include, at a minimum: • OCM Guide • OCM Report • OCM Presentations • Training needs assessment • Training recommendations
6.3 6.2 | Conduct OCM Activities | Complete OCM | During System Development | State acceptance of OCM Activities

## List (hidden)
Yes
No