# Rutland Natural Resources Conservation District

# Answers to RFP Questions June 24, 2026

Q: Is there a budget for this work that RNRCD is able to share?

A: Attached is the Engineer’s COI and Project Budget Estimate dated December, 2025. Available funding for this project phase has been secured based on these estimates.

| Engineer's Opinion of Probable Costs RUSSELLVILLE ROAD CULVERT REPLACEMENT 3-Sided Precast Concrete Shrewsbury, VT SLR #12942.00003 December 2025 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| ITEM NO. | ITEM DESCRIPTION | UNIT | QUANTITY | UNIT PRICE | DOLLAR AMOUNT |
|  | Structure Excavation | CY | 1,100 | $75.00 | $82,500.00 |
|  | Structural Backfill | CY | 400 | $60.00 | $24,000.00 |
|  | Water Handling | LS | 1 | $25,000.00 | $25,000.00 |
|  | Removal of Existing Structure | LS | 1 | $10,000.00 | $10,000.00 |
|  | Cast-In-Place Reinforced Concrete | CY | 180 | $1,300.00 | $234,000.00 |
|  | Reinforcing Steel | LB | 24,000 | $3.50 | $84,000.00 |
|  | 3-Sided Precast Concrete Culvert - 19' X 8' | LS | 1 | $175,000.00 | $175,000.00 |
|  | Channel Work & Bank Treatment | LS | 1 | $50,000.00 | $50,000.00 |
|  | Roadway Reconstruction | LF | 80 | $250.00 | $20,000.00 |
|  | Crushed Stone | CY | 50 | $75.00 | $3,750.00 |
|  | Metal Guardrail | LF | 120 | $30.00 | $3,600.00 |
|  | Metal Guardrail End Section | EA | 4 | $3,000.00 | $12,000.00 |
|  | Sediment and Erosion Controls | LS | 1 | $5,000.00 | $5,000.00 |
|  | Seed & Mulch/Site Restoration | LS | 1 | $15,000.00 | $15,000.00 |
|  | Mobilization (7.5%) | LS | 1 | $55,800.00 | $55,800.00 |
|  | Clearing & Grubbing (1%) | LS | 1 | $7,500.00 | $7,500.00 |
|  | Construction Staking (1%) | LS | 1 | $7,500.00 | $7,500.00 |
|  | Maintenance and Protection of Traffic (1%) | LS | 1 | $7,500.00 | $7,500.00 |
|  | Minor Items (20%) | LS | 1 | $148,800.00 | $148,800.00 |

| PROJECT STRUCTURE COST = | $970,950.00 |
| --- | --- |
| Contingency ±25% = | $242,737.50 |
| TOTAL (ROUNDED) = | $1,220,000.00 |

Page 1 of 1

Project Budget Estimate - Russellville Road Culvert Replacement 12/12/2025

Item	Cost

| Final Design and Permitting | $ 80,000 |
| --- | --- |
| Bid Phase Services | $ 15,000 |
| Construction Phase Services | $ 50,000 |
| Construction (Major, Minor and Inflation) | $ 1,220,000 |
| TOTAL | $ 1,365,000 |

Maintenance Item	Cost	Frequency (years)

| Inspection and light channel debris clearing | $ 5,000 | 2 |
| --- | --- | --- |
| TOTAL ANNUAL |  | $ 2,500 |
| TOTAL LIFE |  | $ 187,500 |

Life Expectancy of Structure

| w/ Cast-in-Place Concrete Wingwalls | 75 Years |
| --- | --- |

Page 1 of 1